## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) Margalla | 132KV New Wah - (WAH-15) - Bahtermore (BMW-2) along with related earth switch |  |  | 25-03-2026 To 31-05-2026 (Contineous) | 25-03-2026 14:00 Hrs | 31-05-2026 14:00 Hrs | For erection & Stringing activities. (during this period, the portion of line New Wah - Bahternmore will be Isolated/ De-Energized as workingportion) | No area will be affected as 132KV GSS Bahtermore will be fed from 132KV GSS Fateh Jang side & 132KV GSS New Wah will be fed from 220KV GSS Burhan side.
7 | IESCO | IBD | NO.I | Khanna Dk | Tramari | Khanna DK | 105501 | 13-04-2026 20-04-2026 27-04-2026 | 09:00 | 14:00 | Area Planning of 11KV UC Road Feeder and 11KV Koral Feeder | Khanna DK & Surrounding area.
8 | IESCO | IBD | NO.I | Rawal | Tramari | Burma | 105502 |  |  |  |  | Burma & Surrounding area.
9 | IESCO | IBD | NO.I | Rawal | Tramari | Waheedabad | 105516 |  |  |  |  | Waheedabad & Surrounding area.
10 | IESCO | IBD | NO.I | Khanna Dk | Tramari | Rehman Enlave | Not allocated |  |  |  |  | Rehman Enlave & Surrounding area.
11 | IESCO | IBD | NO.I | Khanna Dk | Tramari | Khanna East | 105510 |  |  |  |  | Khanna East & Surrounding area.
12 | IESCO | RWP | Satellite Town | Gangal | Tramari | Khanna-II | 105514 |  |  |  |  | Khanna-II & Surrounding area.
13 | IESCO | RWP | Satellite Town | Gangal | Tramari | Al Noor Colony | 105515 |  |  |  |  | Al Noor Colony & Surrounding area.
14 | IESCO | IBD | NO.I | Tarlai | Tramari | Shareefabad | 105521 |  |  |  |  | Shareefabad & Surrounding area.
15 | IESCO | IBD | NO.I | Tarlai | Tramari | Ghouri Garden | 105513 |  |  |  |  | Ghouri Garden & Surrounding area.
16 | IESCO | IBD | NO.I | Tarlai | Tramari | Scheme-I | 105525 |  |  |  |  | Scheme-I & Surrounding area.
1 | IESCO | Rawalkot | Plandri | Plandri | 132KV GSS Plandri. | Azad Pattan | 48525 | 01.04.2026 04.04.2026 06.04.2026 08.04.2026 11.04.2026 13.04.2026 15.04.2026 18.04.2026 20.04.2026 22.04.2026 25.04.2026 27.04.2026 29.04.2026 | 07:00 Hrs | 17:00 Hrs | for Stringing of Tower Loc # 31 to 39 at 132KV SDT T/Line Azad Pattan Plandri | Azad Pattan & Surrounding area
1 | IESCO | City | Westridge | Tarnol | 132 KV F-16 | Bhadana | 14435 | 15.04.2026 25.04.2026 | 10:00 Hrs | 13:00 Hrs | D/W Modern prison H-16 Islamabad | Village bhaddana and surrounding areas
2 |  |  |  |  | 132 KV KTM | Zarkoon Heights | 008628 |  |  |  |  | Zarkoon Heights
1 | IESCO | IBD | NO.II | I-9 | I-8 | I-8/4 | 61121 | 04-04-2026 07-04-2026 13-04-2026 27-04-2026 | 08:00 | 13:00 | HT Proposal for Bifurcation of I-8 Markaz Feeder Emanating from 132KV I-8 Grid Station Under DOP Head 2K25412DOPHT52 | I-8/4
2 | IESCO | IBD | NO.II | I-9 | I-8 | I-8 MKZ | 61129 |  | 08:00 | 13:00 |  | I-8 MKZ
3 | IESCO | IBD | NO.II | I-9 | I-8 | CCC-II | 61135 |  | 08:00 | 13:00 |  | CCC-II
17 | IESCO | IBD | No.II | F-8 | G-9 | F-8/1 | 122317 | 02.04.2026 '04-04-2026 18-04-2026 | 08:00 | 13:00 | Removal of HT Fault on 11 KV Centaurus Hotel Feeder | Sector F-8/1
18 | IESCO | IBD | No.II | F-8 | G-9 | F-8 Markaz | 122316 |  | 08:00 | 13:00 |  | Sector F-8
19 | IESCO | IBD | No.II | G-7 | G-9 | Meezan Bank | 122321 |  | 08:00 | 13:00 |  | Independent
20 | IESCO | IBD | No.II | F-8 | G-9 | HC3 Pims | 122324 |  | 08:00 | 13:00 |  | Independent
21 | IESCO | IBD | NO.II | F-8 | F-11 | F-10 MKZ | 069208 | 08-04-2026 14-04-2026 20-04-2026 | 08:00 | 13:00 | Estimate for Reconductoring of 11 KV F-10 Feeder From ACSR Rabbit to ACSR DOG From Street No.63 F-10/3 to Gull Plaza F-10 Markaz Islamabad 2k25412DOPHT03 | F-10 MKZ
22 | IESCO | IBD | NO.II | F-8 | F-11 | F-10 | 069203 |  | 08:00 | 13:00 |  | F-10
23 | IESCO | IBD | NO.II | F-8 | F-11 | F-10/3 | 069212 |  | 08:00 | 13:00 |  | F-10/3
1 | IESCO | Jhelum | Jhelum-II | Sanghoi | 132KV Sanghoi | New Sanghoi | 126302 | 06.04.2026 11.04.2026 15.04.2026 25.04.2026 30.04.2026 | 0700 | 1200 | Stringing of 11 KV Sanghoi Feeder | Sanghoi & Surrounding area
2 | IESCO | Jhelum | Jhelum-II | Sanghoi | 132KV Sanghoi | Chotala | 126303 |  | 0700 | 1200 |  | Chotala & Surrounding area
3 | IESCO | Jhelum | Jhelum-II | Sanghoi | 132KV Sanghoi | Khai Khulia | 126301 |  | 0700 | 1200 |  | Khai Kullian & Surrounding area
6 | IESCO | Jhelum | Jhelum-1 | Civil line | 132KV Jhelum | Akram Shaheed | 7719 | 18.04.2026 27.04.2026 | 0700 | 1200 |  | Akram Shaheed & Surrounding area
7 | IESCO | Jhelum | Jhelum-1 | Cantt | 132KV Jhelum | Zubair Shaheed | 7717 |  | 0700 | 1200 |  | Zubair Shaheed & Surrounding area
8 | IESCO | Jhelum | Jhelum-II | Rural | 132KV Jhelum | City Housing | 7729 | 06.04.2026 11.04.2026 15.04.2026 22.04.2026 29.04.2026 | 0700 | 1200 | Errection of poles and stringing of ADS-IV Jhelum | City Housing Jhelum
9 | IESCO | Jhelum | Jhelum-II | Sanghoi | 132KV Jhelum | Sanghoi | 7712 |  | 0700 | 1200 |  | Sanghoi & Surrounding area
10 | IESCO | Jhelum | Jhelum-II | Sanghoi | 132KV Jhelum | Safdar Shaheed | 7722 |  | 0700 | 1200 |  | Safdar Shaheed
11 | IESCO | Jhelum | Jhelum-II | Sanghoi | 132KV Jhelum | Nathwala | 7716 |  | 0700 | 1200 |  | Nathwala & Surrounding area
12 | IESCO | Jhelum | Jhelum-I | Cantt | 132KV Jhelum | LangarPur | 7725 |  | 0700 | 1200 |  | Langar pur & Surrounding area
14 | IESCO | Jhelum | Jhelum-2 | Rural | 132KV Jhelum | Pakhwal | 7720 | 08.04.2026 11.04.2026 14.04.2026 21.04.2026 25.04.2026 28.04.2026 | 0700 | 1200 | 11KV Pakhwal Feeder | Village Pakhwal, Chak Daulat
15 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.2 (Chip Board) | 7702 |  | 0700 | 1200 |  | Kala Gurjan Ehsan Road Etc
16 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | Industrial | 7721 |  | 0700 | 1200 |  | S.I.E. Rathain & Surrounding area
17 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.10 ( Kala Base) | 7710 |  | 0700 | 1200 |  | Kala Gurjan Ehsan Road Etc
18 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | Jakkar | 7714 | 18.04.2026 21.04.2026 25.04.2026 28.04.2026 | 0700 | 1200 | 11KV Jakkar Feeder | Village Jakkar, Khokhar Agar Khan & Surrounding area
19 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.9 (Chak Daulat) | 7709 |  | 0700 | 1200 | 11KV Chak Daulat Feeder | Village Chak Daulat & Surrounding area
20 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Abdullah Pur | 058206 | 02.04.2026 09.04.2026 16.04.2026 23.04.2026 28.04.2026 | 0700 | 1200 | Shifting of line Lillah Jhelum road | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
21 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Jalal Pur | 058203 |  | 0700 | 1200 |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
22 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Sagharpur | 058202 |  | 0700 | 1200 |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
23 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | C.W.O. | 058204 |  | 0700 | 1200 |  | Army Area - Civil Work Organization.
24 | IESCO | Chakwal | P.D.Khan | Daryala Jalip | Pinanwal | DHARYALA JALIP | 058205 | 09.04.2026 28.04.2026 | 0700 | 1200 |  | Chak Mujahid, Dharyala Jalip, Khothian Jalip, Dera Khothian, Mirza Pur, Karim Pur, Jaiti Pur, Azam Pur, Burj Sattar, Fateh abad, Chak Hameed, Dhingwal, Chak Ali Shah, Adowal
25 | IESCO | Chakwal | P.D.Khan | Daryala Jalip | Dandot | Duffer | 29001 | 07.04.2026 14.04.2026 21.04.2026 30.04.2026 | 0700 | 1200 |  | P.D Khan. Katchery etc
26 | IESCO | Chakwal | P.D.Khan | P.D.Khan | Dandot | P.D. Khan | 29005 |  | 0700 | 1200 |  | P.D Khan. Katchery etc
27 | IESCO | Cantt | Mandra | Wadala | Rawat | Basali | 017728 | 04.04.2026 07.04.2026 16.04.2026 21.04.2026 30.04.2026 | 0700 | 1200 | Erection of Poles /Fitting & Stringing of HT Conductor iro Deposit Feeder EXIMPO Cool Chains Pvt Ltd.Cold Storage at Haraka | BASALI, MOHRA KOTIAN, DK GURHA, DK JUMMA, CHANDNI CHOWK & Surrounding area
28 | IESCO | Cantt | Tariqabad | Adyala | 500 KV New Rawat | Jarar Camp | 064510 | 04.04.2026 07.04.2026 11.04.2026 16.04.2026 | 0700 | 1200 |  | JARAR CAMP & SURROUNDING AREA
29 | IESCO | Cantt | Mandra | Chak Beli Khan | 500 KV New Rawat | Bhall | 064507 |  | 0700 | 1200 |  | BHALL & SURROUNDING AREA
30 | IESCO | Cantt | Mandra | Wadala | 500 KV New Rawat | Jatha Hathial | 064503 |  | 0700 | 1200 |  | JHATHA HATHIAL, NAKRALI, CHAPPER, JABBAR MIANA, LARRI MALANA & Surrounding area
31 | IESCO | Cantt | Mandra | Mandra | 500 KV New Rawat | Ghumti | 064512 | 17.04.2026 | 0700 | 1200 | For Completion of Safety Hazard works | Mohra Mandoo, Kuri Dolal, Ghumti, Noor Dolal, Karyali, & Surrounding area
37 | IESCO | Jhelum | Jhelum-II | Sanghoi | Sanghoi | Khai Kulia | 126301 | 13.04.2026 20.04.2026 25.04.2026 | 0700 | 1200 | Completion of Depsoit work Shifting of HT/LT Line Lillah to PD Khan Road | Khai Kula , Bin Shaheed, Daryala & Surrounding area
38 | IESCO | Jhelum | Jhelum-II | Sanghoi | Jhelum | Nathwala | 7716 |  | 0700 | 1200 |  | Maloot, Watalian, Potha, Badlot, Daryala, Village Jango,. Kot Baseera,
39 | IESCO | Jhelum | Jhelum-II | Sanghoi | Jhelum | Sanghoi | 7712 |  | 0700 | 1200 |  | Sanghoi & Surrounding area
40 | IESCO | Jhelum | Jhelum-II | Sanghoi | Jhelum | Safddar Shaheed | 7722 |  | 0700 | 1200 |  | Nawan Lok, Chotala, Khurd, Rasool Nagar, Bhimber & Surrounding area
41 | IESCO | Jhelum | Gujar Khan | City Gujar khan | Gujar Khan | Karoli | 4920 | 22.04.2026 28.04.2026 | 0700 | 1200 | For Completion of Safety Hazard works | W.No.19, DK. Waheeklan
42 | IESCO | Jhelum | Gujar Khan | City Gujar khan | Gujar Khan | Matwa | 4906 | 23.04.2026 | 0700 | 1200 |  | Nigial Umer Khan,Qazian Road,Matwa, Dumma & Surrounding area
1 | IESCO | IBD | B/Kahu | Murree | 132KV Kuldana Murree | Kuldana | 13702 | 06.04.2026 14.04.2026 20.04.2026 | 09:00 | 14:00 | Removal / Shifting of services remodling of Jhika Gali Chowk Tehsil & District Murree | Mall Road, Kashmir Point and Mashyari.
2 | IESCO | IBD | B/Kahu | J/Gali | 132KV Kuldana Murree | GHARIAL | 13711 |  | 09:00 | 14:00 |  | J/gali Bazar Gjarial camp.Kashmiri Bazar,seher bagla Aliot
7 | IESCO | IBD | B/Kahu | B/K (R) | 132/220 KV G/S B/Khu | Tret | 89203 | 06.04.2026 20.04.2026 | 09:00 | 14:00 |  | Nai Abadi,Country Form
10 | IESCO | IBD | B/Kahu | B/K (U) | 132/220 KV G/S B/Khu | Shahpur | 89218 | 07-04-2026 09-04-2026 13-04-2026 22-04-2026 29-04-2026 | 09:00 | 14:00 | Stringing of HT line/ Installation of HT Structure 58' Beneath the existing HT lines in IRO Bifurcation of 11KV Shah Pur Feeder /Strinning of HT line in R/O External Electrification of Park View City Housing Society | Bhara Kahu Bazar, Sanjalian and Surrounding Area
11 | IESCO | IBD | B/Kahu | B/K (U) | 132/220 KV G/S B/Khu University | N.I.H | 89210 |  | 09:00 | 14:00 |  | Malpur, Lake view, Banigala, NIH, Dk. Jillani, LVL, Dk. Mohri.
12 | IESCO | IBD | B/Kahu | B/K (U) | 132/220 KV G/S B/Khu University | T&T | 89204 |  | 09:00 | 14:00 |  | Mangoo Town, 17 Meel, Abdullah Town.
13 | IESCO | IBD | B/Kahu | B/K (U) | 132/220 KV G/S B/Khu | B/ Khu-I | 89201 |  | 09:00 | 14:00 |  | Bhara Kahu Bazar, Sanjalian and Surrounding Area
14 | IESCO | IBD | B/Kahu | B/K (U) | 132/220 KV G/S B/Khu | B/ Khu-II | 89219 |  | 09:00 | 14:00 |  | Madina Town, Nain Sukh,and Surrounding Area
15 | IESCO | IBD | B/Kahu | B/K (R) | 132/220 KV G/S B/Khu | Tret | 89203 |  | 09:00 | 14:00 |  | Nai Abadi,Country Form
16 | IESCO | IBD | B/Kahu | B/K (R) | 132/220 KV G/S B/Khu | Golf city | 89216 |  | 09:00 | 14:00 |  | Golf City
17 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Park View | 122511 |  | 09:00 | 14:00 |  | Park View city
18 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Athal | 89217 |  | 09:00 | 14:00 |  | Simly dam road , Athal Road, Tumair, Athal.
19 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | Kurri | 105506 | 21-04-2026 28-04-2026 | 09:00 | 14:00 | Federal Urdu University at Kurri Road Zone-IV Near Bahria Enclave Islamabad | Kuri Sher.
20 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | Rehara | 105511 |  | 09:00 | 14:00 |  | Mohra Noor, Rehara
21 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | CM Pak Zong | 105509 |  | 09:00 | 14:00 |  | Office of CM PAK
3 | IESCO | Cantt | Rawat | Sagri | 132 KV Rawat | Sagri | 98102 | 11.04.2026 14.04.2026 16.04.2026 | 9:00 | 12:00 | For 11 KV Sagri Feeder Work | DHA Homes & sorrounding area
5 | IESCO | Cantt | Rawat | Kallar | 132 KV Kallar | Doberan | 098106 | 08.04.2026 19.04.2026 | 9:00 | 12:00 | For completion of Safety Hazard Work at Nisar Colony Kallar Syedan | Doberan & sorrounding area
4 |  | Attock | Taxila | Sangjani | 220KV Sangjani | Paswal | 81002 | 15.04.2026 20.04.2026 | 09:00am | 11:00pm | Shifting of HT Line of NHA | Paswal, Jandu
9 |  | Attock | Taxila | Taxila | 132KV Taxila | HMC Road | 21227 | 14.04.2026 16.04.2026 | 09:00am | 11:00pm | LV Ayubia Town | HMC Road
1 | IESCO | City | Westridge | Westridge | KTM | Dk. Chaudrian | 008621 | 04.04.2026 07.04.2026 11.04.2026 14.04.2026 23.04.2026 | 07:00 | 12:00 | Emergency work Peshawar road underpass project | Lane No. 04, 05 Range road and surrounding areas
2 | [5 empty] | Peshawar Road | 008612 |  |  |  |  | Peshawar Road Lane No. 04 to 07, Mehboob Lane, Fazeelabad and surrounding areas
3 | [5 empty] | Millatabad | 008616 |  |  |  |  | Misrial Road, Ilyas Colony, Lane 1,2,3 and surrounding areas
4 | [5 empty] | Cheering Cross | 008602 |  |  |  |  | Gulnar colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding areas
5 | [5 empty] | NRC | 008622 |  |  |  |  | Westridge bazar, Hali Road, Iqbal Road, Churr Chowk Race Course ground and surrounding areas
6 |  |  |  |  | Pirwadhai | COB Lane | 043329 |  |  |  |  | Cob lane and surrounding areas
7 |  |  |  | Misrial |  | Askari-XI | 043325 |  |  |  |  | Askari-XI, Lane No. 01 to 07, St. No. 01 to 14 and surrounding areas
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Cantt | Khadim Hussain Road | 17906 | 05.04.2026 12.04.2026 19.04.2026 | 9:00 | 12:00 | For Construction of GPO Underpass Signal Free Mall Road Project Part A Rawalpindi | Khadim Hussain Road
2 |  |  |  | Tariqabad |  | CMH Flats | 17936 |  |  |  |  | CMH Flats
3 |  |  | Cantt | Civil Line |  | Adam Jee Road | 17923 |  |  |  |  | Adam Jee Road
4 |  |  |  | Civil Line |  | Askari 7 | 17919 |  |  |  |  | Askari 7
5 |  |  |  | Civil Line |  | Sir Syed Road | 17913 |  |  |  |  | Sir Syed Road
6 |  |  |  | Saddar |  | FFC | 17927 |  |  |  |  | Fauji Fertilizer
7 |  |  | Tariqabad | R.A Bazar |  | GHQ Express | 017924 |  |  |  |  | GHQ & sorrounding area | Subject to provision of NOC from GHQ
8 |  |  |  | Tariqabad | 132KV Chaklala | State Bank | 2521 |  |  |  |  | State Bank
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | R.E New Wah | 132KV New Wah (WAH-5) to POF POF South (POS-4) along with related earth switch |  |  | 05-04-2026 To 26-04-206 (Contineous) | 05-04-2026 08:00 Hrs | 26-04-2026 16:00 Hrs | For safety Purpose for erection and stringing of conductor between Loc No. 07 To 12 for remodeling work of 132KV T/Line POF East, West & North | on 05-04-2026 from 08:00 Hrs to 16:00 Hrs 132KV GSS South, East, West & North will be affected & After that No area will be affected. However, all 132KV GSS South, East, West & North will be fed from WAH-6, which PTW will be cancelled on 05-04-206 at 16:00 Hrs.
1 | IESCO | City | Westridge | Tarnol | 132 KV F-16 | Eighteen | 111405 | 08.04.2026 16.04.2026 | 09:00 Hrs | 12:00 Hrs | D/W Modern Priosn H-16 Islamabad | Eighteen and surrounding area
1 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Attock Cantt | 18901 | 07.04.2026 12.04.2026 16.04.2026 21.04.2026 | 07:00 | 12:00 | Shifting of line from existing line to new proposed HT structure 58 IRO 11KV independent Feeder MCH Attock | Attock Cantt & Surrounding Area
2 | IESCO | Attock | Attock |  |  | Dhoke Fteh | 18911 |  | 07:00 | 12:00 |  | Dhoke Fateh & Surrounding Area
3 | IESCO | Attock | Attock |  |  | Dar ul Islam Colony | 18909 |  | 07:00 | 12:00 |  | Dar ul Islam Colony & Surrounding Area
4 | IESCO | Attock | Attock |  |  | Katchery | 18902 |  | 07:00 | 12:00 |  | Katchery & Surrounding Area
6 | IESCO | Attock | Attock | Attock City | 132KV Attock | Attock Rural | 75101 | 08.04.2026 11.04.2026 20.04.2026 25.04.2026 30.04.2026 | 07:00 | 12:00 | Reconducting of 3-Meela Feeder | Attock, Takbeer Colony & surrounding area
7 | IESCO | Attock | Attock |  |  | Teen Mela | 75113 |  | 07:00 | 12:00 |  | Teen Mela & Surrounding Area
8 | IESCO | Attock | Attock |  |  | Bagh Nelab | 75114 |  | 07:00 | 12:00 |  | Bagh Nelab & Surrounding Area
9 | IESCO | Attock | Attock | Attock City | 132KV Attock | Fawara Chowk | 75103 | 13.04.2026 28.04.2026 | 07:00 | 12:00 | Replacement of Old Conductor & Pole Under Beautification of Attock | A.B.C.R Block, City area, Lorry area & surrounding area
2 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | APF | 96808 | 09.04.2026 13.04.2026 23.04.2026 | 07:00 | 12:00 | For stringing jumpering of HT line IRO Electrification of Qurtaba City Chakri Road Rawalpindi | APF & surrounding area
3 | IESCO | Cantt | Tariqabad |  |  | SPD | 96806 |  | 07:00 | 12:00 |  | SPD & surrounding area
4 | IESCO | Cantt | Tariqabad |  |  | Paryal | 96809 |  | 07:00 | 12:00 |  | Paryal & surrounding area
5 | IESCO | Cantt | Tariqabad |  |  | Chakri | 96801 |  | 07:00 | 12:00 |  | Chakri & surrounding area
6 | IESCO | Cantt | Tariqabad |  |  | HASCOL | 96812 |  | 07:00 | 12:00 |  | Hascol & surrounding area
7 | IESCO | Cantt | Tariqabad | Adiala | 132KV Adiala | Khasala | 109108 | 08.04.2026 16.04.2026 | 07:00 | 12:00 | For completion of work IRO LV Work Old Abadi Gorakh Pur | Khasala & Surrounding areas
9 | IESCO | Cantt | Tariqabad | Adiala | 132KV Adiala | Rose Lane | 109105 | 29.04.2026 | 07:00 | 12:00 | For installation of 200 KVA T/F IRO Caltex Road | Rose Lane & sorrounding area
10 | IESCO | Cantt | Tariqabad | Q.A Colony | 132 KV Kamalabad | Gulshan e Saeed | 001024 | 15.04.2026 18.04.2026 | 07:00 | 12:00 | For installation of T/F IRO Al Mehboob Colony | Thallian ,Dhoke Sama.Pelo .ect
11 | IESCO | Cantt | Tariqabad | Q.A Colony | 132 KV Ranyal | Qureshiabad | 120401 | 20.04.2026 25.04.2026 | 07:00 | 12:00 | For Stringing of HT Line IRO Boston Town Near Yasir LV work | Qureshiabad & sorrounding area
12 | IESCO | Cantt | Tariqabad | Q.A Colony | 132KV Ranyal | Hayal | 120402 | 21.04.2026 27.04.2026 | 07:00 | 12:00 | For removal of Safety Hazard IRO Ahle Mohalla Gulistan e Fatima | Hayal & sorrounding area
13 | IESCO | Cantt | Tariqabad | Dhamial |  | Gulistan e Fatima | 120403 |  | 07:00 | 12:00 |  | Gulistan e Fatima & sorrounding area
14 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Paryal | 96809 | 22.04.2026 28.04.2026 30.04.2026 | 07:00 | 12:00 | For removal of Safety Hazard IRO ABC Cable Paryal Village | Paryal & surrounding area
1 | IESCO | City | S.Town | Chandni Chowk | 132 KV I-8 | A-Block | 061104 | 11.04.2026 15.04.2026 22.04.2026 | 09:00 | 12:00 | Shifting of underground 11KV National Market Feeder to overhead near 6th road Rawalpindi | A-Block, Dk. Paracha, C-Block, Murree Road and surrounding areas
2 |  |  |  |  | 132 KV Satellite Town | National Market | 095822 |  |  |  |  | National Market, Asghramall Scheme and surrounding areas
3 |  |  |  | Sadiqabad |  | C-Block | 095831 |  |  |  |  | C-Block, Dk. Khillo, Kurri Road and surrounding areas
4 | [5 empty] | Sadiqabad | 095815 |  |  |  |  | Dk. Babu Irfan, Sadiqabad, Muslim town, Affandi Colony and surrounding areas
5 | [5 empty] | Affandi Colony | 095808 |  |  |  |  | Sadiqabad, Muslim town, Affandi Colony and surrounding areas
6 |  |  | City | Asgharmall |  | Asgharmall | 095805 |  |  |  |  | Asgharmall and surrounding areas
1 | IESCO | City | Westridge | Tench Bhatta | 132 KV Kamalabad | Tench Bhatta | 107607 | 16.04.2026 23.04.2026 25.04.2026 | 10:00 Hrs | 13:00 Hrs | Installation of ABC Cable | Jaan Colony, Tench Bazar and surrounding area
1 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | Old Rawat | 17716 | 11.04.2026 15.04.2026 18.04.2026 25.04.2026 29.04.2026 | 07:00 | 12:00 | For shifting of HT line from T-Chowk to HASCOL Pump T-Chowk Flyover | Rawat & sorrounding area
2 | [5 empty] | New Rawat | 17701 |  | 07:00 | 12:00 |  | Rawat & sorrounding area
3 |  |  |  |  | 500KV New Rawat | AOWHS | 64506 |  | 07:00 | 12:00 |  | Emaar & sorrounding area
4 |  |  |  |  | 132KV Old Rawat | Suparco | 17717 |  | 07:00 | 12:00 |  | Suparco & sorrounding area
5 |  |  | Rawat | Sagri |  | DHA Homes | 17725 | 15.04.2026 22.04.2026 | 07:00 | 12:00 | For shifting of HT Line a DHA Homes Deposit Work | DHA Homes & sorrounding area
12 |  |  | Cantt | Sowan | 132KV Sowan | Fouji Foundation | 87405 | 19.04.2026 26.04.2026 | 07:00 | 12:00 | For re-conductoring of FFH Hospital | Fauji Foundation & Surrounding area
13 |  |  |  | Sowan |  | Mora Nagial | 87422 |  | 07:00 | 12:00 |  | Mohra Nagiyal and Surrounding area.
14 |  |  |  | Morgah |  | Morgah | 87406 |  | 07:00 | 12:00 |  | Morgah, Park View and Surrounding area.
15 |  |  |  | Sowan |  | Walayat Complex | 87412 |  | 07:00 | 12:00 |  | Walayat Complex and Surrounding area.
1 | IESCO | Attock | Taxila | Wah Cantt | 132KV New Wah Grid | Small Industrial Easte | 14625 | 11.04.2026 18.04.2026 21.04.2026 25.04.2026 | 08:00 | 16:00 | for safety purpose during ereection and stringing of conductor from location No. 02 to 13 for remodeling of 132kv T/Line POF East, West and North. | Lala Rukh, Basti, Uppal Chokw
2 |  |  |  | Mora Chowk |  | Lala Rukh | 14622 |  |  |  |  | Lala Rukh & Surrounding area
3 | [5 empty] | Garhi Afghan | 14626 |  |  |  |  | Garhi afghana, Malpur, Budhu
4 | [5 empty] | Lal zar | 14607 |  |  |  |  | Lala zar, gulshan colony
5 |  |  |  | Khan pur |  | Khan pur | 14606 |  |  |  |  | Khan Pur & Surrounding area
6 |  |  |  | Mora Chowk |  | AWC Housing | 14624 | 09.04.2026 |  |  |  | AWC Housing
7 | [5 empty] | Rashid Minhas | 14620 |  |  |  |  | village Lab, Sultan pur & Surrounding area
1 | IESCO | Jhelum | Gujar Khan | Sohawa | Gujar Khan | Bhai Khan | 4919 | 24.04.2026 | 0900 Hrs | 1100 Hrs | for Completion of LV work Daryala Khaki | Jand Mehloo, Laddr, Daryala Khaki, Jermote etc
2 | IESCO | Jhelum | Gujar Khan | Sohawa | 132kv Gujar Khan | Nai Khangah | 125004 | 27.04.2026 | 1100 Hrs | 1300 Hrs | for Completion of LV work Dhari | Sehala Minhas , Nai Khangah, Miani Bala etc
3 | IESCO | Jhelum | Gujar Khan | Sohawa | 132 KV Sohawa | Pind Mattay Khan | 125003 | 29.04.2026 |  |  | for Completion of LV work Khabal Awan | Koken Jhand, Aheer, Jhand Mehloo, Bhalote, Dhoke Badar Din, Jabbo Kassi etc.
4 | IESCO | Jhelum | Gujar Khan | Guliana | Gujar Khan | Kountrilla | 4917 | 30.04.2026 |  |  | for Completion of LV work Baba Jawan | Jero Ratial,Kharli Bangial,Mohri Rajgan,Dk Amb,
1 | IESCO | City | Westridge | MES | Pirwadhai | COB Lane | 043329 | 11.04.2026 14.04.2026 23.04.2026 | 07:00 | 15:00 | for Stringing of 132KV newly erected Poleas from Loc # 32 to 37 | Cob lane and surrounding areas
2 |  |  |  | Misrial |  | Askari-XI | 043325 |  |  |  |  | Askari-XI, Lane No. 01 to 07, St. No. 01 to 14 and surrounding areas
3 |  |  |  | Westridge | KTM | Cheering Cross | 008602 |  |  |  |  | Gulnar colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding areas
1 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | Sector-IV | 002536 | 13.04.2026 16.04.2026 20.04.2026 23.04.2026 27.04.2026 30.04.2026 | 07:00 | 12:00 | Stringing of Work IRO Bifurcation of 11KV Dk. Gangal feeder emanating from 132KV Chaklala GSS under ELR Head (2k26-431 ELT-HT-01) | Airport Housing Society, Sector-4 (I.G.H Block) & Surrounding area.
2 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | APHS | 002526 |  |  |  |  | Airport Society, Dk. Anwar & Surrounding area.
3 | IESCO | Cantt | Chaklala | Chaklala | 132KV Chaklala | Rehmatabad-1 | 002519 |  |  |  |  | Rehmatabad-1 & Surrounding area
4 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | PAF | 002509 |  |  |  |  | PAF & Surrounding area.
5 | IESCO | City | Taeiqabad | Adyala | 132KV Adyala | Adyala | 109106 | 11.04.2026 14.04.2026 22.04.2026 |  |  | for Stringing of Work IRO Area Planning of 11KV Shahpur & Dk. Noor feeder | Adyala & Surrounding area.
6 | IESCO | City | Taeiqabad | Adyala | 132KV Adyala | Dk. Noor | 109104 |  |  |  |  | Dk. Noor & Surrounding area.
7 | IESCO | Cantt | Taeiqabad | Adyala | 132KV Adyala | Samarzar | New |  |  |  |  | Samarzar & Surrounding area.
1 | IESCO | Chakwal | Chakwal | Main Bazar | Chakwal | ISLAMIA CHOWK | 2223 | 16.04.2026 18.04.2026 21.04.2026 28.04.2026 | 8:00 | 11:00 | For Dismantling Poles D/Work Shifting of Pole for restoration / improvement of Chakwal to Kallar Kahar Road (Road Widening Project) | Moti Bazar, Islamia Chowk to Bhoun Chowk, Nia Mohallah, Khumeni Chowk, Moh: Gharbi, Moh: Khawajgan, Sarpak, Kot Ganish Eid Gah,
2 | IESCO | Chakwal | Chakwal | Main Bazar | Chakwal | MAIN BAZAR | 2214 | 22.04.2026 25.04.2026 30.04.2026 |  |  |  | Main Bazar, Chappar Bazar Talagang Road, Jhelum Road, Ali Masjid, Moh: Ghosia, Moh: Farooqi, Hospital Road, Old Sabzi Mandi, Moh: Hajveri, Tatral Hotel, Dhok Hayat, Sabzi Mandi, Moh: Grid Station etc
1 | IESCO | IBD | XEN-I | Tarlai | 132 KV Tramri | Kund Rajgan | 105522 | 15-04-2026 24-04-2026 | 9:00 | 0:00 | External Electrification work IRO IT Technology Park Chak Shahzad | Chatta Baktawar and surrounding area
2 |  |  |  |  | 132KV Rawal | Scheeme-II | 17430 |  |  |  |  | Scheeme-I & Scheeme-II
1 | IESCO | Attock | Attock | Hazro | 132 KV Faqirabad | Shah Dher | 12013 | 14.04.2026 16.04.2026 | 12:00 | 14:00 | Dk:Jungle Shah Dher and Nr: Old Masjid Shah Dher installation of T.F | Shah Dher, Sarwana, Khagwani & surrounding area
1 | IESCO | Attock | Taxila | Hassan Abdal | 132 KV GSS New Wah | Burhan | 014601 | 14.04.2026, 16.04.2026 | 12:00 Hours | 14:00 Hours | Shifting of HT/LT line under safety hazards Program. | Nikoo Bafad,Kola ,Bai,Jallo,Tass and sorrunding area
1 | IESCO | IBD | B/Kahu | J/Gali | 132KV Kuldana Murree | Gharial | 13711 | 23.04.2026 30.04.2026 07.05.2026 | 09:00 | 14:00 | Removal / Shifting of services remodling of Jhika Gali Chowk Tehsil & District Murree | J/gali Bazar Gjarial camp. Kashmiri Bazar,seher bagla Aliot
1 | IESCO | City | Westridge | Tarnol | KTM | Golra | 018906 | 18.04.2026 23.04.2026 | 07:00 | 12:00 | Deposit Work A.Q Khan Research Laboratory | Naseerabad, Awan Colony & Surrounding area
2 | IESCO | City | Westridge | Tarnol | KTM | Azharabad | 008620 |  |  |  |  | Peshawar Road, Pind Paracha & Surrounding area.
3 | IESCO | City | Westridge | Tarnol | KTM | New Azharabad | [5 empty] | Peshawar Road, Pind Paracha & Surrounding area.
4 | IESCO | City | Westridge | Tarnol | KTM | Zarkoon Heights | 008628 |  |  |  |  | Zarkoon Heights
5 | IESCO | City | Westridge | Tarnol | KTM | Shamas Colony | 104903 |  |  |  |  | H-13 & Surrounding area
6 | IESCO | City | Westridge | Tarnol | KTM | Quaid-e-Azam Hospital | 008624 |  |  |  |  | Quaid-e-Azam International Hospital
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 16-04-2026 To 15-05-2026 (Contineous) | 16-04-2026 18:00 Hrs | 15-05-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 60 to 70 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | Attock | Taxila | Sangjani | 132KV B17 | Saray Kharboza | 121802 | 16.04.2026 21.04.2026 23.04.2026 28.04.2026 | 09:00am | 12:00pm | LV/ Safety Hazard works | Saray Kharboza
2 |  |  |  |  | 220KV Sangjani | Shah Allah Ditta | 81011 | 20.04.2026 22.04.2026 24.04.2026 |  |  | LV/ Safety Hazard works | Shah Allah Ditta Dk Abbasi
3 |  |  |  |  | 220KV Sangjani | Sangjani | 81003 | 15.04.2026 20.04.2026 |  |  | LV works Dhoke Billa | 11KV Sangjani
5 |  |  |  | Marglla | 132KV Margalla | Jalalla | 83304 | 16.04.2026 21.04.2026 23.04.2026 28.04.2026 | 09:00am | 12:00pm | LV J Hussain Abad and Malik Abad | Jameel Abad Jalalla
6 |  |  |  |  | 132KV Margalla | Mushtaq Hussain | 83308 |  |  |  |  | Faisal Iqbal Twon
7 |  |  |  | Taxila | 132KV Taxila | Nawazish Shaheed | 21221 | 15.04.2026 20.04.2026 22.04.2026 27.04.2026 29.04.2026 |  |  | LV Moh: Banni and Village missain | Gulshan Colony
8 |  |  |  |  | 132KV Taxila | Sher Shah Suri | 21217 |  |  |  | LV Abdullah Abad and Gohar Abad | Taxila
1 | IESCO | Cantt | T/Abad | Dhaimial | 132KV Ranyal | Moorat | 120405 | 20.04.2026 28.04.2026 | 07:00 | 12:00 | for installation of Poles & stringing of HT Conductor iro Capital Smart City | Moorat & Surrounding areas
2 | [5 empty] | Kohala | 120404 |  |  |  |  | Khasala & Surrounding areas
3 | [5 empty] | Fatima Jinnah | 120408 |  |  |  |  | Fatima Jinnah
4 | IESCO | Cantt | Cantt | Korang | 132KV NPF | NPF-I | 090003 | 18.04.2026 25.04.2026 28.04.2026 | 07:00 | 12:00 | For erection of poles IRO 11 KV Independent Feeder IRO Fedeation Employees Housing Society Lohi Bher Islamabad | NPF & Surrounding areas
5 | [5 empty] | NPF-II | 090004 |  |  |  |  | NPF & Surrounding areas
6 | [5 empty] | Doctor Town | 090016 |  |  |  |  | Doctor Town
7 | [5 empty] | PWD-I | 090014 | 25.04.2026 28.04.2026 |  |  |  | PWD'& Surrounding areas
8 | [5 empty] | PWD-II | 090015 |  |  |  |  | PWD'& Surrounding areas
1 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | Sector-IV | 002536 | 20.04.2026 27.04.2026 05.05.2026 09.05.2026 | 07:00 | 12:00 | For realignment of 11 KV HT Poles - Dry Port Road Rawalpindi | Airport Housing Society, Sector-4 (I.G.H Block) & Surrounding area.
2 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | APHS | 002526 |  |  |  |  | Airport Society, Dk. Anwar & Surrounding area.
3 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Rehmatabad-I | 2519 |  |  |  |  | Rehmatabad & sorrounding area
4 | [5 empty] | Chaklala | 2503 |  |  |  |  | Rehmatabad & sorrounding area
5 | [5 empty] | Takbeer-I | 2543 |  |  |  |  | Takbeer Project & sorrounding area
6 | [5 empty] | Takbeer-II | [5 empty] | Takbeer Project & sorrounding area
7 | [5 empty] | Takbeer-III | [5 empty] | Takbeer Project & sorrounding area
8 | [5 empty] | Kot Jabbi | 2539 |  |  |  |  | Kot Jabbi & sorrounding area
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | R.E New Wah | 132KV New Wah (WAH-5) to POF (North) to POF South and New Wah (WAH-6) to POF East along with related earth switch |  |  | 19-04-2026 | 07:00 Hrs | 13:00 Hrs | For Energization of 01No.Power T/F and 02 No. Line Bays at 132KV POF South (WAH-6) & POF East. | No area will be effected as all POF Grids will be fed through 11KV Generation POF Power House
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | R.E Zeropoiint | 31.5/40MVA Power Transformer T-1 At 132KV GSS Zeropoint |  |  | 18-4-2026 | 09:00 Hrs | 16:00 Hrs | For replacement of 132KV Lightening Arrestor | No area will be affected as load of Power Transformer T-1 will be shifted to Power Transformer T-2 through Bu Coipler.
1 | IESCO | IBD | NO.II | I-9 | I-8 | I-8/4 | 61121 | 21-04-2026 30-04-2026 04.05.2026 | 08:00 | 13:00 | HT Proposal for Bifurcation of I-8 Markaz Feeder Emanating from 132KV I-8 Grid Station Under DOP Head 2K25412DOPHT52 | I-8/4
2 | IESCO | IBD | NO.II | I-9 | I-8 | I-8 MKZ | 61129 |  |  |  |  | I-8 MKZ
3 | IESCO | City | S/Town | Gangal | I-8 | Fazaia | 61112 |  |  |  |  | Fazaia
4 | IESCO | IBD | NO.II | I-9 | I-8 | CCC-II | 61135 |  |  |  |  | CCC-II
5 | IESCO | IBD | NO.I | Tarlai | Tarmari | Tarmari | 105503 | 16-04-2026 22-04-2026 |  |  | Directorate Genral Inter-services Intelligence Jinnah/pothwar Complex for conversion into underground to overhead on 11 KV ISI feeder. | Tarmari
6 | IESCO | IBD | NO.I | Rawal | Tramri | Waheedabad | 105516 |  |  |  |  | Waheedabad
7 | IESCO | IBD | NO.I` | Tarlai | Tramri | Kund Rajgan | 105522 |  |  |  |  | Kund Rajgan
8 | IESCO | IBD | NO.I` | Tarlai | Tramri | King Hammad | 105526 |  |  |  |  | King Hammad
9 | IESCO | IBD | NO.I | Tarlai | Tarmari | Azad Shaheed | 105512 |  |  |  |  | Azad Shaheed
10 | IESCO | IBD | NO.I | Tarlai | Tarmari | Lehtrar Road | 105517 |  |  |  |  | Lehtrar Road
11 | IESCO | IBD | NO.I | Tarlai | Tarmari | Chatta Bakhtawar | 105507 |  |  |  |  | Chatta Bakhtawar
12 | IESCO | IBD | NO.I | Tarlai | Tarmari | Kuri Road | 105506 |  |  |  |  | Kuri Road
13 | IESCO | IBD | NO.I | Tarlai | Tarmari | Rehara | 105511 |  |  |  |  | Rehara
14 | IESCO | IBD | No.II | F-8 | G-9 | F-8/1 | 122317 | 21-04-2026 27.04.2026 30.04.2026 |  |  | Removal of HT Fault on 11 KV Centaurus Hotel Feeder | Sector F-8/1
15 | IESCO | IBD | No.II | F-8 | G-9 | F-8 Markaz | 122316 |  |  |  |  | Sector F-8
16 | IESCO | IBD | No.II | G-7 | G-9 | Meezan Bank | 122321 |  |  |  |  | Independent
17 | IESCO | IBD | No.II | F-8 | G-9 | HC3 Pims | 122324 |  |  |  |  | Independent
1 | IESCO | Attock | Taxila | Sang Jani | 220 KV Sang Jani | Shah Allah Ditta | 081011 | 18.04.2026 21.04.2026 23.04.2026 27.04.2026 29.04.2026 | 09:00 Hours | 11:00 Hours | AMI Project | GT Road,Zila Tax,Madrassa Road
2 | IESCO | Attock | Taxila | Sang Jani | 132 KV GSS B-17 | Saray Kharbooza | 121802 | 16.04.2026 20.04.2026 22.04.2026 25.04.2026 28.04.2026 30.04.2026 | 09:00 Hours | 11:00 Hours | AMI Project | Dhoke Abbasi,Johd,Sarai Kharbooza
1 | IESCO | IBD | XEN-I | Rawal | Zero Point | Zia Masjid | 22342 | 16-04-2026 21.04.2026 25.04.2026 27.04.2026 | 8:30 | 11:30 | Safety Hazard Works IRO Rawal Sub Division | Khanna Dak and Surrounding Areas
2 | IESCO | IBD | XEN-I | Khanna Dak | NPF | Lohi Bher | 90002 | 22.04.2026 30.04.2026 |  |  | Removel of Safety Hazard Shifiting of Dangerous HT Line at Pinwal Mehra Lohi Bher Nukhar Hussain Abadi ICT. | Khanna Dak and Surrounding Areas
1 | IESCO | City | Westridge | Seham | 132 KV I-16 | Lakhu Road | 104615 | 22.04.2026 | 10:00 Hrs | 13:00 Hrs | Installation of T/F New Westridge St. No. 01 near tower | Gulshan-e-Khudadad, Kohsar Colony, Razzaq Town, Rehmat Town, Aftab Town and surrounding area
1 | IESCO | City | Westridge | Kamalabad | 132 KV I-16 | Officer Colony | 104614 | 20.04.2026 | 10:00 Hrs | 13:00 Hrs | LV Work | Dk. Gujran, Officer Colony, Friends Colony, Hamza Colony and surrounding area
2 |  |  |  | Tarnol | 132 KV Tarnol | Bajnial-I | 104910 | 18.04.2026 22.04.2026 25.04.2026 |  |  |  | Bajnial and surrounding area
3 | [5 empty] | Bajnial-II | 104911 | 21.04.2026 |  |  |  | Bajnial and surrounding area
4 |  |  |  |  | 132 KV G-13 | Nust Road | 106708 | 23.04.2026 27.07.2026 |  |  |  | Nust Road and surrounding area
1 | IESCO | GSO CIRCLE IESCO ISD | SS&TL DIVISIONIESCO RAJJAR | A.E (T) Chakwal | 132KV Chakwal (CWL-7) - Bhagwal (NLA-1) - Talagang (TLG-1) |  |  | 16-04-2026 to 24-05-2026 (Contineous) | 16-04-2026 18:00 Hrs | 24-05-2026 18:00 Hrs | Remodeling/Stringing of Chakwal - Talagang circuit from Loc No. 01 to 33 | 132KV GSS Bhagwal will be affected from 09:00 Hrs to 15:00 Hrs. after that No area will be affected as 132KV Chakwal already feeding from 500KV Rawat, Bhagwal will be fed from Talagang side & Talagang will be fed from Tamman side. However, 35 to 40 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | City | Westridge | MES | Pirwadhai | COB Lane | 043329 | 18.04.2026 23.04.2026 26.04.2026 02.05.2026 05.05.2026 | 07:00 | 14:00 | for Stringing of 132KV newly erected Poles from Loc # 32 to 37 | Cob lane and surrounding areas
2 |  |  |  | Misrial |  | Askari-XI | 043325 |  |  |  |  | Askari-XI, Lane No. 01 to 07, St. No. 01 to 14 and surrounding areas
3 |  |  |  | Westridge | KTM | Cheering Cross | 008602 |  |  |  |  | Gulnar colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding areas
1 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | APF | 96808 | 18.04.2026 25.04.2026 | 09:00 | 12:00 | For Jumpering of HT Line IRO Qurtaba City Chakri Rawalpindi | APF & surrounding area
2 | [5 empty] | SPD | 96806 |  |  |  |  | SPD & surrounding area
3 | [5 empty] | Paryal | 96809 |  |  |  |  | Paryal & surrounding area
4 | [5 empty] | Chakri | 96801 |  |  |  |  | Chakri & surrounding area
5 | [5 empty] | HASCOL | 96812 |  |  |  |  | Hascol & surrounding area
6 |  |  |  | Adiala | 132KV Adiala | Kalyal | 109101 | 27.04.2026 | 07:00 | 10:00 | For completion of LV Work IRO Mehmoodabad Jarahi & Sanjoli State Lane NO.01 | Kalyal & Surrounding areas
1 | IESCO | Jhelum | Gujar Khan | Sohawa | Gujar Khan | kulia | 4909 | 18.04.2026 | 0930 Hrs | 1230 Hrs | for Completion of Deposit Work Metro City Gujar Khan | Bhai Khan, Missa
2 | IESCO | Jhelum | Gujar Khan | Guliana | Gujar Khan | Kountrilla | 4917 |  |  |  |  | Jero Ratial,Kharli Bangial,Mohri Rajgan,Dk Amb,
3 | IESCO | Jhelum | Gujar Khan | Sohawa | Gujar Khan | Bhai Khan | 4919 |  |  |  |  | Jand Mehloo, Laddr, Daryala Khaki, Jermote etc
1 | IESCO | Cantt | Cantt | Civil Line | 132KV Chaklala | Rawalpindi-III | 002510 | 23.04.2026 25.04.2026 28.04.2026 30.04.2026 | 9:00 | 12:00 | For Phulgran Safety Hazard Estimate for Removal of Safety Hazard Point at near 132 KV GSS Chaklala Rawalpindi & Estimate for removal of Safety Hazard Point at Opposite Ashfaq ENT Hospital Rashid Minhas Road Marrir Hassan Rawalpindi | IESCO Complex, District Courts, DCO Office & Surrounding areas
2 | [5 empty] | Jahangir Road | 002505 |  |  |  |  | Jahangir Road & Surrounding areas
3 |  |  |  | Jhanda | 132KV Cantt | Jhanda Chichi | 017921 |  |  |  |  | Jhanda Chichi & sorrounding area
4 |  |  | Mandra | Wadala | 132KV Rawat | New Kalyam | 017721 |  |  |  |  | Effected area Kalyam Village Jaliary mouzam Shah Khai awan & Surrounding area
5 | [5 empty] | Old Kalyam | 017710 |  |  |  |  | Effected Area Jhummat Manga Sain Singhori & Sarwar Shaheed & Surrounding
1 | IESCO | Chakwal | Chakwal | Chakwal City | Chakwal | LINE PARK | 2203 | 22.04.2026 | 9:00 | 12:00 | For Shifting of HT Pole and T/F From ABL Public Park to outside the ABL Public Park | Faisal Colony, Madina Town, General Bus Stand, ABL Park, Thanil Road, Ashraf Town, Pindi Bypass, Small Industries