## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | R.E New Wah | 132KV New Wah (WAH-5) to Loc No. 18 (open) along with related earth switch |  |  | 01-02-2026 | 09:00 Hrs | 12:00 Hrs | For safety purpose to mproivisw jumper for lod shifting of WAH-6 to WAH-5 for remodelling work of 132KV T/Line POF East, West and North. | 132KV POF East, West & North Grids (Consumer) will be affected.
2 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | R.E New Wah | 132KV New Wah (WAH-6) - POF East, North along with related earth switch |  |  | 01-02-2026 To 31-03-2026 (Contineous) | 01-02-2026 09:00 Hrs | 31-03-2026 16:00 Hrs | For saftety puprose for errection & stringing work between Loc No. 01 to 17 of WAH-6 portion for remodelling work of 132KV T/Line POF East, West & North. | No area will affected as POF East, West and North will mbe fed from 132KV GSS New Wah (WAH-5)
10 | IESCO | Attock | Attock | Attock City | 132 KV Attock | Fawara Chowk | 75103 | 11.02.2026 | 09:00 | 14:00 | Replacement of Old Wire & Pole Under Beautification of Attock | City area, Lorry area & surrounding area
11 | IESCO | Attock | Attock | Attock City | 132 KV Attock |  |  | 18.02.2026 25.02.2026 28.02.2026 | 07:00 | 12:00
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 15-02-2026 To 16-04-2026 (Contineous) |  | 15-02-2026 18:00 Hrs | 16-04-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 30 to 40 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO CIRCLE IESCO ISD | SS&TL DIVISIONIESCO RAJJAR | A.E (T) Chakwal | 132KV Chakwal (CWL-7) - Bhagwal (NLA-1) - Talagang (TLG-1) |  |  | 15-02-2026 to 16-04-2026 (Contineous) |  | 15-02-2026 18:00 Hrs | 16-04-2026 18:00 Hrs | Remodeling/Stringing of Chakwal - Talagang circuit from Loc No. 01 to 33 | 132KV GSS Bhagwal will be affected from 09:00 Hrs to 15:00 Hrs. after that No area will be affected as 132KV Chakwal already feeding from 500KV Rawat, Bhagwal will be fed from Talagang side & Talagang will be fed from Tamman side.
8 | IESCO | IBD | NO.II | F-8 | 132KV GSS G-9 | F-8/1 | 122317 | 02-03-2026 05-03-2026 09-03-2026 12-03-2026 14-03-2026 17-03-2026 | 07:00 | 12:00 |  | Sector F-8/1
9 | IESCO | IBD | NO.II | F-8 | 132KV GSS G-9 | F-8 Markaz | 122316 |  | 07:00 | 12:00 |  | Sector F-8
10 | IESCO | IBD | NO.I | G-7 | 132KV GSS G-9 | Meezan Bank | 122321 |  | 07:00 | 12:00 |  | Independent
11 | IESCO | IBD | No.II | F-8 | 132KV GSS G-9 | HC3 Pims | 122324 |  | 07:00 | 12:00 |  | Independent
12 | IESCO | IBD | B/Khu | Murree | 132KV Kuldana Murree | Kuldana | 13702 | 24-02-2026 03-03-2026 10-03-2026 17-03-2026 | 07:00 | 12:00 | Removal / Shifting of services remodling of Jhika Gali Chowk Tehsil & District Murree | Mall Road, Kashmir Point and Mashyari.
13 | IESCO | IBD | B/Khu | J/Gali | 132KV Kuldana Murree | GHARIAL | 13711 |  | 07:00 | 12:00 |  | J/gali Bazar Gjarial camp.Kashmiri Bazar,seher bagla Aliot
14 | IESCO | IBD | Div-I | Tarlai | 132 KV Tramri GS | Kund Rajgan | 105522 | 26-02-2026 05-03-2026 12-03-2026 | 07:00 | 12:00 | External Electrification work IRO IT Technology Park Chak Shahzad Islamabad | Chatta Bakhtawa and surrounding Area
15 | IESCO | IBD | Div-I | Tarlai | 132 KV Rawal | Scheme-II | 17430 |  | 07:00 | 12:00 |  | Scheme -I & Scheme - II
16 | Div-I | IBD | Div-I | Tarlai | Trammari | Comsats | 105508 |  | 07:00 | 12:00 |  | Comsats University
17 | IESCO | IBD | Div-I | Tarlai | 132 KV Tramri | Chata | 105507 |  | 07:00 | 12:00 |  | Chattah Bakhtawar and surrounding
18 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | Kurri | 105506 | 26-02-2025 30-03-2025 | 07:00 | 12:00 | Federal Urdu University at Kurri Road Zone-IV Near Bahria Enclave Islamabad | Kuri Sher.
19 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | Rehara | 105511 |  | 07:00 | 12:00 |  | Mohra Noor, Rehara
20 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | CM Pak Zong | 105509 |  | 07:00 | 12:00 |  | Office of CM PAK
21 | IESCO | IBD | B/Kahu | B/K (U) | University | N.I.H | 89210 | 23-02-2026 25-02-2026 02-03-2026 04-03-2026 09-03-2026 11-03-2026 16-03-2026 31-03-2026 | 07:00 | 12:00 | Stringing of HT line/ Installation of HT Structure 58' Beneath the existing HT lines in IRO Bifurcation of 11KV Shah Pur Feeder /Strinning of HT line in R/O External Electrification of Park View City Housing Society | Malpur, Lake view, Banigala, NIH, Dk. Jillani, LVL, Dk. Mohri.
22 | IESCO | IBD | B/Kahu | B/K (U) | University | T&T | 89204 |  | 07:00 | 12:00 |  | Mangoo Town, 17 Meel, Abdullah Town.
23 | IESCO | IBD | B/Khu | B/K (U) | 132/220 KV G/S B/Khu | B/ Khu-I | 89201 |  | 07:00 | 12:00 |  | Bhara Kahu Bazar, Sanjalian and Surrounding Area
24 | IESCO | IBD | B/Khu | B/K (U) | 132/220 KV G/S B/Khu | B/ Khu-II | 89219 |  | 07:00 | 12:00 |  | Madina Town, Nain Sukh,and Surrounding Area
25 | IESCO | IBD | B/Khu | B/Khu (R) | 132/220 KV G/S B/Khu | Tret | 89203 |  | 07:00 | 12:00 |  | Nai Abadi,Country Form
26 | IESCO | IBD | B/Khu | B/K (R) | 132/220 KV G/S B/Khu | Golf city | 89216 |  | 07:00 | 12:00 |  | Golf City
27 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Park View | 122511 |  | 07:00 | 12:00 |  | Park View city
28 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Athal | 89217 |  | 07:00 | 12:00 |  | Simly dam road , Athal Road, Tumair, Athal.
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132 KV Cantt | Khadim Hussain Road | 17906 | 22.02.2026 01.03.2026 | 7:00 | 10:00 | for GPO Chowk Under Pass Singnal free Mall Road Project (Part A) Rawalpindi | Khadim Hussain Road
2 | IESCO | Cantt | Tariqabad | Tariqabad | 132 KV Cantt | CMH Flats | 17936 |  | 7:00 | 10:00 |  | CMH Flats
3 | IESCO | Cantt | Cantt | Civil Line | 132 KV Cantt | Adam jee road | 17923 |  | 7:00 | 10:00 |  | Adam jee road
4 | IESCO | Cantt | Tariqabad | Tariqabad | 132 KV Cantt | Askari-7 | 17919 |  | 7:00 | 10:00 |  | Askari-7
5 | IESCO | Cantt | Cantt | Civil Line | 132 KV Cantt | Sir Syed road | 17913 |  | 7:00 | 10:00 |  | Sir Syed road
6 | IESCO | Cantt | Cantt | Saddar | 132 KV Cantt | FFC | 17927 |  | 7:00 | 10:00 |  | FFC
7 | IESCO | Cantt | Tariqabad | R.A Bazar | 132 KV Cantt | GHQ Express | 17924 |  | 7:00 | 10:00 |  | GHAQ Express
1 | IESCO | City | Westridge | Misrial | Pirwadhai | Askari-XI | 043325 | 23.02.2026 25.02.2026 02.03.2026 | 10:00 | 13:00 | D/W Army Grave Yard | Askari-XI, Lane No. 1 to 7 Street No 1 to 14 & surrounding area
2 | IESCO | City | Westridge | Westridge | KTM | NRC | 008622 |  | 10:00 | 13:00 | D/W Army Grave Yard | Westridge Bazar, Hjali Road, Iqbal Road, Churr Chowk, Race Course Ground & Surroundindg aea
1 | IESCO | City | Westridge | Kamalabad | Kamalabad | People Colony | 001022 | 24.02.2026 27.02.2026 03.03.2026 06.03.2026 | 8:00 | 11:00 | Safetey Hazard work Molvi Khursheed streeet | People Colony
2 | IESCO | City | Westridge | Kamalabad | Kamalabad | Radio Pak | 001006 |  | 8:00 | 11:00 |  | Radio Pak
3 | IESCO | City | Westridge | Kamalabad | Kamalabad | Kamalabad | 001025 |  | 8:00 | 11:00 |  | Kamalabad
4 | IESCO | City | Westridge | Tarnol | Tarnol | Bijnial-1 | 104910 | 23.02.2026 26.02.2026 02.03.2026 05.03.2026 | 8:00 | 11:00 | LV work village Katrian | Village Bijnial & Surrounding area
1 | IESCO | IBD | NO.II | G-9 | G-9 | G-9/1 | 122304 | 24-02-2026 27-02-2026 | 08:00 Am | 11:00 AM | Extension of Load and conversion of on Point Supply into HT individual Metering IRO Regional Tax Office at Plot No 21-B Muave Area Sector G-9/1 Islamabad | G-9/1
2 | IESCO | IBD | NO.II | G-9 | G-9 | G-9/2 | 122305 | 02-03-2026 05-03-2026 |  |  |  | G-9/2
1 | IESCO | IBD | XEN-I | G-6 | Zero Point | Aabpra | 22302 | 26.02.2026 02.03.2026 | 8:00 | 11:00 | 11KV VIP Feeder From U/G To O/H Zero Point Grid Station To Nacta Office G-7/1 Islamabad | Aabpra Market and G-6
1 | IESCO | IBD | NO.II | F-8 | F-11 | F-10 MKZ | 069208 | 25-02-2026 03-03-2026 | 08:00 Am | 11:00 AM | Reconductoring of 11 KV F-10 Feeder From ACSR Rabbit to ACSR DOG From Street No.63 F-10/3 to Gull Plaza F-10 Markaz Islamabad 2k25412DOPHT03 | F-10 MKZ
2 | IESCO | IBD | NO.II | F-8 | F-11 | F-10 | 069203 |  |  |  |  | F-10
3 | IESCO | IBD | NO.II | F-8 | F-11 | F-10/3 | 069212 |  |  |  |  | F-10/3
1 | IESCO | Attock | Taxila | Hassan Abdal | 132 KV GSS New Wah | Burhan | 014601 | 24.02.2026 27.02.2026 | 11:00 Hours | 13:00 Hours | installation of 100 KVA Transformer at Village Jallo | Nikko Bafad,Kolia,Bai,Jallo,Tass and Surrounding.
1 | IESCO | Cantt | Cantt | Civil Line | Cantt | Dk.Farman Ali | 17922 | 25-02-2026 28-02-2026 | 06:00 | 11:00 | for HT Work of Tipu Road Feeder | Dhoke Farman Ali, Dk, Khabba, -T&T Exchange.
2 | IESCO | Cantt | Cantt | Civil Line | Cantt | Tipu road | 17916 |  | 06:00 | 11:00 |  | Tipu Road, Fauji Tower, Rwp Medical College
1 | IESCO | City | Westridge | Seham | 132 KV I-16 | Pind Hoon | 104612 | 24.02.2026 26.02.2026 | 07:00 Hrs | 10:00 Hrs | For Stringing of HT Conductor IRO Taj Recidencia | Pind Hoon and Surrounding areas
2 | [5 empty] | I-14/2 | No load |  |  |  |  | Sector I-14 and Surrounding areas
3 | [5 empty] | I-14/3 | 104602 |  |  |  |  | Sector I-14/3 and Surrounding areas
4 | [5 empty] | Noon | 104603 |  |  |  |  | Noon and Surrounding areas
5 | [5 empty] | I-16/1 | 104604 |  |  |  |  | I-16 and Surrounding areas
6 | [5 empty] | HPT (Radio Pak) | 104613 |  |  |  |  | HPT
7 | [5 empty] | Lakhoo Road | 104615 |  |  |  |  | Lakhoo road and Surrounding areas
8 |  |  |  | Kamalabad |  | Ameer Hamza | 104616 |  |  |  |  | Ameer Hamza Colony and Surrounding areas
9 | [5 empty] | Officer Colony | 104614 |  |  |  |  | Officer Colony and surrounding areas
1 | IESCO | Attock | Taxila | Wah Cantt | 132KV New Wah Grid | Khan Abad | 14619 | 25.02.2026 28.02.2026 03.03.2026 07.03.2026 | 06:00 | 14:00 | for safety purpose during erection and stringing of conductor from location No. 02 to 13 for remodeling of 132kv T/Line POF East, West & North | Asifabad, Green Town, Basti Chokw
2 | IESCO | Attock | Taxila |  |  | Small Industrial Estate | 14625 |  |  |  |  | Basti, Minar Road
3 | IESCO | Attock | Taxila | Mora Chowk |  | Pour Miana | 14608 |  |  |  |  | Pour Miana
4 | IESCO | Attock | Taxila |  |  | Lala Rukh | 14622 |  |  |  |  | Lala Rukh, Basti, Uppal Chokw
5 | IESCO | Attock | Taxila | Wah Cantt |  | Gudwal-I | 14615 |  |  |  |  | Gudwal-I
6 | IESCO | Attock | Taxila |  |  | Gudwal-II | 14616 |  |  |  |  | Gudwal-II
7 | IESCO | Attock | Taxila | Mora Chowk |  | Garhi Afghan | 14626 |  |  |  |  | Bhdu ,Garhi Afghan, Mal pur
| IESCO | Attock | Taxila |  |  | Shahia | 14629 | 10.03.2026 |  |  |  | Village Shahiya Pind Mehri ,Jhari Kas
8 | IESCO | Attock | Taxila |  |  | Munir Abad | 14628 | 25.02.2026 28.02.2026 03.03.2026 10.03.2026 |  |  |  | Munirabad, GT Road
2 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Margalla | 132 KV T/L New Wah (WAH-15) - Bahter More (BMW-2) Along with related earth switches. |  |  | 25-02-2026 To 25-03-2026 (Contineous) | 25-02-2026 09:00 h | 25-03-2026 14:00 h | During this period, the portion of line will be isolated/ de-energized as working portion for erection & stringing from 132 KV GSS Bahter More to 132 KV GSS New Wah. | No area will be affected, however132 KV GSS Fauji Cement Plant (Consumer Grid) will be fed from 132 KV GSS Fateh Jang and 132 KV GSS Bahtarmore will be fed from 132 KV GSS Fateh Jang side & 132 KV GSS New Wah will be fed from 220 KV GSS Burhan side.
2 | IESCO | Chakwal | Chakwal | Main Bazar | Chakwal | MAIN BAZAR | 2214 | 26.02.2026 02.03.2026 05.03.2026 12.03.2026 14.03.2026 | 8:00 | 11:00 | Dismantling of Feeder Work | Main Bazar, Chappar Bazar Talagang Road, Jhelum Road, Ali Masjid, Moh: Ghosia, Moh: Farooqi, Hospital Road, Old Sabzi Mandi, Moh: Hajveri, Tatral Hotel, Dhok Hayat, Sabzi Mandi, Moh: Grid Station etc
3 | IESCO | Chakwal | Chakwal | Main Bazar | Chakwal | ISLAMIA CHOWK | 2223 | 28.02.2026 03.03.2026 10.03.2026 | 8:00 | 11:00 | Completion of Shifting of Poles for Road Widening Project | Moti Bazar, Islamia Chowk to Bhoun Chowk, Nia Mohallah, Khumeni Chowk, Moh: Gharbi, Moh: Khawajgan, Sarpak, Kot Ganish Eid Gah,
4 | IESCO | Chakwal | Dhudial | Tariq Shaheed | Dhudial | PINWAL | 2224 | 25.02.2026 03.03.2026 09.03.2026 | 8:00 | 11:00 | Completion of Safety Hazard Works | Village Pinwal, Har Char Dhab, Mian Mair, Chak Norang, Chak Umra, Behkri, Pinwal, Chak Malook, Noorwal, Dhoke Bair, Chak Bazeed , Ameenabad etc.
5 | IESCO | Chakwal | Dhudial | Tariq Shaheed | Dhudial | BEHKRI | 2204 | 04.03.2026 | 8:00 | 11:00 | Completion of Work under SDG Works | Faisal Colony, Bahadar Abad, Sub-Jail, Village Thanil Fatohi, Har Char Dhab, Mian Mair, Chak Norang, Chak Umra, Behkri,
1 | IESCO | City | Satellite Town | Gulzar-e-Quaid | 132 KV Chaklala | Sector-IV | 2536 | 25.02.2026 02.03.2026 05.03.2026 09.03.2026 12.03.2026 16.03.2026 | 7:00 | 10:00 | For Shifting of 2 x Feeder of Chaklala Sub Division & Gulzar-e-Quaid Sub Division on 58' Structures | Gracy Line
2 | [5 empty] | Aiport Society | 2501 |  |  |  |  | Airport Society
1 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Chaklala | 2503 |  |  |  |  | Chaklala & Surrounding
2 | [5 empty] | Rehmatabad-I | 2541 |  |  |  |  | Rehmatabad & Surrounding
1 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Chahan | 96802 | 25.02.2026 02.03.2026 05.03.2026 | 7:00 | 10:00 | For D/W Sky 47 Capital Smart City | Chan, Rajar, Kinger, Mera Kalwan, Mara Khurrd.
2 |  |  |  | Adyala |  | Chauntra | 96804 |  |  |  |  | Chountra, Pind Maloo, Adawal, Chokar, Dhalla, Kasala Kurd.
3 |  |  |  | Chakri |  | Rajjar | 96803 |  |  |  |  | Mujahid, Sihal, Pelo thallian, Kollian, Ghreeba moorat etc.
4 | [5 empty] | SPF | 96807 |  |  |  |  | Sadiq Poultry Form
5 | [5 empty] | Chakri | 96801 |  |  |  |  | Moorat & Surrounding areas
1 | IESCO | Attock | Pindi Gheb | Fateh Jang Rural | 132 KV Fateh Jnag | Gul Muhammad | 27213 | 02-03-2026 03-03-2026 04-03-2026 05-03-2026 | 11:00am | 02:00pm | Defence Project Horizon Tech Service (Pvt) Ltd | Atomic Energy, Fateh Jang Hastal, Tajabara, kot Fateh Khan, Fateh Jang City & Surrounding Area
2 |  |  |  | Fateh Jang Rural |  | Gagan | 27217
3 | [5 empty] | Laniwala | 27210
4 |  |  |  | Fateh Jang Urban |  | Sajjad Shaheed | 27211
5 | [5 empty] | City-2 | 27216
1 | IESCO | Attock | Pindi Gheb | Fateh Jang R | 132KV Fateh Jang | Tanaza Dam | 27215 | 28.02.2026 01.03.2026 | 07:00 | 12:00 | Defence Project Horizon Tech Service (Pvt) Ltd | Atomic Energy, Fateh Jang, Hastal, Taja Bara, Kot Fateh Khan, & Surrounding Area
2 | [5 empty] | Gul Muhammad | 27213
3 | [5 empty] | Gagan | 27217
4 | [5 empty] | Laniwala | 27210
5 |  |  |  | Fateh Jang U |  | City-II | 27216
6 | [5 empty] | Sajjad Shaheed | 27211
7 | [5 empty] | Nescom | 27218
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | R.E New Wah | 132KV New Wah (WAH-5) to POF North to POF West &132KV New Wah (WAH-6) to POF East along with related earth switch |  |  | 01-03-2026 | 07:00 Hrs | 13:00 Hrs | For safety purpose for providing of droppers/jumpers from Loc No. 18 to POF East and energization of 132KV Bus Bar at New Wah Grid Station POF South. | No area will be affected. However, 132KV POF Grid (Consumer) will be fed through 11KV Generation POF Power House.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rajjar | A.E (T) Jhelum | 31.5/40MVA Power Transformer T-2 At 132KV GSS Dina |  |  | 03-03-2026 | 07:00 Hrs | 11:00 Hrs | For replacement of Winding Temprature Gauge | No area will be affected as load of Power Transformer T-2 will be shifted to T-1 through Bus Coupler.
1 | IESCO | Attock | Taxila | Sang Jani | 132 KV GSS B-17 Sang Jani | Sarai Kharbooza | 121802 | 02.03.2026 03.03.2026 05.03.2026 | 09:00 Hours | 11:00 Hours | For errection of poles and installation of Transformer | Sarai Kharbooza,Dhoke Mehrban
2 | [5 empty] | Shah Allah Ditta | 081011 |  |  |  |  | Shah Allah Ditta
1 | IESCO | Cantt | Tariqabad | Chakri | 132 KV Chakri | Paryal | 96809 | 25.02.2026 02.03.2026 | 10:00 | 13:00 | for couplling & energization of New 11KJV Qurtaba City Paryal | Paryal,Chak Denal,Dhari Mohra ,Mial,Kurar, Krahi,ect
2 | IESCO | Cantt | Tariqabad | Chakri | 132 KV Chakri | Hascool | 096812 |  | 10:00 | 13:00 |  | Hascool & Surrounding area
3 | IESCO | Cantt | MANDRA | C/B KHAN | CHAKRI | MAHOOTA | 96810 |  | 10:00 | 13:00 |  | MAHOOTA MOHRA, CB KHAN, JARAY, RUPPAR KALAN, MEHMOODA ETC
4 | IESCO | Cantt | Tariqabad | Tariqabad | 132 KV K/Abad | Dheri Hassan abad | 1027 | 26.02.2026 28.02.2026 | 9:00 | 12:00 | for errection of poles IRO Florencw Marque Khawaja Corporation Chowk. | Dheri Hassan Abad, Tahli Mohri Chowk
5 | IESCO | Cantt | Tariqabad | Tariqabad | 132 kv Adyala | Lalkurti | 1004 |  | 9:00 | 12:00 |  | Dheri Hassan Abad, Sabzazar , Qazi Road, Harly Street ect/
6 | IESCO | Cantt | Tariqabad | Tariqabad | 132 KV Chaklala | Maj/ Riaz | 1017 |  | 9:00 | 12:00 |  | Tulsa Rd, Tehli Mohri, Dheeri Hassan Abad