## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) Margalla | 132KV New Wah - (WAH-15) - Bahtermore (BMW-2) along with related earth switch |  |  | 30-06-2026 To 31-07-2026 (Contineous) | 30-06-2026 14:00 Hrs | 31-07-2026 14:00 Hrs | For erection & Stringing activities. (during this period, the portion of line New Wah - Bahternmore will be Isolated/ De-Energized as workingportion) | No area will be affected as 132KV GSS Bahtermore will be fed from 132KV GSS Fateh Jang side & 132KV GSS New Wah will be fed from 220KV GSS Burhan side.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) Margalla | 132KV New Wah - (WAH-15) - Bahtermore (BMW-2) along with related earth switch |  |  | 31-07-2026 To 31-08-2026 (Contineous) | 31-07-2026 14:00 Hrs | 31-08-2026 14:00 Hrs | For erection & Stringing activities. (during this period, the portion of line New Wah - Bahternmore will be Isolated/ De-Energized as workingportion) | No area will be affected as 132KV GSS Bahtermore will be fed from 132KV GSS Fateh Jang side & 132KV GSS New Wah will be fed from 220KV GSS Burhan side.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 30-06-2026 To 31-07-2026 (Contineous) | 30-06-2026 18:00 Hrs | 31-07-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 60 to 70 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 31-07-2026 To 31-08-2026 (Contineous) | 31-07-2026 18:00 Hrs | 31-08-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 60 to 70 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132KV AWC (AWC-1) - HMC Taxila (TXL-4) & 132KV Sangjani (E8Q1) - Burhan (Disconnected) |  |  | 01-07-2026 To 31-7-2026 Contineous | 01-07-2026 09:00 Hrs | 31-07-2026 16:00 Hrs | For Safety Purpose during erection of tower for remodeling work of 132KV T/Line AWC to HMC Taxila | No area will be affected as 132KV GSS AWC will be fed from Burhan side & 132KV GSS Taxila will be fed from 220KV Sangjani side & 132KV GSS New Wah side. Moreover, CDA Pumping is currently feeding from Sangjani (E9Q1) - Taxila (TXL-3) ckt T-off.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132KV AWC (AWC-1) - HMC Taxila (TXL-4) & 132KV Sangjani (E8Q1) - Burhan (Disconnected) |  |  | 31-07-2026 To 31-08-2026 Contineous | 31-07-2026 09:00 Hrs | 31-08-2026 16:00 Hrs | For Safety Purpose during erection of tower for remodeling work of 132KV T/Line AWC to HMC Taxila | No area will be affected as 132KV GSS AWC will be fed from Burhan side & 132KV GSS Taxila will be fed from 220KV Sangjani side & 132KV GSS New Wah side. Moreover, CDA Pumping is currently feeding from Sangjani (E9Q1) - Taxila (TXL-3) ckt T-off.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) No.I, Isd | 31.5/40MVA Power Transformer T-1 at 132KV GSS Rawat-II |  |  | 27-7-2026 To 02-8-2026 (Contineous) | 27-7-2026 08:00 Hrs | 02-8-2026 17:00 Hrs | For replacement of Drain Valve for Diverter Switch & Bottom Sampling Valve DN-25 by the Elswedy Team & De-Hydration of Transformer Oil by T&I Team | No area will be affected as load of Power Transformer T-1 will be shifted to Power Transformer T-2 through Bus Coupler.
2 |  |  |  |  | 31.5/40MVA Power Transformer T-2 at 132KV GSS Rawat-II |  |  | 03-8-2026 To 09-8-2026 (Contineous) | 03-8-2026 08:00 Hrs | 09-8-2026 17:00 Hrs | For replacement of Bottom Sampling Valve DN-25, Top Filtering Valve DN-40, Bottom Filtering Valve DN-40 & Drain Valve for Diverter Switch by the Elswedy Team & De-Hydration of Transformer Oil by T&I Team | No area will be affected as load of Power Transformer T-2 will be shifted to Power Transformer T-1 through Bus Coupler.
8 | IESCO | City | Westridge | Tarnol | 132 KV KTM | EME Complex | 008615 | 07.07.2026 22.07.2026 29.07.2026 01.08.2026 | 06:00 | 10:00 | Shifting of HT/LT Line Haji Camp road widening | EME Complex
9 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Jhangi | 008608 |  |  |  |  | Shaheenabad, Faisal Colony, Jhangi Syedan, Tarnol and surrounding area
10 | IESCO | City | Westridge | Tarnol | 132 KV KTM | P&T Wani | 008610 |  |  |  |  | Jhangi Syedan, Haideri Chowk and surrounding area
11 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Azharabad | 008620 |  |  |  |  | Peshawer Road, Pind Paracha and surrounding area
12 | IESCO | City | Westridge | Tarnol | 132 KV KTM | CWO | 008601 |  |  |  |  | CWO
1 | IESCO | Attock | Taxila | Sang Jani | 132 KV Cabinet Division | Millat Colaony | 136602 | 15.07.2026 17.O7.2026 20.07.2026 22.07.2026 24.07.2026 27.07.2026 29.07.2026 31.07.2026 | 07:00 Hours | 09:00 Hours | AMI Project | Tarnol,Millat Colony,Gulshan Colony,Ittifaq Colony
1 | IESCO | Attock | Taxila | Taxila | 132 KV Taxila Grid | Ghouri | 021219 | 24.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | LV Works | Usman Khattar,Godho
2 | [5 empty] | Harro | 021216 |  |  |  |  | Kamra,Ihatta,Farooqia
10 | IESCO | Islamabad | Islamabad-I | Tarlai | 132kV GSS Tramari | Azad Shaheed | 105512 | 01-08-2026 | 05:00 | 11:00 | For safety purpose during stringing of conductor between location No.29-30, 7,8, 23-29 & 8-11 to 7 to 7 for new 132kV T/Line Feed For Shakrial. | Azad Shaheed
1 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New | 30.07.2026 03.08.2026 06.08.2026 10.08.2026 | 7:00: AM | 10:00: AM | Extension of Load CM Pak Complex Kurri Road Islamabad. | Independent
2 | IESCO | IBD | XEN-I | Tarlai | Rawal | Scheme-II | 17430 |  |  |  |  | Scheme-I & Scheme-II
3 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Kund Rajgan | 105522 |  |  |  |  | Kund Rajgan
4 | IESCO | IBD | XEN-I | Tarlai | Tramri | King Hammad | 105526 |  |  |  |  | King Hammad
5 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Chatta Bakhtwar | 105507 |  |  |  |  | Chatta Bakhtwar
1 | IESCO | City | Satellite Town | Chandni Chowk | 132 KV Satellite Town | Faizabad | 095813 | 28.07.2026 03.08.2026 | 06:00 Hrs | 09:00 Hrs | Erection of poles & stringing work IRO Dual Source of Urology Hospital | Shamsabad, Gulshan Dadan, Murree Road, Faizabad and surrounding area
2 |  |  |  | F-Block |  | Haidri Chowk | 095830 |  |  |  |  | E-Block, Saidpur Road, D-Block and surrounding area
1 | IESCO | Chakwal | Dhudial | Dhudial | Padshahan | DHUDIAL RURAL | 79102 | 23.07.2026 30.07.2026 01.08.2026 .03.08.2026 06.08.2026 | 07:00 AM | 10:00 PM | For Completion of HV work Area Planning of Dhudial Rural | Dk.Akbar, Dandi, Dk.Kamal, Mona, Dk.Wadhan, Fareed Kasar, Dk.Hajian, Nadral, Damal, Hadala
1 | IESCO | Attock | Taxila | Margalla | 132 KV Bahtar | Dharik | 112006 | 29.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | Safety Hazards Pind Buhadar Khan HT line Crossing over the houses | Pind Buhadar Khan,Bahtar,Dharik,Bahlol and sorroundings.
1 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Kot Jabbi | 2539 | 04.08.2026 06.08.2026 | 07:00 Hours | 10:00 Hours | for Removal of Safety Hazards at street No 07, 08 & 09 Gulbarg Colony Chaklala | Kot Jabbi
2 | IESCO | Cantt | Rawat | Kahuta | 132KV Kahuta | Kahuta City | 9001 | 24.07.2026 25.07.2026 28.07.2026 30.07.2026 01.08.2026 |  |  | fro bifurcation & rehabilitation of libraray Road Kahutain the name of District officer (I& S) District Councel Rawalpindi. | Kahuta City
3 | IESCO | Cantt | Rawat | Kahuta | 132KV Kahuta | Hanif Shaheed | 9007 |  |  |  |  | Hanif Shaheed
1 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | Kuri Road | 105506 | 27.07.2026 30.07.2026 03.08.2026 06.08.2026 | 7:00: AM | 10:00: AM | External Electrification Work IRO IT Technology Park Chak Shahzad Islamabad. | Kuri Sher.
2 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | Rehara | 105511 |  |  |  |  | Mohra Noor, Rehara
3 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | CM Pak Zong | 105509 |  |  |  |  | Independent
4 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New |  |  |  |  | Independent
1 | IESCO | Attock | Taxila | Hassan Abdal | 132 KV New Wah | Hussain Abad | 014627 | 29.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | Installation of Transformer at Shadman Town. | Shadman Town,Pind Kamala Banian.
1 | IESCO | Attock | Taxila | Taxila | 132 KV Taxila | HMC Road | 21227 | 29.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | Shifting of HT line at Model Town | Model Town HMC Road.
2 |  |  |  |  | 132 KV Margalla | Mushtaq Hussain | 83308 |  |  |  | Shifting of HT Line at Saleem Nagar | Nawab Abad,Saleem Nagar.
1 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Rehmatabad-I | 2519 | 29.07.2026 31.07.2026 04.08.2026 06.08.2026 | 7:00 | 10:00 | For Dismantling at Chungi No.III to Gulraiz Phase-III Chaklala Rwp Deposit Work | Rehmatabad & sorrounding area
2 | [5 empty] | Rehmatabad-II | 2530 |  |  |  |  | Rehmatabad & sorrounding area
3 | [5 empty] | Jail Park | 2516 |  |  |  |  | Jail Park & sorrounding area
4 | [5 empty] | Kot Jabbi | 2539 |  |  |  |  | Kot Jabbi & sorrounding area
5 | [5 empty] | Mecca Chowk | 2535 |  |  |  |  | Mecca Chowk & sorrounding area
6 | [5 empty] | Bostan Khan | 2538 |  |  |  |  | Bostan Road & sorrounding area
1 | IESCO | City | Westridge | Kamalabad | 132 KV I-16 | Ameer Hamza | 104616 | 29.07.2026 01.08.2026 05.08.2026 08.08.2026 | 07:00 Hrs | 10:00 Hrs | Bifurcation of 11KV Lakhu road feeder | Dk. Gujran, Ameer Hamza Colony, Chakra Road, Misrial Road and surrounding area
2 | [5 empty] | HPT | 104613 |  |  |  |  | Radio Pak, HPT
3 | [5 empty] | Officer Colony | 104614 |  |  |  |  | Officer Colony, Friends Colony, Ameer Hamza Colony and saurrounding area
4 |  |  |  | Seham |  | I-14/3 | 104602 |  |  |  |  | I-14/1, I-14/2, I-14/3, I-14/4
5 | [5 empty] | Lakhu Road | 104615 |  |  |  |  | Gulshan-e-Khudadad, Kohsar Colony, Razzaq Town, Rehmat Town, Aftab Town and surrounding area
6 |  |  |  |  | 132 KV KTM | Range Road | 008627 |  |  |  |  | Mukarram Town, Moh Rajputan Range Road and surrounding area
7 | [5 empty] | Seham | 008618 |  |  |  |  | Usmaina Colony, Qadria Colony, Farooqabad and surrounding area
8 | [5 empty] | Chakra | 008604 |  |  |  |  | Chistiabad, Muhammadi Colony, Dk. Sada and surrounding area
9 |  |  |  | Tarnol |  | Dk. Suleman | 008629 |  |  |  |  | KTM and surrounding area
1 | IESCO | Attock | Taxila | Hassan abdal | 220 KV Burhan Grid | Indistrial | 21101 | 30.07.2026 to 03.08.2026 (Daily basis) | 6:00 | 12:00 | for Stringing Activity between Section T. No. 109 to 112 | Village Bahtar, Dirik, Pind Buhadar Khan.
2 | IESCO | Attock | Taxila | Hassan abdal | 132 KV F/Abad Grid | Shafi Chohan | 12023 |  |  |  |  | Village Bahtar, Dirik, Pind Buhadar Khan.
1 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New Wah Grid | Hussain Abad | 14627 | 31.07.2026 03.08.2026 07.08.2026 12.08.2026 | 5:00 | 12:00 | for safety purpose during Strining of Conductorbetween location No15 to 18& 19 to 23 for remodeling Work of 132kv T/Line New Wah to Bather more to Fateh Jang | Hussain Abad
2 | [5 empty] | Lala Zar | 14607 |  |  |  |  | Lala Zar
3 | [5 empty] | Lala Zar | 14607 | 15.08.2026 18.08.2026 21.08.2026 |  |  | for safety purpose during Strining of Conductor between location No23 to 27 for remodeling Work of 132kv T/Line New Wah to Bather more to Fateh Jang | Lala Zar
1 | IESCO | Jhelum | Gujar Khan | Bhadana | Gujar Khan | Islampura | 4910 | 31.07.2026 | 8 | 10 | Shifting of HT/LT Line for 02 No. underpasses at GT Road Gulyana Morr and Technicla College Gujar Khan | Islampura, Jabbar etc.
1 | IESCO | IBD | XEN-II | I-9 | H-11 | Ufone | 72733 | 01-08-2026 08.08.2026 | 7:00: AM | 10:00: AM | Shifting of H/T Line Due to Rehabilitayion and widening of 7 UP chowk to NISCOM Hospital Islamabad. | Independent
2 | IESCO | IBD | XEN-II | I-9 | H-11 | SES | 72731 |  |  |  |  | Independent
3 | IESCO | IBD | XEN-II | I-9 | H-11 | Fazal Ghee | 72705 |  |  |  |  | Independent
4 | IESCO | IBD | XEN-II | I-9 | I-10 | Industrial-III | 6431 |  |  |  |  | Independent
5 | IESCO | IBD | XEN-II | I-9 | I-10 | Industrial-II | 6422 |  |  |  |  | Independent
6 | IESCO | IBD | XEN-II | I-9 | I-10 | Warid | 6439 |  |  |  |  | Independent
7 | IESCO | IBD | XEN-II | I-9 | I-10 | Old PTN | 6405 |  |  |  |  | Independent
8 | IESCO | IBD | XEN-II | I-9 | I-10 | Industrial-I | 6409 |  |  |  |  | Independent
9 | IESCO | IBD | XEN-II | I-9 | I-10 | EVC-II | 6441 |  |  |  |  | Independent
1 | IESCO | Chakwal | Chakwal | Chakwal City | Chakwal | LINE PARK | 2203 | 03.08.2026 | 7:00 | 10:00 | Installation of 100KVA T/F of NGSC App No. 14525-260615004 IRO Zeshan Abbas Dhudial Road Chakwal | Faisal Colony, Madina Town, General Bus Stand, ABL Park, Thanil Road, Ashraf Town, Pindi Bypass, Small Industries
2 |  |  |  | Main Bazar |  | KSM-I | 2205 |  |  |  |  | KSM-I, Permanent Disconnected Since Loge
1 | IESCO | GSO Circle IESCO ISD | SS&TL Division IESCO RAJJAR | A.E (T) Chakwal | 132KV Chakwal (CWL-7) - Talagang (TLG-1) - Bhagwal (NLA-1) T/Line | Following 11 KV O/G feeders will be affected. |  | 02-8-2026 | 06:30 Hrs | 10:30 Hrs. | For De-Jumpering at Loc No. 36 & 66 to isolate the section from Loc No. 36 to 66 at Talagang side for remodeling/ stringing & Erection. | 132KV GSS Neela (Bhagwal) will be affected. | After this Shut Down Neela Bhagwal will be fed from Chakwal side. Talagang GSS will be fed from Tamman side.
[6 empty] | NEELA | 64301 |  |  |  |  | NEELA
[6 empty] | HASSAL | 64302 |  |  |  |  | HASSAL
[6 empty] | BALKASSAR | 64303 |  |  |  |  | BALKASSAR
[6 empty] | Kot Chaudhrian | 64304 |  |  |  |  | KOT CHAUDHRIAN
[6 empty] | PIPLI | 64305 |  |  |  |  | PIPLI
[6 empty] | DULLAHA | 64306 |  |  |  |  | DULLAHA
[6 empty] | KARSAL | 64307 |  |  |  |  | KARSAL
2 |  |  |  |  | 132KV C.B Talagang (TLG-1) |  |  | 10-8-2026 | 06:30 Hrs | 10:30 Hrs. | For Re-Jumpering at Loc No. 36 & 66 at Talagang side | No area will be affected
3 |  |  |  |  | 132KV C.B Talagang (TLG-1) |  |  | 17-8-2026 | 06:30 Hrs | 10:30 Hrs. | For De-Jumpering at Loc No. 66 | No area will be affected
4 |  |  |  |  | 132KV C.B Talagang (TLG-1) |  |  | 23-8-2026 | 06:30 Hrs | 10:30 Hrs. |  | No area will be affected
1 | IESCO | Attock | Taxila | Margalla | 132KV Margalla | Bahlot | 83303 | 04.08.2026 06.08.2026 | 06:00 | 10:00 | for safety Hazards Dhoke Poono shifting of composit LT Line. | Bahlot, Thatha, Bahtor.
1 | IESCO | City | Westridge | Westrudge | 132 KV KTM | Cheering Cross | 008602 | 06.08.2026 10.08.2026 22.08.2026 31.08.2026 | 06:00 | 10:00 | Deposit Work of Dr. A.Q Khan Research Laboratory | Gulnar Cly, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding area
2 |  |  |  | Tarnol |  | Golra | 018906 |  |  |  |  | Naseerabad, Awan Colony and surrounding area
3 | [5 empty] | Azharabad | 008620 |  |  |  |  | Peshawer Road, Pind Paracha and surrounding area
4 | [5 empty] | Zarkoon Heights | 008628 |  |  |  |  | Zarkoon Heights
5 | [5 empty] | Dk. Sulaiman | New |  |  |  |  | Dk. Sulaiman
6 | [5 empty] | Shammas Colony | 008626 |  |  |  |  | H-13 and surrounding area
7 | [5 empty] | Quaid-e-Azam Hospital | 008624 |  |  |  |  | Quaid-e-Azam International Hospital
8 | [5 empty] | Jhangi | 008608 |  |  |  |  | Shaheenabad, Faisal Colony, Jhangi Syedan, Tarnol and surrounding area
9 | [5 empty] | CWO | 008601 |  |  |  |  | CWO
1 | IESCO | Chakwal | Chakwal | Ghaziabad | 132KV Chakwal | Mureed | 002201 | 02.08.2026 05.08.2026 16.08.2026 20.08.2026 23.08.2026 30.08.2026 | 06:00 | 12:00 | for Stringing at location No # 08 to 11 & location No. 46 to 66 of 132KV T/Line Chakwal - Talagang. | Mureed & Surrounding area
2 | [5 empty] | Jamal Wal | 002219 | 04.08.2026 07.08.2026 10.08.2026 13.08.2026 16.08.2026 30.08.2026 |  |  |  | Jamal Wal & Surrounding area
3 | [5 empty] | Mengan | 002211 |  |  |  |  | Mengan & Surrounding area
1 | IESCO | Chakwal | Chakwal | Azhar Shaheed | 132KV Chakwal | Karyala | 002216 | 04.08.2026 07.08.2026 10.08.2026 | 06:00 | 12:00 | for Errection of location No # 03 at 132KV T/Line Chakwal - Talagang. | Karyala & Surrounding area
2 | [5 empty] | K.S.M Unit-3 | 002212 |  |  |  |  | K.S.M Mills & Surrounding area
1 | IESCO | City | S.Town | F-Block | 132 KV GSS S/Town | T&T | 095810 | 01.08.2026 | 0800 to 1000 |  | For energization of NGSC against App:No.14312260506004 dt. 06.05.2026 | 7th Road,Saidpur Road, B-Block etc
2 | IESCO | City | S.Town |  |  | PTCL | 095823 |  |  |  | Safety Purpose | PTCL Complex
3 | IESCO | City | S.Town |  |  | 6th Road | 095827 |  |  |  | Safety Purpose | 7th Road,Saidpur Road, B-Block etc
1 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Chahan | 96802 | 31.07.2026 | 7:00 | 10:00 | For Stringing of HT Conductor at 132 KV GSS Chakri Rawalpindi | Chan, Rajar, Kinger, Mera Kalwan, Mara Khurrd.
2 |  |  |  | Adyala |  | Chauntra | 96804 |  |  |  |  | Chountra, Pind Maloo, Adawal, Chokar, Dhalla, Kasala Kurd.
3 |  |  |  | Chakri |  | Rajjar | 96803 |  |  |  |  | Mujahid, Sihal, Pelo thallian, Kollian, Ghreeba moorat etc.
4 | [5 empty] | SPF | 96807 |  |  |  |  | Sadiq Poultry Form
5 | [5 empty] | Chakri | 96801 |  |  |  |  | Moorat & Surrounding areas
1 |  |  |  | Chakri |  | APF | 96808 |  |  |  |  | APF & surrounding area
2 | [5 empty] | SPD | 96806 |  |  |  |  | SPD & surrounding area
[6 empty] | Sky-47 | 096813 |  |  |  |  | SPD & surrounding area
3 | [5 empty] | Paryal | 96809 |  |  |  |  | Paryal & surrounding area
5 | [5 empty] | HASCOL | 96812 |  |  |  |  | Hascol & surrounding area
7 | [5 empty] | Rangers | 96811 |  |  |  |  | Rangers & surrounding area
8 |  |  |  | CB Khan |  | Gaggan | 096805 |  |  |  |  | Gaggan & sorrounding area
7 | [5 empty] | Mahoota | 096810 |  |  |  |  | Mahoota & sorrounding area
1 | IESCO | Cantt | Tariqabad | Adyala | 132 KV Adyala | Kalyal | 109101 | 03.08.2026 06.08.2026 10.08.2026 13.08.2026 17.08.2026 22.08.2026 28.08.2026 | 7:00 | 10:00 | For installation of Poles IRO Khawaja Corporation Chowk to Gorakh Pur Adyala Road Rawalpindi for road widening | Dk. Parian, Adyala Jail, Shahpur, Gorakhpur, Sammar Zar Cly, Shah pur Syedan.
2 | [5 empty] | Shahpur | 109103 |  |  |  |  | Kalyal Adyala Road, Khaja Corportion, Jarahi, Janjua Town, Natinal Housing Society
3 | [5 empty] | Adyala | 109106 |  |  |  |  | Adyala Road Khawaja Corporation, Mubarak Lane, Ali Town, Chungi No.20, Dhoke Noor etc.
4 | [5 empty] | Khasala | 109108 |  |  |  |  | Khasala village
5 |  |  |  | Tariq Abad |  | Humayun-1 | 109111 |  |  |  |  | Askari-14 & Surrounding areas.
6 |  |  |  | Adyala |  | Dhok Noor | 109104 |  |  |  |  | Dhoke Mehra, Dhoke Haji Imam Din, Dhoke noor, Tarbela Colony
7 | [5 empty] | Gulshanabad | 109102 |  |  |  |  | Gulshanabad
8 | [5 empty] | Rose Lane | 109105 |  |  |  |  | New Lalazar, 502 Workshop
9 | [5 empty] | Adyala Jail | 109107 |  |  |  |  | Adyala Jail
10 | [5 empty] | Shaigan | 109110 |  |  |  |  | Shaigan
11 | [5 empty] | Defence Road | 109113 |  |  |  |  | Defence Road.
12 | [5 empty] | Samar zar | 109114 |  |  |  |  | Samarzar Housing Society.
13 |  |  |  | Tariq Abad |  | Askari-14 | 109112 |  |  |  |  | Askari-14
14 |  |  |  | Adiala |  | PGHS | 109109 |  |  |  |  | Punjab Government Housing Scheme & sorrounding area
1 |  |  |  | Dhamial | 132 KV Ranyal | Hayal | 120404 | 04.08.2026 |  |  | For removing of Safety Hazard Moh Ahl e Mohallah Gulistan e Fatima | Hayal & sorrounding area
2 | [5 empty] | Gulistan e Fatima | 120406 |  |  |  |  | Gulistan-e-Fatima & sorrounding area
1 |  |  |  | Adyala | 132KV Adyala | Dk Noor | 109104 | 12.08.2026 |  |  | For Bilal Colony Dk Noor | Dk Noor & sorrounding area
8 | [5 empty] | Rose Lane | 109105 | 20.08.2026 |  |  | For Caltex Road Iqbal Street | New Lalazar, 502 Workshop
5 |  |  |  | Chakri | 132 KV Chakri | Chakri | 96801 | 24.08.2026 |  |  | For Jumpering of HT Line IRO Qurtaba City Chakri | Moorat & Surrounding areas
6 |  |  |  | Dhamial | 132KV Ranyal | Moorat | 120405 | 05.08.2026 08.08.2026 11.08.2026 15.08.2026 18.08.2026 27.08.2026 |  |  | For stringing of HT Conductor IRO Capital Smart City | Moorat & Surrounding areas
7 | [5 empty] | Kohala | 120404 |  |  |  |  | Khasala & Surrounding areas
8 | [5 empty] | Fatima Jinnah | 120408 |  |  |  |  | Jarrar Camp
1 | IESCO | City | Westridge | Tarnol | 132 kV Tarnol | Top City | 104905 | 06.08.2026 31.08.2026 | 07:00 Hrs | 10:00 Hrs | Reconducting of HT line of Top City Feeder | Top City
2 | [5 empty] | Nogazi | 104901 |  |  |  |  | Nogazi, Dk. Miskeen, Main Fateh Jang road and surrounding area
3 | [5 empty] | Top City | 104905 | 20.08.2026 29.08.2026 |  |  |  | Top City
4 | [5 empty] | Bajniyal-I | 104910 |  |  |  |  | Bajniyall Village and surrounding area
1 | IESCO | Cantt | Cantt | Chaklala | 132 KV Chaklala | Takbeer-I | 2543 | 30.07.2026 04.08.2026 05.08.2026 06.08.2026 08.08.2026 | 7:00 | 10:00 | For Stringing work IRO Bifrucation of 11 KV Dk Gangal Feeder emanating from 132 KV Chaklala Grid Station under ELR Head (2K26-431-ELR-HT-01) | Takbeer Project & sorrounding area
1 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Chahan | 96802 | 04.08.2026 08.08.2026 | 7:00 | 10:00 | For Stringing of HT Conductor at 132 KV GSS Chakri Rawalpindi | Chan, Rajar, Kinger, Mera Kalwan, Mara Khurrd.
2 |  |  |  | Adyala |  | Chauntra | 96804 |  |  |  |  | Chountra, Pind Maloo, Adawal, Chokar, Dhalla, Kasala Kurd.
3 |  |  |  | Chakri |  | Rajjar | 96803 |  |  |  |  | Mujahid, Sihal, Pelo thallian, Kollian, Ghreeba moorat etc.
4 | [5 empty] | SPF | 96807 |  |  |  |  | Sadiq Poultry Form
5 | [5 empty] | Chakri | 96801 |  |  |  |  | Moorat & Surrounding areas
6 |  |  |  | Chakri |  | APF | 96808 |  |  |  |  | APF & surrounding area
7 | [5 empty] | SPD | 96806 |  |  |  |  | SPD & surrounding area
8 | [5 empty] | Sky-47 | 096813 |  |  |  |  | SPD & surrounding area
9 | [5 empty] | Paryal | 96809 |  |  |  |  | Paryal & surrounding area
10 | [5 empty] | HASCOL | 96812 |  |  |  |  | Hascol & surrounding area
11 | [5 empty] | Rangers | 96811 |  |  |  |  | Rangers & surrounding area
12 |  |  |  | CB Khan |  | Gaggan | 096805 |  |  |  |  | Gaggan & sorrounding area
13 | [5 empty] | Mahoota | 096810 |  |  |  |  | Mahoota & sorrounding area