## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) Margalla | 132KV New Wah - (WAH-15) - Bahtermore (BMW-2) along with related earth switch |  |  | 30-06-2026 To 31-07-2026 (Contineous) | 30-06-2026 14:00 Hrs | 31-07-2026 14:00 Hrs | For erection & Stringing activities. (during this period, the portion of line New Wah - Bahternmore will be Isolated/ De-Energized as workingportion) | No area will be affected as 132KV GSS Bahtermore will be fed from 132KV GSS Fateh Jang side & 132KV GSS New Wah will be fed from 220KV GSS Burhan side.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 30-06-2026 To 31-07-2026 (Contineous) | 30-06-2026 18:00 Hrs | 31-07-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 60 to 70 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132KV AWC (AWC-1) - HMC Taxila (TXL-4) & 132KV Sangjani (E8Q1) - Burhan (Disconnected) |  |  | 01-07-2026 To 31-7-2026 Contineous | 01-07-2026 09:00 Hrs | 31-07-2026 16:00 Hrs | For Safety Purpose during erection of tower for remodeling work of 132KV T/Line AWC to HMC Taxila | No area will be affected as 132KV GSS AWC will be fed from Burhan side & 132KV GSS Taxila will be fed from 220KV Sangjani side & 132KV GSS New Wah side. Moreover, CDA Pumping is currently feeding from Sangjani (E9Q1) - Taxila (TXL-3) ckt T-off.
8 | IESCO | Jhelum | Gujar Khan | City GK | Gujar khan | Hayat Sir Road | 4908 | 23.07.26 30.07.26 | 06:00 | 10:00 | Completion of Deposit work iro Tariq sharif Smart city | W/No.19 Hayat Sir Road W/No.11 & Surrounding Area.
18 | IESCO | Cantt: | Mandra | Mandra | Gujar khan | LTC | 4914 | 23.07.26 30.07.26 | 06:00 | 10:00 | Completion of Deposit work iro Tariq sharif Smart city | LTC
19 | IESCO | Cantt | Mandra | Mandra | Gujar Khan | New Mandra | 004918 |  |  |  |  | DK. Farman Ali, Karyala, Dk. Habib, Thandi Sarak, Mohra Gattian, Jorian , etc
20 | IESCO | Cantt: | Mandra | Mandra | Gujar khan | Old Mandra | 4904 |  |  |  |  | Mandra. Chihari , Bochial , & Surrounding Area.
21 | IESCO | Cantt: | Mandra | Mandra | Gujar khan | Hamid Jhangi | 4915 |  |  |  |  | Hamid Jhangi & Surrounding Area.
22 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Karyala | 047008 | 01.07.26 06.07.26 09.07.26 13.07.26 16.07.26 20.07.26 23.07.26 27.07.26 30.07.26 | 06:00 | 10:00 | Errection of poles and stringing of Karyala Feeder | Karyala
23 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Metro City | 047012 |  |  |  |  | Metro City
24 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Grand City | 047008 |  |  |  |  | Grand City
25 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Bolani | 047006 |  |  |  |  | Bolani
1 | IESCO | Attock | Attock | Attock City | 132KV Attock | Attock Rural | 75101 | 01-07-2026 04-07-2026 09-07-2026 13-07-2026 16-07-2026 20-07-2026 30-07-2026 | 06:00 | 10:00 | reconducting of Bagh Nelab Feeder | Attock Cantt & Surrounding Area
2 | [5 empty] | Teen Mela | 75113 |  |  |  |  | Teen Mela & Surrounding Area
3 | [5 empty] | Bagh Nelab | 75114 |  |  |  |  | Bagh Nelab & Surrounding Area
5 | [5 empty] | Fawara Chowk | 75103 | 02-07-2026 07-07-2026 11-07-2026 14-07-2026 18-07-2026 21-07-2026 25-07-2026 30-07-2026 |  |  | replacement of Old Wire & pole under Beautification of Attock | A.B.C.R Block, City area, Lorry area & surrounding area
2 | IESCO | Chakwal | Chakwal | Ghaziabad | 132KV Chakwal | Jamal Wal | 002219 | 02.07.2026 06.07.2026 13.07.2026 20.07.2026 27.07.2026 30.07.2026 | 06:00 | 15:00 | for Stringing at location No # 11 to 18 & location No. 46 to 66 of 132KV T/Line Chakwal - Talagang. | Jamal Wal & Surrounding area
3 | [5 empty] | Mengan | 002211 |  |  |  |  | Mengan & Surrounding area
1 | IESCO | Attock | Taxila | Sangjani | 132KV B17 | CABINAT | 121813 | 06-07-2026 07-07-2026 14-07-2026 30-07-2026 | 06:00am | 09:00am | Shifting of HT Line crossing over the Margalla Avenue | Cabinat
2 |  |  |  |  | 132KV B17 | Block-A | 121803 |  |  |  |  | B-17
3 |  |  |  |  | 132KV B17 | Gulshan e Sehat | 121806 |  |  |  |  | Gulshan e Sehat
4 |  |  |  |  | 220KV Sangjani | Vally | 81001 |  |  |  |  | Sangjani GT Road
5 |  |  |  |  | 220KV Sangjani | Sangjani | 81003 |  |  |  |  | Shah Allah Ditta Dk Abbasi
6 |  |  |  |  | 132KV B17 | Pind Parian | 121801 |  |  |  |  | Sangjani GT Road
7 |  |  |  |  | 132KV B17 | Saray Kharboza | 121802 |  |  |  |  | Saray Kharboza
8 |  |  |  |  | 220KV Sangjani | Shah Allah Ditta | 81011 |  |  |  |  | Shah Allah Ditta Dk Abbasi
2 | IESCO | IBD | Div-I | Tarlai | 132 KV Rawal | Scheme-II | 17430 | 14-07-2026 20-07-2026 27-07-2026 30-07-2026 | 6:00 | 10:00 | Shifting of HT/LT line IRO Margallah Avenue link road Near NIH Allergy center Park road Islamabad | Scheme - I & Scheme - II
3 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | Rehara | 105511 |  |  |  |  | Mohra Noor, Rehara
4 | IESCO | IBD | B/Kahu | B/K (U) | 132 kv G/S B/Khu | Mohra Noor | 122504 |  |  |  |  | Mal Pur,lake view, Bani Gala,Dk.Jellani
5 | IESCO | IBD | Div-I | G-6 | Rawal | Shehzad Town | 17424 |  |  |  |  | Rawal Town, Schme-4, Sohan Vil, CDA Tubewells (Ameen Faheem)
6 | IESCO | IBD | Div-I | G-6 | Rawal | Islamabad Club-I | 17417 |  |  |  |  | Banigala, orchard scheme, club road.
8 | IESCO | City | Westridge | Tarnol | 132 KV KTM | EME Complex | 008615 | 07.07.2026 22.07.2026 29.07.2026 01.08.2026 | 06:00 | 10:00 | Shifting of HT/LT Line Haji Camp road widening | EME Complex
9 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Jhangi | 008608 |  |  |  |  | Shaheenabad, Faisal Colony, Jhangi Syedan, Tarnol and surrounding area
10 | IESCO | City | Westridge | Tarnol | 132 KV KTM | P&T Wani | 008610 |  |  |  |  | Jhangi Syedan, Haideri Chowk and surrounding area
11 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Azharabad | 008620 |  |  |  |  | Peshawer Road, Pind Paracha and surrounding area
12 | IESCO | City | Westridge | Tarnol | 132 KV KTM | CWO | 008601 |  |  |  |  | CWO
1 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | Faisal Masjid | 22310 | 08-07-2026 11-07-2026 16-07-2026 21-07-2026 25-07-2026 30-07-2026 | 06:00 | 10:00 | For Replacement of Old Deteoriorated Cables of 11 kV HC-I & HC-II Feeder of PIMS Hospital. | F-8/4 & Surrounding
2 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | Ayub Market | 22318 |  |  |  |  | F-8/4 & Surrounding
3 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | HC-I | 22322 |  |  |  |  | PIMS Hospital G-8/3
4 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | HC-II | 22309 |  |  |  |  | PIMS Hospital G-8/3
5 | IESCO | Islamabad | Division No.II | G-9 | Zero Point | G-9/4 | 22340 |  |  |  |  | G-9/4 & Surrounding
6 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | Suparco | 22324 |  |  |  |  | Suparco Chowk & Surrounding Area
7 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | T&T | 22319 |  |  |  |  | G-8/1,G-8/4 & Surrounding
8 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | PTCL | 22331 |  |  |  |  | PTCL Headqurter
9 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | G-8/1 | 22330 |  |  |  |  | G-8/1 & Surrounding
10 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | G-8 | 22326 |  |  |  |  | G-8 & Surrounding
11 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | G-8 Markaz | 22338 |  |  |  |  | G-8 Markaz & Surrounding
12 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | Marvi | 22317 |  |  |  |  | G-7/2
1 | IESCO | City | Westridge | Westridge | 132 KV KTM | Dk. Chaudrian | 008621 | 11.07.2026 14.07.2026 21.07.2026 28.07.2026 30.07.2026 | 07:00 Hrs | 10:00 Hrs | Emergency work Peshawar road underpass project | Lane No. 04, 05 Range road and surrounding areas
2 | [5 empty] | Peshawar Road | 008612 |  |  |  |  | Peshawar Road Lane No. 04 to 07, Mehboob Lane, Fazeelabad and surrounding areas
3 | [5 empty] | Millatabad | 008616 |  |  |  |  | Misrial Road, Ilyas Colony, Lane 1,2,3 and surrounding areas
4 | [5 empty] | Cheering Cross | 008602 |  |  |  |  | Gulnar colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding areas
5 | [5 empty] | NRC | 008622 |  |  |  |  | Westridge bazar, Hali Road, Iqbal Road, Churr Chowk Race Course ground and surrounding areas
7 |  |  |  | Misrial | 132 KV Pirwadhai | Askari-XI | 043325 |  |  |  |  | Askari-XI, Lane No. 01 to 07, St. No. 01 to 14 and surrounding areas
1 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New Wah | Hassan Abdal | 14617 | 14-07-2026 16-07-2026 21-07-2026 23.07.2026 28.07.2026 30.07.2026 | 03:00pm | 06:00am | shifting of HT/LT Line Hassan Abdal City under bifurcation and Public Safety initiative | Hassan Abdal | 11KV Hassan Abdal feeder is feeding to court complex worthy C.E (O&M) vide Letter No. 140-48 dated 08-01-2026 has stopped all shut down during court working hours (08:00am to 03:00pm) so this office process shut down after working hours of court.
1 | IESCO | Chakwal | Dhudial | Khanpur | Padshahan | KHANPUR | 79107 | 13.07.2026 16.07.2026 23.07.2026 27.07.2026 30.07.2026 | 7:00 | 10:00 | For Completion of HV Work of Area Planning of 11KV Dhudial Rural & Saigalabad and Khanpur Feeders, emanating from 13KV Grid Station Padshahan | Hardu Saba, Amir Pur Mangan, Bheen, Khanpur, Chak Baqar Shah, Punjain, Lalyandi, Duman, Arrar Mughlan, Takia Shah Murad, Jandial Faiz Ullah, Chabbar.
1 | IESCO | Attock | Taxila | Sang Jani | 132 KV Cabinet Division | Millat Colaony | 136602 | 15.07.2026 17.O7.2026 20.07.2026 22.07.2026 24.07.2026 27.07.2026 29.07.2026 31.07.2026 | 07:00 Hours | 09:00 Hours | AMI Project | Tarnol,Millat Colony,Gulshan Colony,Ittifaq Colony
2 | IESCO | Attock | Taxila |  | 132 KV Cabinet Division | Saifia Town | 136601 | 16.07.2026 18.07.2026 21.07.2026 23.07.2026 25.07.2026 28.07.2026 30.07.2026 | 07:00 Hours | 09:00 Hours |  | Pind Parrian,Dorray,Roshan Pakistan,Cabinet Division and Saifia Town.
1 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | Old Rawat | 17716 | 16.07.2026 20.07.2026 23.07.2026 27.07.2026 30.07.2026 | 06:00 | 10:00 | For shifting of HT line from T-Chowk to HASCOL Pump T-Chowk Flyover | Rawat & sorrounding area
2 | IESCO | Cantt | Rawat | Rawat |  | New Rawat | 17701 |  |  |  |  | Rawat & sorrounding area
3 | IESCO | Cantt | Rawat | Rawat | 500KV New Rawat | AOWHS | 64506 |  |  |  |  | Emaar & sorrounding area
4 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | Suparco | 17717 |  |  |  |  | Suparco & sorrounding area
5 | IESCO | Cantt | Rawat | Rawat |  | CWO | 17722 |  |  |  |  | CWO & surrounding area
1 | IESCO | Attock | Taxila | Taxila | 132 KV Taxila Grid | Ghouri | 021219 | 24.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | LV Works | Usman Khattar,Godho
2 | [5 empty] | Harro | 021216 |  |  |  |  | Kamra,Ihatta,Farooqia
1 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Abdullah Pur | 058206 | 20.07.2026 23.07.2026 25.07.2026 30.07.2026 | 06:00 | 11:00 | Errection/Shifting of poles at site of Lillah Widening project. | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
2 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Jalal Pur | 058203 |  |  |  |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
3 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Sagharpur | 058202 |  |  |  |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
4 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | C.W.O. | 058204 |  |  |  |  | Army Area - Civil Work Organization.
10 | IESCO | Islamabad | Islamabad-I | Tarlai | 132kV GSS Tramari | Azad Shaheed | 105512 | 01-08-2026 | 05:00 | 11:00 | For safety purpose during stringing of conductor between location No.29-30, 7,8, 23-29 & 8-11 to 7 to 7 for new 132kV T/Line Feed For Shakrial. | Azad Shaheed
2 | IESCO | Chakwal | Chakwal | Ghaziabad | 132KV Chakwal | Jamal Wal | 002219 | 20.07.2026 27.07.2026 30.07.2026 | 6:00 | 15:00 | for Stringing at location No # 11 to 18 & location No. 46 to 66 of 132KV T/Line Chakwal - Talagang. | Jamal Wal & Surrounding area
3 | [5 empty] | Mengan | 002211 |  |  |  |  | Mengan & Surrounding area
1 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New | 30.07.2026 03.08.2026 06.08.2026 10.08.2026 | 7:00: AM | 10:00: AM | Extension of Load CM Pak Complex Kurri Road Islamabad. | Independent
2 | IESCO | IBD | XEN-I | Tarlai | Rawal | Scheme-II | 17430 |  |  |  |  | Scheme-I & Scheme-II
3 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Kund Rajgan | 105522 |  |  |  |  | Kund Rajgan
4 | IESCO | IBD | XEN-I | Tarlai | Tramri | King Hammad | 105526 |  |  |  |  | King Hammad
5 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Chatta Bakhtwar | 105507 |  |  |  |  | Chatta Bakhtwar
1 | IESCO | City | Satellite Town | Chandni Chowk | 132 KV Satellite Town | Faizabad | 095813 | 28.07.2026 03.08.2026 | 06:00 Hrs | 09:00 Hrs | Erection of poles & stringing work IRO Dual Source of Urology Hospital | Shamsabad, Gulshan Dadan, Murree Road, Faizabad and surrounding area
2 |  |  |  | F-Block |  | Haidri Chowk | 095830 |  |  |  |  | E-Block, Saidpur Road, D-Block and surrounding area
1 | IESCO | Chakwal | Dhudial | Dhudial | Padshahan | DHUDIAL RURAL | 79102 | 23.07.2026 30.07.2026 01.08.2026 .03.08.2026 06.08.2026 | 07:00 AM | 10:00 PM | For Completion of HV work Area Planning of Dhudial Rural | Dk.Akbar, Dandi, Dk.Kamal, Mona, Dk.Wadhan, Fareed Kasar, Dk.Hajian, Nadral, Damal, Hadala
1 | IESCO | Cantt | Tariq Abad | Adyala | 132 KV Adyala | Kayal | 109101 | 22.07.2026 25.07.2026 30.07.2026 | 07:00 AM | 10:00 PM | For installation of poles by PPRO Khawaja Corporation Chowk to Gorakh Pur Adyala Road, Rawalpindi, for road widening. | Kayal
2 | [5 empty] | Shahpur | 109103 |  |  |  |  | Shahpur
3 | [5 empty] | Adyala | 109106 |  |  |  |  | Adyala
4 |  |  |  | Tariq Abad |  | Khassala | 109108 |  |  |  |  | Khassala
5 |  |  |  | Adyala |  | Humayun-1 | 109111 |  |  |  |  | Humayun-1
6 | [5 empty] | Dhok Noor | 109104 |  |  |  |  | Dhok Noor
7 | [5 empty] | Gushahnabad | 109102 |  |  |  |  | Gushahnabad
8 | [5 empty] | Rose Lane | 109105 |  |  |  |  | Rose Lane
9 | [5 empty] | Adyala Jail | 109107 |  |  |  |  | Adyala Jail
10 | [5 empty] | Shaghan | 109110 |  |  |  |  | Shaghan
11 | [5 empty] | Defence Road | 109113 |  |  |  |  | Defence Road
12 | [5 empty] | Samar Zar | 109114 |  |  |  |  | Samar Zar
13 |  |  |  | Tariq Abad |  | Askan-14 | 109112 |  |  |  |  | Askan-14
14 |  |  |  | Adyala |  | PGS | 109109 |  |  |  |  | PGS
1 | IESCO | Attock | Taxila | Margalla | 132 KV Bahtar | Dharik | 112006 | 29.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | Safety Hazards Pind Buhadar Khan HT line Crossing over the houses | Pind Buhadar Khan,Bahtar,Dharik,Bahlol and sorroundings.
1 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Kot Jabbi | 2539 | 04.08.2026 06.08.2026 | 07:00 Hours | 10:00 Hours | for Removal of Safety Hazards at street No 07, 08 & 09 Gulbarg Colony Chaklala | Kot Jabbi
2 | IESCO | Cantt | Rawat | Kahuta | 132KV Kahuta | Kahuta City | 9001 | 24.07.2026 25.07.2026 28.07.2026 30.07.2026 01.08.2026 |  |  | fro bifurcation & rehabilitation of libraray Road Kahutain the name of District officer (I& S) District Councel Rawalpindi. | Kahuta City
3 | IESCO | Cantt | Rawat | Kahuta | 132KV Kahuta | Hanif Shaheed | 9007 |  |  |  |  | Hanif Shaheed
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) No.I, Isd | 31.5/40MVA Power Transformer T-1 at 132KV GSS Rawat-II |  |  | 27-7-2026 To 02-8-2026 (Contineous) | 27-7-2026 08:00 Hrs | 02-8-2026 17:00 Hrs | For replacement of Drain Valve for Diverter Switch & Bottom Sampling Valve DN-25 by the Elswedy Team & De-Hydration of Transformer Oil by T&I Team | No area will be affected as load of Power Transformer T-1 will be shifted to Power Transformer T-2 through Bus Coupler.
2 |  |  |  |  | 31.5/40MVA Power Transformer T-2 at 132KV GSS Rawat-II |  |  | 03-8-2026 To 09-8-2026 (Contineous) | 03-8-2026 08:00 Hrs | 09-8-2026 17:00 Hrs | For replacement of Bottom Sampling Valve DN-25, Top Filtering Valve DN-40, Bottom Filtering Valve DN-40 & Drain Valve for Diverter Switch by the Elswedy Team & De-Hydration of Transformer Oil by T&I Team | No area will be affected as load of Power Transformer T-2 will be shifted to Power Transformer T-1 through Bus Coupler.
1 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | Kuri Road | 105506 | 27.07.2026 30.07.2026 03.08.2026 06.08.2026 | 7:00: AM | 10:00: AM | External Electrification Work IRO IT Technology Park Chak Shahzad Islamabad. | Kuri Sher.
2 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | Rehara | 105511 |  |  |  |  | Mohra Noor, Rehara
3 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | CM Pak Zong | 105509 |  |  |  |  | Independent
4 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New |  |  |  |  | Independent
1 | IESCO | IBD | XEN-B/Kahu | J/Gali | 132/220 KV Kuldana Murree | Gharial | 13711 | 28-07-2026 30-07-2026 | 08:00 AM | 11:00 AM | Removal/Shifiting of Services remoding of J/Gali Chowk Tehsil & District Murree. | J/Gali Bazar Gharial Camp,Kashmiri Bazar,Seher Bagla Aliot
1 | IESCO | Attock | Taxila | Hassan Abdal | 132 KV New Wah | Hussain Abad | 014627 | 29.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | Installation of Transformer at Shadman Town. | Shadman Town,Pind Kamala Banian.
1 | IESCO | Attock | Taxila | Taxila | 132 KV Taxila | HMC Road | 21227 | 29.07.2026 31.07.2026 | 08:00 Hours | 10:00 Hours | Shifting of HT line at Model Town | Model Town HMC Road.
2 |  |  |  |  | 132 KV Margalla | Mushtaq Hussain | 83308 |  |  |  | Shifting of HT Line at Saleem Nagar | Nawab Abad,Saleem Nagar.
1 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Rehmatabad-I | 2519 | 29.07.2026 31.07.2026 04.08.2026 06.08.2026 | 7:00 | 10:00 | For Dismantling at Chungi No.III to Gulraiz Phase-III Chaklala Rwp Deposit Work | Rehmatabad & sorrounding area
2 | [5 empty] | Rehmatabad-II | 2530 |  |  |  |  | Rehmatabad & sorrounding area
3 | [5 empty] | Jail Park | 2516 |  |  |  |  | Jail Park & sorrounding area
4 | [5 empty] | Kot Jabbi | 2539 |  |  |  |  | Kot Jabbi & sorrounding area
5 | [5 empty] | Mecca Chowk | 2535 |  |  |  |  | Mecca Chowk & sorrounding area
6 | [5 empty] | Bostan Khan | 2538 |  |  |  |  | Bostan Road & sorrounding area
1 | IESCO | City | Westridge | Tarnol | 132 Kv Tarnol | Top City | 104905 | 28.07.2026 30.07.2026 | 07:00 Hrs | 10:00 Hrs | Reconducting of HT line of Top City Feeder | Top City
3 | [5 empty] | Nogazi | 104901 |  |  |  |  | Nogazi, Dk. Miskeen, Main Fateh Jang Road and surrounding area
1 | IESCO | City | Westridge | Kamalabad | 132 KV I-16 | Ameer Hamza | 104616 | 29.07.2026 01.08.2026 05.08.2026 08.08.2026 | 07:00 Hrs | 10:00 Hrs | Bifurcation of 11KV Lakhu road feeder | Dk. Gujran, Ameer Hamza Colony, Chakra Road, Misrial Road and surrounding area
2 | [5 empty] | HPT | 104613 |  |  |  |  | Radio Pak, HPT
3 | [5 empty] | Officer Colony | 104614 |  |  |  |  | Officer Colony, Friends Colony, Ameer Hamza Colony and saurrounding area
4 |  |  |  | Seham |  | I-14/3 | 104602 |  |  |  |  | I-14/1, I-14/2, I-14/3, I-14/4
5 | [5 empty] | Lakhu Road | 104615 |  |  |  |  | Gulshan-e-Khudadad, Kohsar Colony, Razzaq Town, Rehmat Town, Aftab Town and surrounding area
6 |  |  |  |  | 132 KV KTM | Range Road | 008627 |  |  |  |  | Mukarram Town, Moh Rajputan Range Road and surrounding area
7 | [5 empty] | Seham | 008618 |  |  |  |  | Usmaina Colony, Qadria Colony, Farooqabad and surrounding area
8 | [5 empty] | Chakra | 008604 |  |  |  |  | Chistiabad, Muhammadi Colony, Dk. Sada and surrounding area
9 |  |  |  | Tarnol |  | Dk. Suleman | 008629 |  |  |  |  | KTM and surrounding area
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 31-07-2026 To 31-08-2026 (Contineous) | 31-07-2026 18:00 Hrs | 31-08-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 60 to 70 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | Attock | Taxila | Hassan abdal | 220 KV Burhan Grid | Indistrial | 21101 | 30.07.2026 to 03.08.2026 (Daily basis) | 6:00 | 12:00 | for Stringing Activity between Section T. No. 109 to 112 | Village Bahtar, Dirik, Pind Buhadar Khan.
2 | IESCO | Attock | Taxila | Hassan abdal | 132 KV F/Abad Grid | Shafi Chohan | 12023 |  |  |  |  | Village Bahtar, Dirik, Pind Buhadar Khan.
1 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New Wah Grid | Hussain Abad | 14627 | 31.07.2026 03.08.2026 07.08.2026 12.08.2026 | 5:00 | 12:00 | for safety purpose during Strining of Conductorbetween location No15 to 18& 19 to 23 for remodeling Work of 132kv T/Line New Wah to Bather more to Fateh Jang | Hussain Abad
2 | [5 empty] | Lala Zar | 14607 |  |  |  |  | Lala Zar
3 | [5 empty] | Lala Zar | 14607 | 15.08.2026 18.08.2026 21.08.2026 |  |  | for safety purpose during Strining of Conductor between location No23 to 27 for remodeling Work of 132kv T/Line New Wah to Bather more to Fateh Jang | Lala Zar
1 | IESCO | Jhelum | Gujar Khan | Bhadana | Gujar Khan | Islampura | 4910 | 31.07.2026 | 8 | 10 | Shifting of HT/LT Line for 02 No. underpasses at GT Road Gulyana Morr and Technicla College Gujar Khan | Islampura, Jabbar etc.
1 | IESCO | IBD | XEN-II | I-9 | H-11 | Ufone | 72733 | 01-08-2026 08.08.2026 | 7:00: AM | 10:00: AM | Shifting of H/T Line Due to Rehabilitayion and widening of 7 UP chowk to NISCOM Hospital Islamabad. | Independent
2 | IESCO | IBD | XEN-II | I-9 | H-11 | SES | 72731 |  |  |  |  | Independent
3 | IESCO | IBD | XEN-II | I-9 | H-11 | Fazal Ghee | 72705 |  |  |  |  | Independent
4 | IESCO | IBD | XEN-II | I-9 | I-10 | Industrial-III | 6431 |  |  |  |  | Independent
5 | IESCO | IBD | XEN-II | I-9 | I-10 | Industrial-II | 6422 |  |  |  |  | Independent
6 | IESCO | IBD | XEN-II | I-9 | I-10 | Warid | 6439 |  |  |  |  | Independent
7 | IESCO | IBD | XEN-II | I-9 | I-10 | Old PTN | 6405 |  |  |  |  | Independent
8 | IESCO | IBD | XEN-II | I-9 | I-10 | Industrial-I | 6409 |  |  |  |  | Independent
9 | IESCO | IBD | XEN-II | I-9 | I-10 | EVC-II | 6441 |  |  |  |  | Independent
1 | IESCO | Chakwal | Chakwal | Chakwal City | Chakwal | LINE PARK | 2203 | 03.08.2026 | 7:00 | 10:00 | Installation of 100KVA T/F of NGSC App No. 14525-260615004 IRO Zeshan Abbas Dhudial Road Chakwal | Faisal Colony, Madina Town, General Bus Stand, ABL Park, Thanil Road, Ashraf Town, Pindi Bypass, Small Industries
2 |  |  |  | Main Bazar |  | KSM-I | 2205 |  |  |  |  | KSM-I, Permanent Disconnected Since Loge