## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) Margalla | 132KV New Wah - (WAH-15) - Bahtermore (BMW-2) along with related earth switch |  |  | 31-05-2026 To 30-06-2026 (Contineous) | 31-05-2026 14:00 Hrs | 30-06-2026 14:00 Hrs | For erection & Stringing activities. (during this period, the portion of line New Wah - Bahternmore will be Isolated/ De-Energized as workingportion) | No area will be affected as 132KV GSS Bahtermore will be fed from 132KV GSS Fateh Jang side & 132KV GSS New Wah will be fed from 220KV GSS Burhan side.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 15-05-2026 To 30-06-2026 (Contineous) | 15-05-2026 18:00 Hrs | 30-06-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 60 to 70 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO CIRCLE IESCO ISD | SS&TL DIVISIONIESCO RAJJAR | A.E (T) Chakwal | 132KV Chakwal (CWL-7) - Bhagwal (NLA-1) - Talagang (TLG-1) |  |  | 15-06-2026 to 15-07-2026 (Contineous) | 15-06-2026 18:00 Hrs | 15-07-2026 18:00 Hrs | Remodeling/Stringing of Chakwal - Talagang circuit from Loc No. 01 to 33 | 132KV GSS Bhagwal will be affected from 09:00 Hrs to 15:00 Hrs. after that No area will be affected as 132KV Chakwal already feeding from 500KV Rawat, Bhagwal will be fed from Talagang side & Talagang will be fed from Tamman side. However, 35 to 40 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132KV New Wah (WAH-6) to POF (East, West & North)along with related earth switch |  |  | 24-05-2026 To 14-06-2026 Contineous | 24-05-2026 08:00 Hrs | 14-06-2026 16:00 Hrs | For safety purpose for erection of Loc No. 20 & stringing of conductor between Loc No. 16 to 17 for remodeling work of 132KV T/Line POF East, West & North | On 24-5-2026 from 08:00Hrs to 16:00Hrs, 132KV GSS South, East, West & North will be affected. After that No area will be effected as all POF Grids will be fed from WAH-5, which PTW will be cancelled on 24-05-2026 at 16:00 HRs.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132KV New Wah (WAH-6) to POF (East, West & North)along with related earth switch |  |  | 14-06-2026 To 28-06-2026 Contineous | 14-06-2026 08:00 Hrs | 28-06-2026 16:00 Hrs | For safety purpose for erection of Loc No. 20 & stringing of conductor between Loc No. 16 to 17 for remodeling work of 132KV T/Line POF East, West & North | On 14.06.2026 from 08:00Hrs to 16:00Hrs, 132KV GSS South, East, West & North will be affected. After that No area will be effected as all POF Grids will be fed from WAH-5, which PTW will be cancelled on 14.06.2026 at 16:00 HRs.
14 | IESCO | IBD | NO.I | Tarlai | Tramari | Shareefabad | 105502 | 16.06.2026 20.06.2026 | 07:00 | 11:00 | Area Planning of 11KV UC Road Feeder and 11KV Koral Feeder | Shareefabad & Surrounding area
15 | IESCO | IBD | NO.I | Tarlai | Tramari | Ghouri Garden | 105513 |  |  |  |  | Ghouri Garden & Surrounding area
1 | IESCO | Chakwal | Chakwal | Ghazi Abad | 132KV Grid Station Chakwal | JAMALWAL | 002219 | 09.06.2026 11.06.2026 15.06.2026 22.06.2026 | 0700 Hrs | 1200 Hrs | for Stringing of Location # 08 to 25 of 132KV T/Line Chakwal - Talagang | Jamalwala & Surrounding Area
2 | [5 empty] | MENGAN | 002211 |  |  |  |  | Mengan & Srounding area
4 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New | 09.06.2026 (Cancelled) (23.06.2026 25.06.2026 | 8:00: AM | 11:00: AM | External Elecfrification Work IRO IT Technology Park Chak Shahzad Islamabad | IT.Park
1 | IESCO | Cantt | Cantt | Civil Line | 132KV Chaklala | Rawalpindi-III | 002510 | (Cancelled 13.06.2026 20.06.2026) | 8:00 | 11:00 | For Removal of Safety Hazard at Ishfaq Hospital near Punjab House Safety Hazard & near Chaklala GSS & for completion of LV Proposal at Street No.02 Dk Khabba | IESCO Complex, District Courts, DCO Office & Surrounding areas
2 | [5 empty] | Jahangir Road | 002505 |  |  |  |  | Jahangir Road & Surrounding areas
3 |  |  |  | Jhanda | 132KV Cantt | Jhanda Chichi | 017921 |  |  |  |  | Jhanda Chichi & sorrounding area
4 |  |  |  | Civil Line | 132KV Cantt | Dk Farman Ali | 017922 |  |  |  |  | Dhoke Farman Ali, Dk Khabba & sorrounding area
5 |  |  |  | Chaklala | 132KV Chaklala | Kot Jabbi | 002539 |  |  |  | For Removal of Safety Hazard at Street No.07, 08 & 09 Gulbahar Colony Chaklala | Kot Jabbi & sorrounding area
1 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Jhangi | 008608 | 23.06.2026 29.06.2026 | 08:00 Hrs | 11:00 Hrs | Near Benazir Chowk Fateh Jang Road Rawalpindi | Shaheenabad, Faisal Colony, Jhangi Syedan, Tarnol and surrounding area
1 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | Sector-IV | 002536 | 08.06.2026 11.06.2026 15.06.2026 18.06.2026 22.06.2026 29.06.2026 | 07:00 | 11:00 | Stringing of Work IRO Bifurcation of 11KV Dk. Gangal feeder emanating from 132KV Chaklala GSS under ELR Head (2k26-431 ELT-HT-01) | Airport Housing Society, Sector-4 (I.G.H Block) & Surrounding area.
2 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | APHS | 002526 |  |  |  |  | Airport Society, Dk. Anwar & Surrounding area.
3 | IESCO | Cantt | Chaklala | Chaklala | 132KV Chaklala | Rehmatabad-1 | 002519 |  |  |  |  | Rehmatabad-1 & Surrounding area
4 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | PAF | 002509 |  |  |  |  | PAF & Surrounding area.
5 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Takbeer-I | 2543 |  |  |  |  | Takbeer Project & sorrounding area
6 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Chaklala | 2503 |  |  |  |  | Chaklala & Surrounding area.
7 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Kot Jabbi | 2539 |  |  |  |  | Kot Jabbi & Surrounding area.
9 | IESCO | City | Westridge | Tarnol | 132 KV Tarnol | Nogazi | 104901 | 10.06.2026 24.06.2026 | 07:00 | 11:00 | Reconductoring of HT Line of Top City feeder | Nogazi and surrounding area
10 | IESCO | City | Westridge | Tarnol | 132 KV Tarnol | Bajniyal-1 | 104910 |  |  |  |  | Bajniyal-1 and surrounding area
11 | IESCO | City | Westridge | Tarnol | 132 KV Tarnol | Top City | 104905 |  |  |  |  | Top City and surrounding area
12 | IESCO | Cantt | Cantt | Korang | 132KV NPF | FECHS | 90001 | 06.06.2026 09.06.2026 13.06.2026 20.06.2026 (Cancelled 16.06.2026 23.06.2026) | 07:00 | 11:00 | For erection of poles IRO 11 KV Independent Feeder IRO Fedeation Employees Housing Society Lohi Bher Islamabad | FECHS & Surrounding areas
13 | IESCO | Cantt | Cantt | Korang | 132KV NPF | NPF-I | 090003 |  |  |  |  | NPF & Surrounding areas
14 | IESCO | Cantt | Cantt | Korang | 132KV NPF | NPF-II | 090004 |  |  |  |  | NPF & Surrounding areas
15 | IESCO | Cantt | Cantt | Korang | 132KV NPF | Doctor Town | 090016 |  |  |  |  | Doctor Town
16 | IESCO | Cantt | Cantt | Korang | 132KV NPF | PWD-I | 090014 |  |  |  |  | PWD'& Surrounding areas
17 | IESCO | Cantt | Cantt | Korang | 132KV NPF | PWD-II | 090015 |  |  |  |  | PWD'& Surrounding areas
18 | IESCO | City | Taeiqabad | Adyala | 132KV Adyala | Adyala | 109106 | 10.06.2026 30.06.2026 | 07:00 | 11:00 | for Stringing of Work IRO Area Planning of 11KV Shahpur & Dk. Noor feeder | Adyala & Surrounding area.
19 | IESCO | City | Taeiqabad | Adyala | 132KV Adyala | Dk. Noor | 109104 |  |  |  |  | Dk. Noor & Surrounding area.
20 | IESCO | Cantt | Taeiqabad | Adyala | 132KV Adyala | Samarzar | New |  |  |  |  | Samarzar & Surrounding area.
1 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | Old Rawat | 17716 | 09.06.2026 13.06.2026 20.06.2026 (Cancelled 24.06.2026) | 7:00 | 11:00 | For shifting of HT line from T-Chowk to HASCOL Pump T-Chowk Flyover | Rawat & sorrounding area
2 | IESCO | Cantt | Rawat | Rawat |  | New Rawat | 17701 |  |  |  |  | Rawat & sorrounding area
3 | IESCO | Cantt | Rawat | Rawat | 500KV New Rawat | AOWHS | 64506 |  |  |  |  | Emaar & sorrounding area
4 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | Suparco | 17717 |  |  |  |  | Suparco & sorrounding area
5 | IESCO | Cantt | Rawat | Rawat |  | CWO | 17722 |  |  |  |  | CWO & surrounding area
6 | IESCO | Cantt | Rawat | Kallar | 132 KV Kallar Syedan | Doberan | 098106 | 12.06.2026 21.06.2026 |  |  | For Removal of Safety Hazard at Chak Mirza Sada Kamal | Doberan & surrounding area
1 | IESCO | Attock | Attock | Attock City | 132KV Attock | Attock Rural | 75101 | 06.06.2026 10.06.2026 13.06.2026 16.06.2026 20.06.2026 24.06.2026 29.06.2026 | 07:00 | 11:00 | Reconducting of 3-Meela Feeder | Attock, Takbeer Colony & surrounding area
2 | IESCO | Attock | Attock | Attock City | 132KV Attock | Teen Mela | 75113 |  |  |  |  | Teen Mela & Surrounding Area
3 | IESCO | Attock | Attock | Attock City | 132KV Attock | Bagh Nelab | 75114 |  |  |  |  | Bagh Nelab & Surrounding Area
6 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Katchery | 18902 | 11.06.2026 23.06.2026 30.06.2026 |  |  | shifting nof line from Exsiting line to new proposed HT Str,58 IRO 11KV independent Feeder MCH Attock | Katchery & Surrounding Area
7 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Dar ul Islam Colony | 18909 |  |  |  |  | Dar ul Islam Colony & Surrounding Area
8 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Attock Cantt | 18901 |  |  |  |  | Attock Cantt & Surrounding Area
|  |  | Rawat | RAWAT | 132KV Old Rawat | New Rawat | 017701 | 06.06.2026 13.06.2026 20.06.2026 | 8:00 | 11:00 | For shifting of HT/ LT Lines at Potohar Avenue | Rawat & sorrounding area
2 |  |  |  |  | 132KV Sowan | Zaraj-I | 87411 |  |  |  |  | Zaraj-I & Surrounding area
3 | [5 empty] | Zaraj-II | 87423 |  |  |  |  | Zaraj-II & Surrounding area
4 | [5 empty] | Zeta-I | 87424 |  |  |  |  | Zeta Mall & Surrounding area
5 | [5 empty] | IST | 87422 |  |  |  |  | IST Universty & Surrounding area
6 | [5 empty] | Dk Awan | 87417 |  |  |  |  | DK Awan & Surrounding area
7 |  |  | Cantt |  |  | Mora Nagial | 87421 |  |  |  |  | Mora Nagial & Surrounding area
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Cantt | Khadim Hussain Road | 17906 | 07.06.2026 21.06.2026 28.06.2026 (Cancelled 14.06.2026) | 8:00 | 11:00 | For Construction of GPO Underpass Signal Free Mall Road Project Part A Rawalpindi | Khadim Hussain Road
2 |  |  |  | Tariqabad |  | CMH Flats | 17936 |  |  |  |  | CMH Flats
3 |  |  | Cantt | Civil Line |  | Adam Jee Road | 17923 |  |  |  |  | Adam Jee Road
4 |  |  |  | Civil Line |  | Askari 7 | 17919 |  |  |  |  | Askari 7
5 |  |  |  | Civil Line |  | Sir Syed Road | 17913 |  |  |  |  | Sir Syed Road
6 |  |  |  | Saddar |  | FFC | 17927 |  |  |  |  | Fauji Fertilizer
7 |  |  | Tariqabad | R.A Bazar |  | GHQ Express | 017924 |  |  |  |  | GHQ & sorrounding area | Subject to provision of NOC from GHQ
8 |  |  |  | Tariqabad | 132KV Chaklala | State Bank | 2521 |  |  |  |  | State Bank
5 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Golra | 018906 | 09.06.2026 11.06.2026 23.06.2026 (Cancelled dated 30.06.2026) | 07:00 | 11:00 | A.Q Khan research Laboratory | Naseerabad, Awan Colony and surrounding area
6 | IESCO | City | Westridge |  |  | Azharabad | 008620 |  |  |  |  | Peshawer Road, Pind Paracha and surrounding areas
7 | IESCO | City | Westridge |  |  | Zarkoon Heights | 008628 |  |  |  |  | Zarkoon Heights
8 | IESCO | City | Westridge |  |  | New Azharabad
9 | IESCO | City | Westridge |  |  | Jhangi | 008608 |  |  |  |  | Shaheenabad, Faisal Colony, Jhangi Syedan, Tarnol and surrounding area
10 | IESCO | City | Westridge |  |  | Quaid-e-Azam Hospital | 008624 |  |  |  |  | Quaid-e-Azam Internation Hospital
11 | IESCO | City | Westridge |  |  | CWO | 008601 |  |  |  |  | CWO
12 | IESCO | City | Westridge |  |  | Shamas Colony | 008626 |  |  |  |  | H-13 and surrounding area
1 | IESCO | Chakwal | Chakwal | Ghazi Abad | 132KV GSS Chakwal | Mureed | 002201 | 13.06.2026 14.06.2026 20.06.2026 21.06.2026 | 0700 Hrs | 1300 Hrs | for installation of Neck Extension at Location # 07 to 08 of 132KV T/Line Chakwal - Talagang | Mureed
2 | [5 empty] | Al-Qaim Mills | 002206 |  |  |  |  | Al-Qaim Mills
3 | [5 empty] | JAMALWAL | 002219 |  |  |  |  | JAMALWAL
4 | [5 empty] | PAF | 002215 |  |  |  |  | PAF
5 | [5 empty] | MENGAN | 002211 |  |  |  |  | MENGAN
1 | IESCO | IBD | NO.II | G-9 | H-11 | CWO | 72708 | 23-06-2026 (Cancelled dated 16-06-2026) | 07:00 | 11:00 | for removal of HT fault on independent 11 KV EOBI Feeder Emanating from 132 KV H-11 Islamabad | Independent
2 | IESCO | IBD | NO.II | G-9 | H-11 | G-10 Markaz | 72720 |  |  |  |  | G-10 Markaz
3 | IESCO | IBD | NO.II | G-9 | H-11 | Category House | 72711 |  |  |  |  | Independent
4 | IESCO | IBD | NO.II | G-9 | H-11 | G-10 Muave Area | 72703 |  |  |  |  | G-10/2
8 | IESCO | IBD | No.II | I-9 | Zero Point | I-8/2 | 22336 | 22-06-2026 | 07:00 | 11:00 | Installation of LBS at 11KV H-8 Feeder from 132KV Zero Point Grid Station W/O 2k26412DOPHT31 | I-8/2 & sorroundings
9 | IESCO | IBD | No.II | I-9 | Zero Point | I-8/3 | 22337 |  |  |  |  | I-8/3
10 | IESCO | IBD | No.II | I-9 | Zero Point | H-8 | 22325 |  |  |  |  | H-8
11 | IESCO | IBD | No.II | I-9 | Zero Point | Shifa | 22341 |  |  |  |  | H-8
1 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New | 13.06.2026 18.06.2026 (IT.Park already Cancelled dated 16.06.2026, 23.06.2026 & 25.06..2026) | 8:00: AM | 11:00: AM | External Elecfrification Work IRO IT Technology Park Chak Shahzad Islamabad | IT.Park
2 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | Kuri Road | 105506 |  |  |  |  | Kuri Road
3 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | Rehara | 105511 |  |  |  |  | Rehara,Mohra Noor
4 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | CM Pak Zong | 105509 |  |  |  |  | CM Pak Office
1 | IESCO | IBD | XEN-I | Khanna Dak | NPF | Lohi Bher | 90002 | 13.06.2026 16.06.2026 20.06.2026 23.06.2026 | 8:00: AM | 11:00: AM | Erection of Poles/Stringing Work IRO 11KV Independent Feeder IRO Federatio Employees Housing Society Lohi Bher Islamabad | Lohi Bher,Koral Harn Mera Toot Stop
1 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | APF | 96808 | 13.06.2026 20.06.2026 | 8:00 | 11:00 | For Jumpering of HT Line IRO Qurtaba City Chakri | APF & surrounding area
2 | [5 empty] | SPD | 96806 |  |  |  |  | SPD & surrounding area
3 | [5 empty] | Paryal | 96809 |  |  |  |  | Paryal & surrounding area
4 | [5 empty] | Chakri | 96801 |  |  |  |  | Chakri & surrounding area
5 | [5 empty] | HASCOL | 96812 |  |  |  |  | Hascol & surrounding area
6 | IESCO | Chakwal | Chakwal | Kallar Kahar | Kallar Kahar Town Ship | KHAIRPUR | 130802 | 20.06.2026 | 7:00 | 10:00 | Completion of LV Work Vill Khandowa, Vill: Khokhar | Chak Khurshi, Khandowa, Khairpur, Khokarbala, Julabi Chowk etc.
7 | IESCO | Chakwal | Chakwal |  |  | SARDHI | 130803 | 22.06.2026 |  |  | Completion of LV Work at Village Ransial | Ransial, Buchal Khurd, Chak Misri, Sardhi, Dk Saidan etc.
8 | IESCO | Chakwal | Chakwal | Bhagwal | Bhagwal (Neela) | KARSAL | 64307 | 20.06.2026 |  |  | Completion of LV Work at Village Karsal Sani Chowk | Karsal, Dhok Walana, Dhok Mistrian, Sidher, Chawali, Dhok Sultan, Dhok Ratti Paddi
1 | IESCO | IBD | XEN-I | F-6 | B/Kahu | Punjab House | 122506 | 17.06.2026 20.06.2026 | 08:00 AM | 11:00 PM | Shifting of 05 No.11KV Feeder Overhead Line to Underground at sector F-5/2 Islamabad 2K25411DOP HT 40 | Punjab House
2 | IESCO | IBD | XEN-I | F-6 | G-5 | F-6/2 | 75005 |  |  |  |  | F-6
3 | IESCO | IBD | XEN-II | G-9 | G-9 | FBR | 122325 | 17-06-2026 19-06-2026 23-06-2026 | 07:00 AM | 10:00 PM | Conversion of U/G 11KV G-9/4 Feeder to O/H From 132 KV Grid Station G-9 Islamabad DOP Head. 2k26412DOPHT52 | Independent
4 | IESCO | IBD | XEN-II | G-9 | G-9 | G-9/2 | 122305 |  |  |  |  | G-9/2
1 | IESCO | Cantt: | Mandra | Mandra | Gujar khan | LTC | 4914 | 20.06.26 | 0600 | 1000 | Completion of Deposit work iro Tariq sharif Smart city | LTC
2 | IESCO | Cantt | Mandra | Mandra | Gujar Khan | New Mandra | 004918 |  |  |  |  | DK. Farman Ali, Karyala, Dk. Habib, Thandi Sarak, Mohra Gattian, Jorian , etc
3 | IESCO | Cantt: | Mandra | Mandra | Gujar khan | Old Mandra | 4904 |  |  |  |  | Mandra. Chihari , Bochial , etc
4 | IESCO | Cantt: | Mandra | Mandra | Gujar khan | Hamid Jhangi | 4915 |  |  |  |  | Hamid Jhangi ,etc
5 | IESCO | Jhelum | Gujar Khan | City Gujar khan | Gujar khan | Hayat Sir Road | 4908 |  |  |  |  | W/No.19 Hayat Sir Road W/No.11
7 | IESCO | Cantt | Mandra | Wadala | Rawat | Basali | 017728 | 24.06.26 |  |  | Erection of Poles /Fitting & Stringing of HT Conductor iro Deposit Feeder EXIMPO Cool Chains Pvt Ltd.Cold Storage at Haraka | BASALI, MOHRA KOTIAN, DK GURHA, DK JUMMA, CHANDNI CHOWK ETC
8 | IESCO | Cantt | Tariqabad | Adyala | 500 KV New Rawat | Jarar Camp | 064510 |  |  |  |  | JARAR CAMP & SURROUNDING AREA
9 | IESCO | Cantt | Mandra | Chak Beli Khan |  | Bhall | 064507 |  |  |  |  | BHALL & SURROUNDING AREA
10 | IESCO | Cantt | Mandra | Wadala |  | Jatha Hathial | 064503 |  |  |  |  | JHATHA HATHIAL, NAKRALI, CHAPPER, JABBAR MIANA, LARRI MALANA ETC
11 | IESCO | Jhelum | Jhelum-II | Sanghoi | Sanghoi | Khai Kulia | 126301 | 23.06.26 |  |  | Completion of Depsoit work Shifting of HT/LT Line Lillah to PD Khan Road | Khai Kula , Bin Shaheed, Daryala Etc
12 | IESCO | Cantt: | Rawat | Rawat | Gangal | Japan road | 110901 | 27.06.26 |  |  | Dismentling of PC Poles IRO Mobeen Abad Feeder Japan Road | Sihala . Jhandala . Gangal , Japan road , etc
13 | IESCO | Rawat | Rawat | Rawat | Gangal | Jhandala | 110910 |  |  |  |  | Jhandala , etc
14 | IESCO | Cantt | Mandra | Mandra | 500 KV New Rawat | Ghumti | 064512 | 22.06.26 |  |  | For Completion of Safety Hazard works | Mohra Mandoo, Kuri Dolal, Ghumti, Noor Dolal, Karyali, etc
15 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Karyala | 047008 | 20.06.26 24.06.26 |  |  | Erection of Poles Karyala Feeder | Karyala
16 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Metro City | 047012 |  |  |  |  | Metro City
17 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Grand City | 047008 |  |  |  |  | Grand City
18 | IESCO | Jhelum | Jhelum-1 | Rajjar | 132KV Rajjar | Bolani | 047006 |  |  |  |  | Bolani
19 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | Jakkar | 7714 | 17.06.26 24.06.26 |  |  | Stringing of 11KV Jakkar Feeder | Village Jakkar, Khokhar Agar Khan Etc
20 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.9 (Chak Daulat) | 7709 |  |  |  | Stringing of 11KV Chak Daulat Feeder | Village Chak Daulat
28 | IESCO | Jhelum | Jhelum-I | Cantt | 132KV Jhelum | City Housing | 7729 | 17.06.26 22.06.26 | 0600 | 1000 | Errection of poles and stringing of ADS-IV Jhelum | City Housing Jhelum
29 | IESCO | Jhelum | Jhelum-2 | Sanghoi | 132KV Jhelum | Sanghoi | 7712 |  |  |  |  | Sanghoi
30 | IESCO | Jhelum | Jhelum-2 | Sanghoi | 132KV Jhelum | Safdar Shaheed | 7722 |  |  |  |  | Safdar Shaheed
31 | IESCO | Jhelum | Jhelum-2 | Sanghoi | 132KV Jhelum | Nathwala | 7716 |  |  |  |  | Nathwala
32 | IESCO | Jhelum | Jhelum-I | Cantt | 132KV Jhelum | LangarPur | 7725 |  |  |  |  | Langar pur etc.
33 | IESCO | Jhelum | Jhelum-1 | Cantt | 132KV Jhelum | Akram Shaheed | 7719 |  |  |  |  | Akram Shaheed
34 | IESCO | Jhelum | Jhelum-1 | Cantt | 132KV Jhelum | Zubair Shaheed | 7717 |  |  |  |  | Zubair Shaheed
35 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.2 (Chip Board) | 7702 | 17.06.26 24.06.26 |  |  |  | Kala Gurjan Ehsan Road Etc
36 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | Industrial | 7721 |  |  |  |  | S.I.E. Rathain
37 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.10 ( Kala Base) | 7710 |  |  |  |  | Kala Gurjan Ehsan Road Etc
38 | IESCO | Jhelum | Jhelum-1 | Urban | 132KV Jhelum | F-7 ( Kutchery) | 7707 | 21.06.26 |  |  | Installation/lying of HT Cable on 11KV Pakhwal Feeder | F-7 ( Kutchery)
39 | IESCO | Jhelum | Jhelum-1 | Urban | 132KV Jhelum | Ajmal Shaheed | 7718 |  |  |  |  | Ajmal Shaheed
40 | IESCO | Jhelum | Jhelum-1 | Urban | 132KV Jhelum | Karim Pura | 7729 |  |  |  |  | Karim Pura, Ramzan Pura, Etc
41 | IESCO | Jhelum | Jhelum-1 | Urban | 132KV Jhelum | Bilal Town | 7730 |  |  |  |  | Bilal Town, Bheri Colony, Ayesha Clinic
42 | IESCO | Jhelum | Jhelum-1 | Urban | 132KV Jhelum | Abbas Pura | 007727 |  |  |  |  | Abass Pura, Karim Pura, Ramzan Pura
43 | IESCO | Jhelum | Jhelum-2 | Rural | 132Kv Jhelum | Borian | 7726 |  |  |  |  | Borian
44 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.2 (Chip Board) | 7702 |  |  |  |  | Kala Gurjan Ehsan Road Etc
45 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | Industrial | 7721 |  |  |  |  | S.I.E. Rathain
46 | IESCO | Jhelum | Jhelum.2 | Rural | 132Kv Jhelum | F.10 ( Kala Base) | 7710 |  |  |  |  | Kala Gurjan Ehsan Road Etc
47 | IESCO | Jhelum | Jhelum-2 | Rural | 132KV Jhelum | Pakhwal | 7720 | 17.06.26 24.06.26 |  |  |  | Pakhwal
48 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Abdullah Pur | 058206 | 18.06.26 23.06.26 |  |  | Shifting of line Lillah Jhelum Road | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
49 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Jalal Pur | 058203 |  |  |  |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
50 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Sagharpur | 058202 |  |  |  |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
51 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | C.W.O. | 058204 |  |  |  |  | Army Area - Civil Work Organization.
52 | IESCO | Chakwal | P.D.Khan | P.D.Khan | Dandot | P.D.Khan | 029005 | 30.06.26 |  |  |  | Dk. Gola, Dera rajgan.etc
53 | IESCO | Chakwal | P.D.Khan | Pinanwal | Dandot | Duffer | 29001 |  |  |  |  | P.D Khan. Katchery etc
1 | IESCO | City | S.Town | F-Block | 132 KV GSS S.Town (T-II) | T&T | 095810 | 18.06.2026 20.06.2026 | 08:00 | 10:00 | Installation of new 50 KVA T/Former against NGSC | Pindora,7th Road,Saidpur Road,B-Block
2 | IESCO | City | S.Town | F-Block | 132 KV GSS I-8 (T-II) | 6th Road (Safety Purpose) | 095827 |  |  |  |  | Pindora,7th Road,Saidpur Road,B-Block
2 | IESCO | City | S.Town | F-Block | 132 KV GSS I-8 (T-IV) | PTCL (Safety Purpose) | 095823 |  |  |  |  | T&T Complex 7Th Road
1 | IESCO | Attock | Taxila | Taxila | 132 KV HMC Taxila | Harro | 021216 | 17.06.2026 22.06.2026 24.06.2026 | 08:00 Hours | 10:00 Hours | Installation of T/F for LV works | Kamra Ihatta
1 | IESCO | Cantt | Cantt | Civil Line | 132 KV Chaklala | Rawalpindi-III | 002510 | 17.06.2026 22.06.2026 | 7:00 | 10:00 | For shifting of HT/ LT Lines at Katchery Avenue | IESCO Complex, District Courts, DCO Office & Surrounding areas
1 | IESCO | Cantt | Rawat | Kallar | 132 KV Kallar | Doberan | 098106 | 20.06.2026 | 7:00 | 10:00 | For completion of PSH Work | Doberan & sorrounding area
2 | IESCO | Cantt | Rawat | RAWAT | 132KV Old Rawat | New Rawat | 017701 | 18.06.2026 21.06.2026 | 7:00 | 10:00 | For shifting of HT/ LT Lines at Potohar Avenue | Rawat & sorrounding area
3 |  |  |  |  | 132KV Sowan | Zaraj-I | 84711 |  |  |  |  | Zaraj-I & Surrounding area
4 | [5 empty] | Zaraj-II | 87423 |  |  |  |  | Zaraj-II & Surrounding area
5 | [5 empty] | Zeta-I | 87424 |  |  |  |  | Zeta Mall & Surrounding area
6 | [5 empty] | IST | 87422 |  |  |  |  | IST Universty & Surrounding area
7 | [5 empty] | Dk Awan | 87417 |  |  |  |  | DK Awan & Surrounding area
8 |  |  | Cantt | Sowan |  | Mora Nagial | 87421 |  |  |  |  | Mora Nagial & Surrounding area
1 | IESCO | Cantt | Tariqabad | Adyala | 132 KV Adyala | Kalyal | 109101 | 17.06.2026 20.06.2026 | 7:00 | 10:00 | For completion of LV Work Landco 3 | Dk. Parian, Adyala Jail, Shahpur, Gorakhpur, Sammar Zar Cly, Shah pur Syedan.
2 | [5 empty] | Adyala | 109106 |  |  |  | For completion of LV Work Lal Shah Bahar Shah | Adyala Road Khawaja Corporation, Mubarak Lane, Ali Town, Chungi No.20, Dhoke Noor etc.
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Kamalabad | Tulsa Road | 001026 | 23.06.2026 | 7:00 | 10:00 | For completion of LV work Arbaaz Street | Cirection colony, shah jeven colony, habib colony ect.
2 | [5 empty] | Lalazar | 001005 | 20.06.2026 |  |  | For completion of LV work Man o Salwa | Lalazar & sorrounding area
1 | IESCO | Attock | Taxila | Sang Jani | 220 KV Sang Jani | Shah Allah Ditta | 081011 | 22.06.2026 | 08:00 Hours | 10:00 Hours | LV works/Safety Hazards work | Shah Allah Ditta,Sarai Kharbooza
2 |  |  |  |  | 132 KV Cabinet Division | Saifia Town | 133601 |  |  |  |  | Saifia Town
1 | IESCO | City | Westridge | Tarnol | 132 KVA Tarnol | Top City | 104905 | 27.06.2026 01.07.2026 06.07.2026 11.07.2026 | 07:00 Hrs | 10:00 Hrs | Reconduction of HT Line of Top City Feeder | Top City
2 | [5 empty] | Nogazi | 104901 |  |  |  |  | Nogazi, Dk. Miskeen, Main Fateh Jang Road and surrounding area
1 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | Rehara | 105511 | 17.06.2026 20.06.2026 22.06.2026 | 6:00: AM | 09:00: AM | Shifting of HT Line in R/O Margallah Avenue link nRoad Near NIH Allergy Cemter Park Road Islamabad. | Rehara
2 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | B/Kahu | Mohra Noor | 122504 |  |  |  |  | Mohra Noor
3 | IESCO | IBD | XEN-I | G-6 | Rawal | Shehzad Town | 17424 |  |  |  |  | Shehzad Town
4 | IESCO | IBD | XEN-I | G-6 | Rawal | Club-1 | 14717 |  |  |  |  | Club-1
4 | IESCO | Jhelum | Jhelum-II | Sanghoi | Sanghoi | Khai Kulia | 126301 | 30.06.26 | 0600 Hrs | 0900 Hrs | Completion of Deposit work Lilla Road | Khai Kulia, Ban Shaheed etc
3 | IESCO | Jhelum | G. Khan | Guliana | Gujar Khan | Thakra | 4921 | 22.06.26 | 0600Hrs | 0900 Hrs | Completion of LV works | Chakri, Cheena
4 | IESCO | Jhelum | G. Khan | Guliana | Gujar Khan | Guliana | 4902 | 27.06.26 |  |  |  | Dulmi, Guliana etc
5 | IESCO | Jhelum | G. Khan | Guliana | Gujar Khan | RT MILL | 4907 |  |  |  |  | RTM Mills
1 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New Wah Grid | Hussain Abad | 14627 | 23-06-2026 | 05:00hrs | 10:00hrs | for safety purpose during erection of tower locatoin No. 18 for remodeling of 132kv T/Line New Wah Bahtar More to Fateh Jang | Hussainabad
1 | IESCO | Attock | Taxila | Mora Chowk | 132KV New Wah Grid | Garhi Afghan | 14626 | 20-06-2026 | 06:00 | 10:00 | for safety purpose during dismantling of Wah-06 between location No. 06 to 17 for remodeling of 132kv T/Line POF East, West & North | Bhdu ,Garhi Afghan, Mal pur
2 | [5 empty] | Pour Miana | 14608 |  |  |  |  | Pour Miana
3 | [5 empty] | Lala Zar | 14607 |  |  |  |  | Lala Zar
4 | [5 empty] | Munir Abad | 14628 |  |  |  |  | Munirabad, GT Road
5 |  |  |  | Wah Cant |  | Khan Abad | 14619 |  |  |  |  | Asifabad, Green Town, Basti Chokw
6 | PESCO | Hazara-1 | Hazara | Panj Katha (Khanpur) |  | Panj Katha (Khanpur) | 14606 |  |  |  |  | Panj Katha (Khanpur)
1 | IESCO | Chakwal | Chakwal | Ghaziabad | 132KV Grid Station Chakwal | Al-Qaim Mills | 002206 | 20.06.2026 & 21.06.2026 | 1300 | 1800 | for Tree Trimming to minimize momentary tripping | Al-Qaim Mills
1 | IESCO | GSO CIRCLE IESCO ISD | SS&TL DIVISION IESCO RAJJAR | A.E (T) Mangla | 20/26MVA Power Transformer T-1 At 132KV GSS R.B Mangla |  |  | 28-06-2026 to 02-07-2026 (Contineous) | 28-06-2026 09:00 Hrs | 02-07-2026 16:00 Hrs | For safety purpose during ndismentling of existing 20/26MVA Power Transformer T-1 along with replacement of 10/13MVA Power Transformer | No area will be affected as load of Power Transformer T-1 will be Shifted to Power Transformer T-2 through Bus Coupler.
1 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Chatta Bakhtwar | 105507 | 18.06.2026 22.06.2026 | 7:00: AM | 10:00: AM | Shifiting of HT/LT Line in Between the Road Near Street No 01 Gulshan Al Huda Islamabad | Chatta Bakhtwar
2 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Kund Rajgan | 105522 |  |  |  |  | Kund Rajgan
1 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Tarmari | 105503 | 30.06.2026 04.07.2026 | 7:00: AM | 10:00: AM | Directorate Genral Inter-services Intelligence Jinnah/pothwar Complex Islamabad at Jinnah/Pothwar Complex for conversion of 11 KVA ISI Feeder | Tarmari
2 | IESCO | IBD | XEN-I | Rawal | Tramri | Waheedabad | 105516 |  |  |  |  | Waheedabad
3 | IESCO | IBD | XEN-I | Tarlai | Tramri | Kund Rajgan | 105522 |  |  |  |  | Kund Rajgan
4 | IESCO | IBD | XEN-I | Tarlai | Tramri | King Hammad | 105526 |  |  |  |  | King Hammad
5 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Azad Shaheed | 105512 |  |  |  |  | Azad Shaheed
6 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Lehtrar Road | 105517 |  |  |  |  | Lehtrar Road
7 | IESCO | IBD | XEN-I | Tarlai | Tramri | Chatta Bakhwar | 105507 |  |  |  |  | Chatta Bakhwar
8 | IESCO | IBD | B/Kahu | B/Kahu (U) | Tramri | Kuri Road | 105506 |  |  |  |  | Kuri Road
9 | IESCO | IBD | B/Kahu | B/Kahu (U) | Tramri | Rehara | 105511 |  |  |  |  | Village Rehara
10 | IESCO | IBD | B/Kahu | B/Kahu (U) | Tramri | CM Pak Zong | 105509 |  |  |  |  | Independent
1 | IESCO | Chakwal | P.D.Khan | P.D.Khan | Dandot | KATCHERY | 29009 | 20.06.2026 | 7:00 | 10:00 | Completion of Bifurcation Work at Main Bazar P.D.Khan | Moh:Jaffarian, Peer Mustafa, Alam Shah, Kot Sultan, Islamia School, Sahotra, Hattar, Pithar Nadi, Mandi, M.Saddiq, Kotala Shah Kameer.
1 | IESCO | City | City | Gunjmandi | 132 KV Cantt | Fawara Chowk | 017934 | 20.06.2026 23.06.2026 | 07:00 Hrs | 10:00 Hrs | U/G to O/H System near Yadea bike Marir Chowk Rwp under DOP head (W/o No. 2k25-432-DOP-HT-53) | Fawara Chowk, Trunk Bazar, Talwaran Bazar, Sabzi Mandi and surrounding area
2 | [5 empty] | DHQ | 017930 |  |  |  |  | Distrcit Head Quarter Hospital Rawalpindi
3 |  |  |  | Committee Chowk |  | Liaquat Bagh | 017926 |  |  |  |  | College Road, Bohar Bazar and surrounding area
4 | [5 empty] | Iqbal Road-II | 017931 |  |  |  |  | Iqbal road, Lunda Bazar, Bohar Bazar, Moti Bazar, Lal Haveli and surrounding area
5 | [5 empty] | City | 103301 |  |  |  |  | Liaquat Road, College road, DAV College road and surrounding area
6 |  |  |  | Bhabra Bazar |  | Sarafa Bazar | 017920 |  |  |  |  | Sarafa Bazar, Children Park, Ziarat Shah Chan Charagh and surrounding area
1 | IESCO | Jhelum | Jhelum-II | Rural | Jhelum | F-9 Chak Daulat | 7709 | 21.06.26 | 0600 Hrs | 0900 Hrs | Bifurcation work of 11KV jakkar, & Chak Doulat feeders | Village Chak Daulat etc
2 | IESCO | Jhelum | Jhelum-II | Rural | Jhelum | Jakkar | 7714 |  |  |  |  | Jakkar, Kokhar, etc
1 | IESCO | Jhelum | Jhelum-II | Jhelum (Rural) | Jhelum | Pakhwal | 7720 |  |  |  | Installation of HT Cable Jakkar feeder | Pakhwal
1 | IESCO | IBD | B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New | 20.06.2026 23.06.2026 | 8:00: AM | 10:00: AM | Extension of Load CM Pak Complex Kurri Road Islamad. | IT.Park
2 | IESCO | IBD | XEN-1 | Tarlai | Rawal | Scheme-II | 17430 |  |  |  |  | Scheme-II
1 | IESCO | City | Satellite Town | Muslim Town | 132 KV Satellite Town | Shaheed Muhammad Din | 095818 | 30.06.2026 08.07.2026 | 07:00 Hrs | 10:00 Hrs | Dismanteling of HT LT Line & Transformer for rehabilitation from chungi No.08 to khanna pul Rawalpindi | Khurram Colony, Band Khanna Road, Bhariy Colony and surrounding area
2 |  |  |  | Gangal | 132 KV Tramari | Al-Noor Colony | 105515 |  |  |  |  | Al-Noor Colony, Khanna Road, Karimabad and surrounding area
3 |  |  |  |  | 132 KV I-8 | Jinnah Camp | 061117 |  |  |  |  | Jinnah Camp Complex
4 |  |  |  | Sadiqabad | 132 KV Satellite Town | C/Block | 095831 | 23.06.2026 |  |  | Installation of transformer at ijaz public school | C-Block, Dk. Khillo, Kuri road and surrounding area
1 | IESCO | Cantt | Cantt | Jhanda | 132KV Chaklala | MES | 002506 | 22.06.2026 29.06.2026 | 6:00 | 9:00 | For stringing work IRO Bifurcation of 11 KV Dk Gangal Feeder emanating from 132 KV GSS Chaklala Rawalpindi under ELR Head | MES & sorrounding area
1 | IESCO | City | S.Town | Muslim Town | 132 KV GSS I-8 (T-II) | Kuri Road | 061123 | 20.06.2026 | 08:00 Hours | 10:00 Hours | for Installation of 50KVA T/F for LV works | At Tayyaba Plaza Kuri Road Rawalpindi
1 | IESCO | City | Westridge | Westridge | 132 KV KTM | Dk. Chaudrian | 8621 | 29.06.2026 01.07.2026 04.07.2026 | 7:00 | 10:00 | Peshawer Road Underpass Project | Lane No. 04,05, Range Road and surrounding area
2 | IESCO | City | Westridge |  |  | Peshawer Road | 8612 |  |  |  |  | Peshawer Road, Mehboob Lane, Lane No. 04 to 07 Mehboob Lane, Fazeelabad and surroundig area
3 | IESCO | City | Westridge |  |  | Millatabad | 8616 |  |  |  |  | Misrial Road, Ilyas Colony, Lane 1,2,3 and surrounding area
4 | IESCO | City | Westridge |  |  | Cheering Cross | 8602 | 30.06.2026 05.07.2026 06.07.2026 |  |  |  | Gulnar Colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding area
5 | IESCO | City | Westridge |  |  | NRC | 8622 |  |  |  |  | Westridge Bazar, Hali Road, Iqbal Road, Churr Chowk, Race Course Ground and surrounding area
6 | IESCO | City | Westridge | Misrial | 132 KV Pirwadhai | Askari-XI | 43325 |  |  |  |  | Askari-XI, Lane 01 to 07 St. No. 01 to 14 and surrounding area