## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) Margalla | 132KV New Wah - (WAH-15) - Bahtermore (BMW-2) along with related earth switch |  |  | 31-05-2026 To 30-06-2026 (Contineous) | 31-05-2026 14:00 Hrs | 30-06-2026 14:00 Hrs | For erection & Stringing activities. (during this period, the portion of line New Wah - Bahternmore will be Isolated/ De-Energized as workingportion) | No area will be affected as 132KV GSS Bahtermore will be fed from 132KV GSS Fateh Jang side & 132KV GSS New Wah will be fed from 220KV GSS Burhan side.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 15-05-2026 To 30-06-2026 (Contineous) | 15-05-2026 18:00 Hrs | 30-06-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 60 to 70 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO CIRCLE IESCO ISD | SS&TL DIVISIONIESCO RAJJAR | A.E (T) Chakwal | 132KV Chakwal (CWL-7) - Bhagwal (NLA-1) - Talagang (TLG-1) |  |  | 24-05-2026 to 15-06-2026 (Contineous) | 24-05-2026 18:00 Hrs | 15-06-2026 18:00 Hrs | Remodeling/Stringing of Chakwal - Talagang circuit from Loc No. 01 to 33 | 132KV GSS Bhagwal will be affected from 09:00 Hrs to 15:00 Hrs. after that No area will be affected as 132KV Chakwal already feeding from 500KV Rawat, Bhagwal will be fed from Talagang side & Talagang will be fed from Tamman side. However, 35 to 40 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO CIRCLE IESCO ISD | SS&TL DIVISIONIESCO RAJJAR | A.E (T) Chakwal | 132KV Chakwal (CWL-7) - Bhagwal (NLA-1) - Talagang (TLG-1) |  |  | 15-06-2026 to 15-07-2026 (Contineous) | 15-06-2026 18:00 Hrs | 15-07-2026 18:00 Hrs | Remodeling/Stringing of Chakwal - Talagang circuit from Loc No. 01 to 33 | 132KV GSS Bhagwal will be affected from 09:00 Hrs to 15:00 Hrs. after that No area will be affected as 132KV Chakwal already feeding from 500KV Rawat, Bhagwal will be fed from Talagang side & Talagang will be fed from Tamman side. However, 35 to 40 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132KV New Wah (WAH-6) to POF (East, West & North)along with related earth switch |  |  | 24-05-2026 To 14-06-2026 Contineous | 24-05-2026 08:00 Hrs | 14-06-2026 16:00 Hrs | For safety purpose for erection of Loc No. 20 & stringing of conductor between Loc No. 16 to 17 for remodeling work of 132KV T/Line POF East, West & North | On 24-5-2026 from 08:00Hrs to 16:00Hrs, 132KV GSS South, East, West & North will be affected. After that No area will be effected as all POF Grids will be fed from WAH-5, which PTW will be cancelled on 24-05-2026 at 16:00 HRs.
1 | IESCO | GSO Circle IESCO Isd | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132KV New Wah (WAH-6) to POF (East, West & North)along with related earth switch |  |  | 14-06-2026 To 28-06-2026 Contineous | 14-06-2026 08:00 Hrs | 28-06-2026 16:00 Hrs | For safety purpose for erection of Loc No. 20 & stringing of conductor between Loc No. 16 to 17 for remodeling work of 132KV T/Line POF East, West & North | On 14.06.2026 from 08:00Hrs to 16:00Hrs, 132KV GSS South, East, West & North will be affected. After that No area will be effected as all POF Grids will be fed from WAH-5, which PTW will be cancelled on 14.06.2026 at 16:00 HRs.
1 | IESCO | Cantt | Plandri | Plandri | 132KV GSS Plandri. | Azad Pattan | 48525 | 16.05.2026 18.05.2026 21.05.2026 24.05.2026 01.06.2026 04.06.2026 08.06.2026 10.06.2026 13.06.2026 | 06:00 Hrs | 15:00 Hrs | for Stringing of Tower Loc # 18 to 31 at 132KV SDT T/Line Azad Pattan Plandri | Azad Pattan & Surrounding area
1 | IESCO | Chakwal | Chakwal | Main Bazar | Chakwal | ISLAMIA CHOWK | 2223 | 08.06.2026 11.06.2026 13.06.2026 15.06.2026 17.06.2026 | 7:00 | 10:00 | For Completion of D-Work of Road Widening Project (Shifting of HT/LT Line And T-Formers From Bhoun Road Chakwal) | Moti Bazar, Islamia Chowk to Bhoun Chowk, Nia Mohallah, Khumeni Chowk, Moh: Gharbi, Moh: Khawajgan, Sarpak, Kot Ganish Eid Gah,
13 | IESCO | IBD | B/Kahu | J/Gali | 132KV Kuldana Murree | GHARIAL | 13711 | 03.06.2026 10.06.2026 16.06.2026 | 09:00 | 14:00 | Removal / Shifting of services remodling of Jhika Gali Chowk Tehsil & District Murree | J/gali Bazar Gjarial camp.Kashmiri Bazar,seher bagla Aliot
14 | IESCO | IBD | B/Khu | B/Khu (R) | 132/220 KV G/S B/Khu | Pir Sohawa | 122503 | 04.06.2026 09.06.2026 (Cancelled 15.06.2026 18.06.2026) | 07:00 | 11:00 | Reconducting of 11KV Pir Sohawa Feeder | Kotla, Pir sohawa, Kohala bala and surrounding area
14 | IESCO | IBD | NO.I | Tarlai | Tramari | Shareefabad | 105502 | 16.06.2026 20.06.2026 | 07:00 | 11:00 | Area Planning of 11KV UC Road Feeder and 11KV Koral Feeder | Shareefabad & Surrounding area
15 | IESCO | IBD | NO.I | Tarlai | Tramari | Ghouri Garden | 105513 |  |  |  |  | Ghouri Garden & Surrounding area
1 | IESCO | City | S/Town | Sadiqabad | 132KV Chaklala | Benazir Bhutto Hospital | 2531 | 03.06.2026 10.06.2026 17.06.2026 | 07:00 | 11:00 | Sanction for Dual Source IRO Rawalpindi Institute of Cardialogy Hospital Rawalpindi | Benazir Bhutto Hospital
2 | IESCO | City | City | Zafar-ul-Haq | 132KV Chaklala | Tehmasamabad | 2518 |  |  |  |  | Tehmasamabad
3 | IESCO | City | City | Zafar-ul-Haq | 132KV Chaklala | Dk.Hukam Dad | 2527 |  |  |  |  | Dk.Hukam Dad
4 | IESCO | Cantt | Cantt | Civil Line | 132KV Chaklala | RIC | 2534 |  |  |  |  | RIC and Surrounding area. | During the Shut down the load of RIC will be shifted to Dk. Farman Ali feeder
5 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Rahimabad | 002541 |  |  |  |  | Rahimabad & sorrounding area
1 | IESCO | Chakwal | Chakwal | Ghazi Abad | 132KV Grid Station Chakwal | JAMALWAL | 002219 | 09.06.2026 11.06.2026 15.06.2026 22.06.2026 | 0700 Hrs | 1200 Hrs | for Stringing of Location # 08 to 25 of 132KV T/Line Chakwal - Talagang | Jamalwala & Surrounding Area
2 | [5 empty] | MENGAN | 002211 |  |  |  |  | Mengan & Srounding area
1 | IESCO | IBD | XEN-I | Tarlai | Tarmari | Kund Rajgan | 105522 | 04.06.2026 06.06.2026 10.06.2026 (Cancelled 16.06.2026) | 8:00: AM | 11:00: AM | External Elecfrification Work IRO IT Technology Park Chak Shahzad Islamabad | Chata Bakhtawer & Surrounding Areas
2 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New |  |  |  |  | IT.Park
3 | IESCO | IBD | XEN-I | Tarlai | Rawal | Scheme-II | 17430 |  |  |  |  | Scheme-I & Scheme-II
4 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New | 09.06.2026 (Cancelled) (23.06.2026 25.06.2026 |  |  |  | IT.Park
2 | IESCO | Attock | Taxila | Hassan Abdal | 132KV New wah | Hassan Abdal | 14617 | 04-06-2026 08-06-2026 10-06-2026 15-06-2026 17-06-2026 | 03:00pm | 06:00pm | shifting of HT/LT line Hassan Abdal city under City Beautification and public safety initiative | Hassan Abdal | 11 KV Hssan Abdal Feeder is Feeding to court complex worthy C.E(O&M) vide letter no.140-48 dated 08.01.2026 has stoped all shut down during court working hours (08.00 am to 03.00 PM ) so after working hours shut down is being processed
1 | IESCO | Cantt | Cantt | Civil Line | 132KV Chaklala | Rawalpindi-III | 002510 | (Cancelled 13.06.2026 20.06.2026) | 8:00 | 11:00 | For Removal of Safety Hazard at Ishfaq Hospital near Punjab House Safety Hazard & near Chaklala GSS & for completion of LV Proposal at Street No.02 Dk Khabba | IESCO Complex, District Courts, DCO Office & Surrounding areas
2 | [5 empty] | Jahangir Road | 002505 |  |  |  |  | Jahangir Road & Surrounding areas
3 |  |  |  | Jhanda | 132KV Cantt | Jhanda Chichi | 017921 |  |  |  |  | Jhanda Chichi & sorrounding area
4 |  |  |  | Civil Line | 132KV Cantt | Dk Farman Ali | 017922 |  |  |  |  | Dhoke Farman Ali, Dk Khabba & sorrounding area
5 |  |  |  | Chaklala | 132KV Chaklala | Kot Jabbi | 002539 |  |  |  | For Removal of Safety Hazard at Street No.07, 08 & 09 Gulbahar Colony Chaklala | Kot Jabbi & sorrounding area
2 | IESCO | Attock | Taxila | Sang Jani | 132 KV B-17 Grid | Sarai Kharbooza | 121802 | 05.06.2026 09.06.2026 10.06.2026 11.06.2026 12.06.2026 15.06.2026 17.06.2026 (Cancelled 13.06.2026 16.06.2026) | 07:00 Hours | 09:00 Hours | AMI Project | Dhoke Abbasi,Johd,Sarai Kharbooza
1 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Jhangi | 008608 | 23.06.2026 29.06.2026 | 08:00 Hrs | 11:00 Hrs | Near Benazir Chowk Fateh Jang Road Rawalpindi | Shaheenabad, Faisal Colony, Jhangi Syedan, Tarnol and surrounding area
1 | IESCO | City | Westridge | Westidge | 132 KV KTM | NRC | 008622 | 09.06.2026 13.06.2026 | 07:00 Hrs | 10:00 Hrs | Near Police Station Westridge | Westridge Bazar, Hali Road, Churr Chowk, Race Course Ground and surrounding area
1 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | Sector-IV | 002536 | 08.06.2026 11.06.2026 15.06.2026 18.06.2026 22.06.2026 29.06.2026 | 07:00 | 11:00 | Stringing of Work IRO Bifurcation of 11KV Dk. Gangal feeder emanating from 132KV Chaklala GSS under ELR Head (2k26-431 ELT-HT-01) | Airport Housing Society, Sector-4 (I.G.H Block) & Surrounding area.
2 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | APHS | 002526 |  |  |  |  | Airport Society, Dk. Anwar & Surrounding area.
3 | IESCO | Cantt | Chaklala | Chaklala | 132KV Chaklala | Rehmatabad-1 | 002519 |  |  |  |  | Rehmatabad-1 & Surrounding area
4 | IESCO | City | Westridge | Gulzar-e-Quaid | 132KV Chaklala | PAF | 002509 |  |  |  |  | PAF & Surrounding area.
5 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Takbeer-I | 2543 |  |  |  |  | Takbeer Project & sorrounding area
6 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Chaklala | 2503 |  |  |  |  | Chaklala & Surrounding area.
7 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | Kot Jabbi | 2539 |  |  |  |  | Kot Jabbi & Surrounding area.
9 | IESCO | City | Westridge | Tarnol | 132 KV Tarnol | Nogazi | 104901 | 10.06.2026 24.06.2026 | 07:00 | 11:00 | Reconductoring of HT Line of Top City feeder | Nogazi and surrounding area
10 | IESCO | City | Westridge | Tarnol | 132 KV Tarnol | Bajniyal-1 | 104910 |  |  |  |  | Bajniyal-1 and surrounding area
11 | IESCO | City | Westridge | Tarnol | 132 KV Tarnol | Top City | 104905 |  |  |  |  | Top City and surrounding area
12 | IESCO | Cantt | Cantt | Korang | 132KV NPF | FECHS | 90001 | 06.06.2026 09.06.2026 13.06.2026 20.06.2026 (Cancelled 16.06.2026 23.06.2026) | 07:00 | 11:00 | For erection of poles IRO 11 KV Independent Feeder IRO Fedeation Employees Housing Society Lohi Bher Islamabad | FECHS & Surrounding areas
13 | IESCO | Cantt | Cantt | Korang | 132KV NPF | NPF-I | 090003 |  |  |  |  | NPF & Surrounding areas
14 | IESCO | Cantt | Cantt | Korang | 132KV NPF | NPF-II | 090004 |  |  |  |  | NPF & Surrounding areas
15 | IESCO | Cantt | Cantt | Korang | 132KV NPF | Doctor Town | 090016 |  |  |  |  | Doctor Town
16 | IESCO | Cantt | Cantt | Korang | 132KV NPF | PWD-I | 090014 |  |  |  |  | PWD'& Surrounding areas
17 | IESCO | Cantt | Cantt | Korang | 132KV NPF | PWD-II | 090015 |  |  |  |  | PWD'& Surrounding areas
18 | IESCO | City | Taeiqabad | Adyala | 132KV Adyala | Adyala | 109106 | 10.06.2026 30.06.2026 | 07:00 | 11:00 | for Stringing of Work IRO Area Planning of 11KV Shahpur & Dk. Noor feeder | Adyala & Surrounding area.
19 | IESCO | City | Taeiqabad | Adyala | 132KV Adyala | Dk. Noor | 109104 |  |  |  |  | Dk. Noor & Surrounding area.
20 | IESCO | Cantt | Taeiqabad | Adyala | 132KV Adyala | Samarzar | New |  |  |  |  | Samarzar & Surrounding area.
1 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | Old Rawat | 17716 | 09.06.2026 13.06.2026 20.06.2026 (Cancelled 24.06.2026) | 7:00 | 11:00 | For shifting of HT line from T-Chowk to HASCOL Pump T-Chowk Flyover | Rawat & sorrounding area
2 | IESCO | Cantt | Rawat | Rawat |  | New Rawat | 17701 |  |  |  |  | Rawat & sorrounding area
3 | IESCO | Cantt | Rawat | Rawat | 500KV New Rawat | AOWHS | 64506 |  |  |  |  | Emaar & sorrounding area
4 | IESCO | Cantt | Rawat | Rawat | 132KV Old Rawat | Suparco | 17717 |  |  |  |  | Suparco & sorrounding area
5 | IESCO | Cantt | Rawat | Rawat |  | CWO | 17722 |  |  |  |  | CWO & surrounding area
6 | IESCO | Cantt | Rawat | Kallar | 132 KV Kallar Syedan | Doberan | 098106 | 12.06.2026 21.06.2026 |  |  | For Removal of Safety Hazard at Chak Mirza Sada Kamal | Doberan & surrounding area
7 | IESCO | Cantt | Rawat | Kallar |  | Kambeli Sadiq | 098102 | 08.06.2026 17.06.2026 |  |  | For Removal of Safety Hazard at Makh & Makh Chaudrian | Kambeli Sadiq & surrounding area
1 | IESCO | Attock | Attock | Attock City | 132KV Attock | Attock Rural | 75101 | 06.06.2026 10.06.2026 13.06.2026 16.06.2026 20.06.2026 24.06.2026 29.06.2026 | 07:00 | 11:00 | Reconducting of 3-Meela Feeder | Attock, Takbeer Colony & surrounding area
2 | IESCO | Attock | Attock | Attock City | 132KV Attock | Teen Mela | 75113 |  |  |  |  | Teen Mela & Surrounding Area
3 | IESCO | Attock | Attock | Attock City | 132KV Attock | Bagh Nelab | 75114 |  |  |  |  | Bagh Nelab & Surrounding Area
5 | IESCO | Attock | Attock | Attock City | 132KV Attock | Fawara Chowk | 75103 | 09.06.2026 13.06.2026 18.06.2026 |  |  | Replacement of Old Wire & Pole Under Beautification of Attock | A.B.C.R Block, City area, Lorry area & surrounding area
6 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Katchery | 18902 | 11.06.2026 23.06.2026 30.06.2026 |  |  | shifting nof line from Exsiting line to new proposed HT Str,58 IRO 11KV independent Feeder MCH Attock | Katchery & Surrounding Area
7 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Dar ul Islam Colony | 18909 |  |  |  |  | Dar ul Islam Colony & Surrounding Area
8 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Attock Cantt | 18901 |  |  |  |  | Attock Cantt & Surrounding Area
|  |  | Rawat | RAWAT | 132KV Old Rawat | New Rawat | 017701 | 06.06.2026 13.06.2026 20.06.2026 | 8:00 | 11:00 | For shifting of HT/ LT Lines at Potohar Avenue | Rawat & sorrounding area
2 |  |  |  |  | 132KV Sowan | Zaraj-I | 87411 |  |  |  |  | Zaraj-I & Surrounding area
3 | [5 empty] | Zaraj-II | 87423 |  |  |  |  | Zaraj-II & Surrounding area
4 | [5 empty] | Zeta-I | 87424 |  |  |  |  | Zeta Mall & Surrounding area
5 | [5 empty] | IST | 87422 |  |  |  |  | IST Universty & Surrounding area
6 | [5 empty] | Dk Awan | 87417 |  |  |  |  | DK Awan & Surrounding area
7 |  |  | Cantt |  |  | Mora Nagial | 87421 |  |  |  |  | Mora Nagial & Surrounding area
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Cantt | Khadim Hussain Road | 17906 | 07.06.2026 21.06.2026 28.06.2026 (Cancelled 14.06.2026) | 8:00 | 11:00 | For Construction of GPO Underpass Signal Free Mall Road Project Part A Rawalpindi | Khadim Hussain Road
2 |  |  |  | Tariqabad |  | CMH Flats | 17936 |  |  |  |  | CMH Flats
3 |  |  | Cantt | Civil Line |  | Adam Jee Road | 17923 |  |  |  |  | Adam Jee Road
4 |  |  |  | Civil Line |  | Askari 7 | 17919 |  |  |  |  | Askari 7
5 |  |  |  | Civil Line |  | Sir Syed Road | 17913 |  |  |  |  | Sir Syed Road
6 |  |  |  | Saddar |  | FFC | 17927 |  |  |  |  | Fauji Fertilizer
7 |  |  | Tariqabad | R.A Bazar |  | GHQ Express | 017924 |  |  |  |  | GHQ & sorrounding area | Subject to provision of NOC from GHQ
8 |  |  |  | Tariqabad | 132KV Chaklala | State Bank | 2521 |  |  |  |  | State Bank
5 | IESCO | City | Westridge | Tarnol | 132 KV KTM | Golra | 018906 | 09.06.2026 11.06.2026 23.06.2026 (Cancelled dated 30.06.2026) | 07:00 | 11:00 | A.Q Khan research Laboratory | Naseerabad, Awan Colony and surrounding area
6 | IESCO | City | Westridge |  |  | Azharabad | 008620 |  |  |  |  | Peshawer Road, Pind Paracha and surrounding areas
7 | IESCO | City | Westridge |  |  | Zarkoon Heights | 008628 |  |  |  |  | Zarkoon Heights
8 | IESCO | City | Westridge |  |  | New Azharabad
9 | IESCO | City | Westridge |  |  | Jhangi | 008608 |  |  |  |  | Shaheenabad, Faisal Colony, Jhangi Syedan, Tarnol and surrounding area
10 | IESCO | City | Westridge |  |  | Quaid-e-Azam Hospital | 008624 |  |  |  |  | Quaid-e-Azam Internation Hospital
11 | IESCO | City | Westridge |  |  | CWO | 008601 |  |  |  |  | CWO
12 | IESCO | City | Westridge |  |  | Shamas Colony | 008626 |  |  |  |  | H-13 and surrounding area
13 | IESCO | City | Westridge | Westridge |  | Dk. Chaudrian | 008621 | 10.06.2026 18.06.2026 (Cancelled dated 15.06.2026 |  |  | Emergency Work Peshawer Road Underpass Project | Lane No. 04,05, Range Road and surrounding area
14 | IESCO | City | Westridge |  |  | Peshawer Road | 008612 |  |  |  |  | Peshawer Road, Mehboob Lane, Lane No. 04 to 07 Mehboob Lane, Fazeelabad and surroundig area
15 | IESCO | City | Westridge |  |  | Millatabad | 008616 |  |  |  |  | Misrial Road, Ilyas Colony, Lane 1,2,3 and surrounding area
16 | IESCO | City | Westridge |  |  | Cheering Cross | 008602 |  |  |  |  | Gulnar Colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding area
17 | IESCO | City | Westridge |  |  | NRC | 008622 |  |  |  |  | Westridge Bazar, Hali Road, Iqbal Road, Churr Chowk, Race Course Ground and surrounding area
18 | IESCO | City | Westridge |  | 132 KV Pirwadhai | Cobe Line | 043329 |  |  |  |  | Cobe line and surrounding area
19 | IESCO | City | Westridge | Misrial |  | Askari-XI | 043325 |  |  |  |  | Askari-XI, Lane 01 to 07 St. No. 01 to 14 and surrounding area
1 | IESCO | City | S.Town | F/Block | 132 KV I-8 | F/Block | 061114 | 09.06.2026 13.06.2026 | 07:00 | 11:00 | Project rehabilitation of Sewerage System at Opposite Holy Family Hospital Gate No. 06 9A/C 02 143120453900) | F/Block & Surrounding area
1 | IESCO | Attock | Taxila | Margalla | 132 KV Bahtar | Dirik | 112006 | 10-06-2026 to 12-06-2026 | 07:00 | 12:00 | for Stringing of 500KV D/C T/Lie from Terbela to Islamabad west S/Station between section T.No.162-165 | Village Bahtar, Dirik, Pind Buhadar Khan.
3 | IESCO | Jhelum | Gujar Khan | Sohawa | Sohawa | Nai Khangah | 125004 | 12.06.2026 | 08:30 | 10:30 | For Completion of LV Works | Nai Khangah
2 | IESCO | Jhelum | Gujar Khan | Guliana | Gujar Khan | RTM Mills | 004907 | 13.06.2026 | 08:30 | 10:30 |  | RTM Mills
4 | IESCO | Jhelum | Gujar Khan | Guliana | Gujar Khan | Guliana | 004902 | 13.06.2026 | 08:30 | 10:30 |  | Guliana
1 | IESCO | Chakwal | Chakwal | Ghazi Abad | 132KV GSS Chakwal | Mureed | 002201 | 13.06.2026 14.06.2026 20.06.2026 21.06.2026 | 0700 Hrs | 1300 Hrs | for installation of Neck Extension at Location # 07 to 08 of 132KV T/Line Chakwal - Talagang | Mureed
2 | [5 empty] | Al-Qaim Mills | 002206 |  |  |  |  | Al-Qaim Mills
3 | [5 empty] | JAMALWAL | 002219 |  |  |  |  | JAMALWAL
4 | [5 empty] | PAF | 002215 |  |  |  |  | PAF
5 | [5 empty] | MENGAN | 002211 |  |  |  |  | MENGAN
1 | IESCO | Chakwal | Dhudial | Dhudial | Padshahan | DHUDIAL CITY | 79104 | 15.06.2026 | 8:00 | 11:00 | For Completion of LV Work Village Dhok Jakkar Near School | Harrar, Dorey, Thanil Chohan, Fim Kasar, Kot Iqbal, Jethal, Sarral, Rawal Bala, Rawal Zair,
1 | IESCO | Attock | Attock | Attock City | 132KV Attock | People Colony | 75110 | 15.06.2026 17.06.2026 | 09:30 | 11:30 | Installation of transformer Mohl Hadri Sheen Bagh | People Colony
2 | IESCO | Attock | Attock | Attock City | 132KV Attock | Shakar Dara | 75111 |  |  |  |  | Shakar Dara
3 | IESCO | Attock | Attock | Attock City | 132KV Attock | Mari | 75112 |  |  |  |  | Mari
1 | IESCO | Cantt | Mandra | Wadala | 500KV New Rawat | Jatha Hathial | 064503 | 11.06.2026 16.06.2026 | 8:00 | 11:00 | For rerouting of HT Line IRO Rawalpindi Ring Road Project | Jatha Hathial & sorrounding area
2 |  |  | Tariqabad | Adyala |  | Jarrar Camp | 064510 |  |  |  |  | Jarrar Camp & sorrounding area
1 | IESCO | IBD | NO.II | G-9 | H-11 | CWO | 72708 | 23-06-2026 (Cancelled dated 16-06-2026) | 07:00 | 11:00 | for removal of HT fault on independent 11 KV EOBI Feeder Emanating from 132 KV H-11 Islamabad | Independent
2 | IESCO | IBD | NO.II | G-9 | H-11 | G-10 Markaz | 72720 |  |  |  |  | G-10 Markaz
3 | IESCO | IBD | NO.II | G-9 | H-11 | Category House | 72711 |  |  |  |  | Independent
4 | IESCO | IBD | NO.II | G-9 | H-11 | G-10 Muave Area | 72703 |  |  |  |  | G-10/2
5 | IESCO | IBD | NO.II | F-8 | F-11 | F-10 MKZ | 069208 | 17-06-2026 |  |  | for Reconductoring of 11 KV F-10 Feeder From ACSR Rabbit to ACSR DOG From Street No.63 F-10/3 to Gull Plaza F-10 Markaz Islamabad 2k25412DOPHT03 | F-10 MKZ
6 | IESCO | IBD | NO.II | F-8 | F-11 | F-10 | 069203 |  |  |  |  | F-10
7 | IESCO | IBD | NO.II | F-8 | F-11 | F-10/3 | 069212 |  |  |  |  | F-10/3
8 | IESCO | IBD | No.II | I-9 | Zero Point | I-8/2 | 22336 | 22-06-2026 |  |  | Installation of LBS at 11KV H-8 Feeder from 132KV Zero Point Grid Station W/O 2k26412DOPHT31 | I-8/2 & sorroundings
9 | IESCO | IBD | No.II | I-9 | Zero Point | I-8/3 | 22337 |  |  |  |  | I-8/3
10 | IESCO | IBD | No.II | I-9 | Zero Point | H-8 | 22325 |  |  |  |  | H-8
11 | IESCO | IBD | No.II | I-9 | Zero Point | Shifa | 22341 |  |  |  |  | H-8
1 |  | GSO | SS&TL Rwp | AET RWP | 132KV T/Line M.E.S - K.T.M Ckt (MES-1 - KTM-4) & 132 KV T/Line M.E.S -S/Town Ckt (MES-2 - STN-1) Along with related earth switch | O/G Feeder (T-1) |  | 13.06.2026 & 14.06.2026 | 06:30 | 14:00 | Dismentling of SPA Pole at Loc # 37 & Stringing from Loc# (36-37) and (31-32) under Construction of underpass Project . | O/G Feeder (T-1)
[6 empty] | RA Bazar | 107601 |  |  |  |  | RA Bazar
[6 empty] | AWT | 107603 |  |  |  |  | AWT
[6 empty] | Mall Road | 107602 |  |  |  |  | Mall Road
[6 empty] | AFIC | 107615 |  |  |  |  | AFIC
[6 empty] | Tehch Bhatta | 107607 |  |  |  |  | Tehch Bhatta
[6 empty] | MH-3 | 107611 |  |  |  |  | MH-3
[6 empty] | Qasim MKT | 107613 |  |  |  |  | Qasim MKT
[6 empty] | CMH-1 | 107608 |  |  |  |  | CMH-1
[6 empty] | CMH-2 | 107614 |  |  |  |  | CMH-2
[6 empty] | Sprint Mall | 107617 |  |  |  |  | Sprint Mall
[6 empty] | O/G Feeder (T-2) |  |  |  |  | Stringing from Loc # (36-37) and (31-32) under Construction of underpass Project . | O/G Feeder (T-2)
[6 empty] | Kiyani Road | 107604 |  |  |  |  | Kiyani Road
[6 empty] | Army Flats | 107606 |  |  |  |  | Army Flats
[6 empty] | M.H-1 | 107609 |  |  |  |  | M.H-1
[6 empty] | M.H-2 | 107610 |  |  |  |  | M.H-2
[6 empty] | Zeeshan Colony | 107612 |  |  |  |  | Zeeshan Colony
[6 empty] | Haider Road | 107616 |  |  |  |  | Haider Road
[6 empty] | NLC | 107618 |  |  |  |  | NLC
[6 empty] | Canning Road | 107621 |  |  |  |  | Canning Road
[6 empty] | Hospital Road | 107620 |  |  |  |  | Hospital Road
[6 empty] | N.I.A.S.R | 107619 |  |  |  |  | N.I.A.S.R
[6 empty] | New GHQ | 107605 |  |  |  |  | New GHQ
| IESCO | City | Westridge | Westridge | 132KV Grid Station KTM | Chairing Cross | 8602 |  |  |  | Stringing from Loc # 31 to 37 under Construction of underpass Project | Chairing Cross & Srounding area
[6 empty] | Millatabad | 8616 |  |  |  | For Safety Purpose | Millatabad & Srounding area
|  |  |  | Misrial | 132KV Grid Pirwadhai | Askari-xi | 43325 |  |  |  |  | Askari-xi & Srounding area
1 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | IT.Park | New | 13.06.2026 18.06.2026 (IT.Park already Cancelled dated 16.06.2026, 23.06.2026 & 25.06..2026) | 8:00: AM | 11:00: AM | External Elecfrification Work IRO IT Technology Park Chak Shahzad Islamabad | IT.Park
2 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | Kuri Road | 105506 |  |  |  |  | Kuri Road
3 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tarmari | Rehara | 105511 |  |  |  |  | Rehara,Mohra Noor
4 | IESCO | IBD | XEN-B/Kahu | B/Kahu (U) | Tramri | CM Pak Zong | 105509 |  |  |  |  | CM Pak Office
1 | IESCO | IBD | XEN-I | Khanna Dak | NPF | Lohi Bher | 90002 | 13.06.2026 16.06.2026 20.06.2026 23.06.2026 | 8:00: AM | 11:00: AM | Erection of Poles/Stringing Work IRO 11KV Independent Feeder IRO Federatio Employees Housing Society Lohi Bher Islamabad | Lohi Bher,Koral Harn Mera Toot Stop
1 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | APF | 96808 | 13.06.2026 20.06.2026 | 8:00 | 11:00 | For Jumpering of HT Line IRO Qurtaba City Chakri | APF & surrounding area
2 | [5 empty] | SPD | 96806 |  |  |  |  | SPD & surrounding area
3 | [5 empty] | Paryal | 96809 |  |  |  |  | Paryal & surrounding area
4 | [5 empty] | Chakri | 96801 |  |  |  |  | Chakri & surrounding area
5 | [5 empty] | HASCOL | 96812 |  |  |  |  | Hascol & surrounding area
1 | IESCO | Cantt | Cantt | Saddar | 132KV MES | Mall Road | 107602 | 14.06.2026 | 6:00 | 9:00 | For shifting of Utility Services, Construction of underpass at GPO Chowk on Mall Road Rawalpindi (Part-A) Signal Free Mall Road Project | Mall Road & Surrounding area
2 | [5 empty] | AWT | 107603 |  |  |  |  | Mall Road & Surrounding area
3 | [5 empty] | Hospital Road | 107620 |  |  |  |  | Mall Road & Surrounding area
4 | [5 empty] | Canning Road | 107621 |  |  |  |  | Mall Road & Surrounding area
5 | [5 empty] | Haider Road | 107616 |  |  |  |  | Sprint & Surrounding area
6 | [5 empty] | Sprint | 107617 |  |  |  |  | AWT & Surrounding area
7 |  |  |  |  | 132KV Cantt | AFIC | 17918 |  |  |  |  | AFIC & Surrounding area
1 | IESCO | Chakwal | Chakwal | Azhar Shaheed | Chakwal | BHARPUR | 2222 | 15.06.2026 | 7:00 | 10:00 | Completion of work at 132KV Grid Station Chakwal | Village Rehna Sadaat, Bhatti Gujjar, Walana, Hattar, Bhar Pur, Maira Aima, Nato Wala Kahar & Ratta Sharif etc
2 | IESCO | Chakwal | Chakwal |  |  | BHOUN | 2202 |  |  |  |  | Bhoun-Kallar Kahar Road, Shah Multani, Bhoun, Thoa Hamayoun, Khai etc
3 | IESCO | Chakwal | Chakwal |  |  | KSM-3 MILLS | 2212 |  |  |  |  | Koh-e-Noor Spinning Mills Unit-03
4 | IESCO | Chakwal | Chakwal |  |  | KARYALA | 2216 |  |  |  |  | Mohallah Yasir Abad, Village Sadwal, Thathi Jamoon, Janga, Mohra Thanil, Karyala.
5 | IESCO | Chakwal | Chakwal | Kallar Kahar | Noorpur | DHARUKNA | 59708 | 16.06.2026 18.06.2026 |  |  | Completion of LV Work at Village Jhamra K/ Kahar | Dharukna, Wasnal, Jhamra, Pahar Khan, Kahoot, Bhaseen, Taliaylah, Shery Wala Kahar.
6 | IESCO | Chakwal | Chakwal |  | Kallar Kahar Town Ship | KHAIRPUR | 130802 | 20.06.2026 |  |  | Completion of LV Work Vill Khandowa, Vill: Khokhar | Chak Khurshi, Khandowa, Khairpur, Khokarbala, Julabi Chowk etc.
7 | IESCO | Chakwal | Chakwal |  |  | SARDHI | 130803 | 22.06.2026 |  |  | Completion of LV Work at Village Ransial | Ransial, Buchal Khurd, Chak Misri, Sardhi, Dk Saidan etc.
8 | IESCO | Chakwal | Chakwal | Bhagwal | Bhagwal (Neela) | KARSAL | 64307 | 20.06.2026 |  |  | Completion of LV Work at Village Karsal Sani Chowk | Karsal, Dhok Walana, Dhok Mistrian, Sidher, Chawali, Dhok Sultan, Dhok Ratti Paddi
1 | IESCO | Chakwal | Chakwal | Ghaziabad | Chakwal | AL-QAIM MILLS | 2206 | 13.06.2026 14.06.2026 | 14:00 | 18:00 | For Tree Trimming to minimize momentary trippings | Independent Feeder (Al-Qaim Textile Mills)
1 | IESCO | Attock | Taxila | Mohra Chowk | 132 KV New Wah | Rashid Minhas | 014620 | 16.06.2026 | 08:00 Hours | 10:00 Hours | Installation of T/F Sultan Pur Mohallah Tanoli and Mohallah Sultan Pur Mohallah Takki LV work | Islampur,Lab,AamGah,and sorrunding area
1 | IESCO | Cantt | MANDRA | SUKHO | JATLI | SUKHO | 007403 | 13.06.2026 | 08:30 Hrs | 10:30 Hrs | Completion of Safety Hazard work | SUKHO, MOHRA KALA KHAN, KARNALI, MOHRA JASWAL, CHOORA ETC
2 | IESCO | Cantt | MANDRA | SUKHO | JATLI | BHAIR KALYAL | 007409 |  | 08:30 Hrs | 10:30 Hrs |  | BHAIR KALYAL, JHUNGAL, MOHRA AMIN, DK BABA HAIDER, DARKALI ETC
3 | IESCO | Cantt | MANDRA | SUKHO | JATLI | KURNB KASWAL | 007410 |  | 08:30 Hrs | 10:30 Hrs |  | MOHRA MALKAN GUJRAN, JHANGI JALAAL, SAR SHARIF, OGAHOON ETC
4 | IESCO | Cantt | MANDRA | SUKHO | JATLI | BHANGALI | 007406 |  | 08:30 Hrs | 10:30 Hrs |  | DK QASIM ALI, BHANGALI GUJJAR, BHANGALI KHINGER, MOHRA HIDAYAT ETC
1 | IESCO | City | S/Town | Chandni Chowk | 132KV GSS S/Town | Faizabad | 95813 | 13.06.2026 | 06:30 Hrs | 08:00 Hrs | Tree Trimming in front of 132kv Satellite Town Grid on directions of CEO IESCO | Faizabad
2 | IESCO | City |  | Sadiqabad |  | Ojri camp | 95832 |  |  |  |  | Ojri camp
3 | IESCO | City |  | Dk. Kala Khan |  | Farooq Azam | 95806 |  |  |  |  | Farooq Azam
4 | IESCO | City |  | Muslim Town |  | Shakrial | 95803 |  |  |  |  | Shakrial
5 | IESCO | City |  | Sadiqabad |  | Sadiqabad | 95815 |  |  |  |  | Sadiqabad
6 | IESCO | City |  | Committee Chowk |  | Dhoke Khaba | 95821 |  |  |  |  | Dhoke Khaba
7 | IESCO | City |  | Asghar Mall |  | Abu Bakar | 95825 |  |  |  |  | Abu Bakar
8 | IESCO | City |  | F/Block |  | Commerial center | 95802 |  |  |  |  | Commerial center
9 | IESCO | City |  | F/Block |  | 4th road | 95804 |  |  |  |  | 4th road