## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
2 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | R.E New Wah | 132KV New Wah (WAH-6) - POF East, North along with related earth switch |  |  | 01-02-2026 To 31-03-2026 (Contineous) | 01-02-2026 09:00 Hrs | 31-03-2026 16:00 Hrs | For saftety puprose for errection & stringing work between Loc No. 01 to 17 of WAH-6 portion for remodelling work of 132KV T/Line POF East, West & North. | No area will affected as POF East, West and North will mbe fed from 132KV GSS New Wah (WAH-5)
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Divisoin No-I Islamabad | 132KV Kahuta City (KHC-2) - Palandri (PLD-3) along with related earth Switch. |  |  | 15-02-2026 To 16-04-2026 (Contineous) |  | 15-02-2026 18:00 Hrs | 16-04-2026 18:00 Hrs | For Erection/stringing purpose | No area will be affected as 132KV GSS Kahuta City along with Chaint will be fed from 132KV GSS KRL Kahuta side & Palandri, Tararkhal & Hajeera will be fed from Kotli side. However, 30 to 40 MW load management may be required to ovaid over loading or any contingency.
1 | IESCO | GSO CIRCLE IESCO ISD | SS&TL DIVISIONIESCO RAJJAR | A.E (T) Chakwal | 132KV Chakwal (CWL-7) - Bhagwal (NLA-1) - Talagang (TLG-1) |  |  | 15-02-2026 to 16-04-2026 (Contineous) |  | 15-02-2026 18:00 Hrs | 16-04-2026 18:00 Hrs | Remodeling/Stringing of Chakwal - Talagang circuit from Loc No. 01 to 33 | 132KV GSS Bhagwal will be affected from 09:00 Hrs to 15:00 Hrs. after that No area will be affected as 132KV Chakwal already feeding from 500KV Rawat, Bhagwal will be fed from Talagang side & Talagang will be fed from Tamman side.
18 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | Kurri | 105506 | 26-02-2025 30-03-2025 | 07:00 | 12:00 | Federal Urdu University at Kurri Road Zone-IV Near Bahria Enclave Islamabad | Kuri Sher.
19 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | Rehara | 105511 |  | 07:00 | 12:00 |  | Mohra Noor, Rehara
20 | IESCO | IBD | B/Kahu | B/K (U) | 132 KV Tramri GS | CM Pak Zong | 105509 |  | 07:00 | 12:00 |  | Office of CM PAK
21 | IESCO | IBD | B/Kahu | B/K (U) | University | N.I.H | 89210 | 23-02-2026 25-02-2026 02-03-2026 04-03-2026 09-03-2026 11-03-2026 16-03-2026 31-03-2026 | 07:00 | 12:00 | Stringing of HT line/ Installation of HT Structure 58' Beneath the existing HT lines in IRO Bifurcation of 11KV Shah Pur Feeder /Strinning of HT line in R/O External Electrification of Park View City Housing Society | Malpur, Lake view, Banigala, NIH, Dk. Jillani, LVL, Dk. Mohri.
22 | IESCO | IBD | B/Kahu | B/K (U) | University | T&T | 89204 |  | 07:00 | 12:00 |  | Mangoo Town, 17 Meel, Abdullah Town.
23 | IESCO | IBD | B/Khu | B/K (U) | 132/220 KV G/S B/Khu | B/ Khu-I | 89201 |  | 07:00 | 12:00 |  | Bhara Kahu Bazar, Sanjalian and Surrounding Area
24 | IESCO | IBD | B/Khu | B/K (U) | 132/220 KV G/S B/Khu | B/ Khu-II | 89219 |  | 07:00 | 12:00 |  | Madina Town, Nain Sukh,and Surrounding Area
25 | IESCO | IBD | B/Khu | B/Khu (R) | 132/220 KV G/S B/Khu | Tret | 89203 |  | 07:00 | 12:00 |  | Nai Abadi,Country Form
26 | IESCO | IBD | B/Khu | B/K (R) | 132/220 KV G/S B/Khu | Golf city | 89216 |  | 07:00 | 12:00 |  | Golf City
27 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Park View | 122511 |  | 07:00 | 12:00 |  | Park View city
28 | IESCO | IBD | Div-1 | Nilore | 132/220kv G/S B/Khu | Athal | 89217 |  | 07:00 | 12:00 |  | Simly dam road , Athal Road, Tumair, Athal.
3 | IESCO | City | Westridge | Kamalabad | Kamalabad | Kamalabad | 001025 |  | 8:00 | 11:00 |  | Kamalabad
2 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Margalla | 132 KV T/L New Wah (WAH-15) - Bahter More (BMW-2) Along with related earth switches. |  |  | 25-02-2026 To 25-03-2026 (Contineous) | 25-02-2026 09:00 h | 25-03-2026 14:00 h | During this period, the portion of line will be isolated/ de-energized as working portion for erection & stringing from 132 KV GSS Bahter More to 132 KV GSS New Wah. | No area will be affected, however132 KV GSS Fauji Cement Plant (Consumer Grid) will be fed from 132 KV GSS Fateh Jang and 132 KV GSS Bahtarmore will be fed from 132 KV GSS Fateh Jang side & 132 KV GSS New Wah will be fed from 220 KV GSS Burhan side.
1 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | C.W.O. | 058204 | 03.03.2026 10.03.2026 17.03.2026 26.03.2026 31.03.2026 | 0700 | 1200 | Shifting of HT/LT Line due to dulization of Lillah - Jhelum Road | Army Area - Civil Work Organization.
2 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Abdullah Pur | 058206 |  | 0700 | 1200 |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
3 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Jalal Pur | 058203 |  | 0700 | 1200 |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
4 | IESCO | Chakwal | P.D Khan | Pinanwal | Pinanwal | Sagharpur | 058202 |  | 0700 | 1200 |  | Chak Mujahid Shumali, Karyala, Chak Shadi, Pinanwal,
6 | IESCO | Chakwal | P.D Khan | P.D Khan | Dandot | Duffer | 29001 | 17.03.2026 26.03.2026 | 0700 | 1200 |  | P.D Khan. Katchery etc
7 | IESCO | Chakwal | P.D.Khan | P.D.Khan | Dandot | P.D.KHAN | 029005 |  | 0700 | 1200 |  | Dhoke Gola Area, Dera Rajjgan, Dhok Malinka, Dhok Vance, Islam Naghar, Kot Kallan, Juggiana, Hussain Abad, Jhelum Road, Dhoke Saghar.
5 | IESCO | IBD | B/Kahu | B/Kahu (U) | 132/220KV B/Kahu | Shahpur | 89218 | 04.03.2026 11.03.2026 16.03.2026 31.03.2026 | 07:00 | 12:00 | Stringing of HT line/ Installation of HT Structure 58' Beneath the existing HT lines in IRO Bifurcation of 11KV Shah Pur Feeder. | Shahpur
5 | IESCO | City | S/Town | Sadiq Abad | 132 KV S/Town | C/Block | 095831 | 24-03-2026 30-03-2026 | 09:00 Hrs | 12:00 Hrs | Shifting of Underground 11-KV National Market Feeder to Overhead near 6th Road Rwp | C-Block, Dk Khillo, Kurri Road & Surrounding Area.
6 | IESCO | City | S/Town | Sadiq Abad | 132 KV S/Town | Sadiqabad | 095815 |  |  |  |  | Dk.Babu Irfan,S/Abad,M.Town,Afandi Colony,
7 | IESCO | City | S/Town | Chandni Chowk | 132 KV I-8 | A-Block | 061104 |  |  |  |  | A.Block,Dk.Paracha,C-Block,Murree Road and surrounding area
8 | IESCO | City | S/Town | Sadiqabad | 132-KV S/Town | Affandi Colony | 095808 |  |  |  |  | S/Abad,M.Town,Afandi Colony,And Surrounding Area.
9 | IESCO | City | S/Town | Chandni Chowk | 132-KV S/Town | National Market | 095822 |  |  |  |  | National Market, Asghar A/Mall Scheme and surounding area.
10 | IESCO | City | City | ASGHAR MALL | 132-KV S/Town | ASGHAR MALL | 95805 |  |  |  |  | Agshar Mall & Surrounding Area
11 | IESCO | City | S/Town | Gangal | 132 KV I-8 | Jinnah Camp | 061117 | 26-03-2026 | 09:00 Hrs | 12:00 Hrs | For reconductoring of LT Line IRO LV work Opposite Faiz-ul-Islam Faizabad Rep (2K26-431-06-22) | Jinnah Camp complex
12 | IESCO | City | S/Town | Gangal | 132 KV I-8 | KRL | 061113 |  |  |  |  | KRL complex
13 | IESCO | City | S/Town | Dk.Kala Khan | 132 KV I-8 | Service Road | 061101 |  |  |  |  | Service Road, Dhoke Chaudhrian, Dhoke Anwar and Surrounding Area
14 | IESCO | City | S/Town | Dk.Kala Khan | 132 KV I-8 | Qayyum Abad | 061116 |  |  |  |  | Qayyum Abad & Surrounding Area
6 | IESCO | City | Westridge | Tarnol | 132 KV Tarnol | Nogazi | 104901 | 05.03.2026 10.03.2026 15.03.2026 31.06.2026 | 07:00 Hrs | 10:00 Hrs | Reconducting of HT line of Top City Feeder | Nogazi, Dk. Miskeen, Main Fateh Jhang road & Surrounding areas
7 | [5 empty] | Shalimar City | 104912 |  |  |  |  | Shalimar town & Surrounding areas
8 | [5 empty] | Top City | 104905 |  |  |  |  | Top City & Surrounding areas
9 | [5 empty] | Bajniyal-II | 104911 | 25.03.2026 | 09:00 Hrs | 12:00 Hrs | Stringing work IRO Safety Hazard work village barkat | Bajnial & Surrounding areas
1 | IESCO | Attock | Attock | Attock Cantt | 132KV Sanjwal | Attock Cantt | 18901 | 05.03.2026 10.03.2026 24.03.2026 29.03.2026 | 07:00 | 12:00 | Striging & Errection of Pole IRO 11KV independent Feeder MCH Attock | Attock Cantt & Surrounding Area
2 | IESCO | Attock | Attock |  |  | Dhoke Fteh | 18911 |  | 07:00 | 12:00 |  | Dhoke Fateh & Surrounding Area
3 | IESCO | Attock | Attock |  |  | Dar ul Islam Colony | 18909 |  | 07:00 | 12:00 |  | Dar ul Islam Colony & Surrounding Area
4 | IESCO | Attock | Attock |  |  | Katchery | 18902 |  | 07:00 | 12:00 |  | Katchery & Surrounding Area
9 | IESCO | Attock | Attock | Attock City | 132KV Attock | Fawara Chowk | 75103 | 04.03.2026 09.03.2026 16.03.2026 18.03.2026 | 07:00 | 12:00 | Replacement of Old Wire & Pole Under Beautification of Attock | A.B.C.R Block, City area, Lorry area & surrounding area
10 | [7 empty] | 30.03.2026 | 09:00 | 14:00
2 | IESCO | Cantt | T/Abad | Dhamial | 132KV Ranyal | Hayal | 120404 | 16.03.2026 25.03.2026 | 9:00 | 12:00 | For completion of LV work Misriot Road & Dk Maira | Ranyal & sorrounding area
3 | IESCO | City | Westridge | Tarnol | Tarnol | Nogazi | 104901 | 24.03.2026 | 07:00 Hrs | 10:00 Hrs | Installation of 25KVA T/F IRO Mr. Mazhar Mehmood S/o Muhammad Mehmood | Nogazi & Fateh Jhang road & Surrounding areas
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Cantt | Askari-7 | 017919 | 08.03.2026 15.03.2026 29.03.2026 | 7:00 | 12:00 | For GPO Chowk underpass Signal Free Mall Road Project (Part A) Rawalpindi | Askari-7 & sorrounding area
2 | [5 empty] | Sir Syed Road | 017913 |  |  |  |  | Sir Syed Road & sorrounding area
3 | [5 empty] | CMH Flats | 017936 |  |  |  |  | Sir Syed Road & sorrounding area
4 |  |  | Cantt | Civil Line |  | FFC | 017927 |  |  |  |  | FFC & sorrounding area
5 | [5 empty] | Khadim Hussain Road | 017727 |  |  |  |  | Khadim Hussain Road & sorrounding area
6 | [5 empty] | Adam Jee Road | 017932 |  |  |  |  | Adam Jee Road & sorrounding area
7 |  |  | Tariqabad | R.A Bazar |  | GHQ Express | 17924 |  |  |  |  | GHQ & sorrounding area | Subject to provision of NOC from GHQ.
8 | IESCO | City | S/Town | Sadiqabad | 132KV Chaklala | Benazir Bhutto Hospital | 2531 | 11.03.2026 18.03.2026 28.03.2026 31.03.2026 | 07:00 | 12:00 | For erection of poles RIC Feeder | Benazir Bhutto Hospital
9 | IESCO | City | City | Zafar-ul-Haq | 132KV Chaklala | Tehmasamabad | 2518 |  |  |  |  | Tehmasamabad
10 | IESCO | City | City | Zafar-ul-Haq | 132KV Chaklala | Dk.Hukam Dad | 2527 |  |  |  |  | Dk.Hukam Dad
11 | IESCO | Cantt | Cantt | Chaklala | 132KV Chaklala | RIC | 2534 |  |  |  |  | RIC and Surrounding area. | Subject to the provision of NOC from Management of Rawalpindi Institute of Cardiology
12 | [5 empty] | Rahimabad | 002541 |  |  |  |  | Rahimabad & sorrounding area
13 | IESCO | Cantt | Mandra | Wadala | 132KV Old Rawat | New Kalyam | 17721 | 10.03.2026 17.03.2026 24.03.2026 29.03.2026 | 07:00 | 12:00 | For Area Planning of 11KV Jatha Hathial & 11KV Pind Jhatla Feeder | Shah Khai awan & Sorrounding Area
14 | [5 empty] | Pind Jhatla | 017727 |  |  |  |  | Suparco & sorrounding area
15 |  |  |  |  | 500KV New Rawat | Jatha Hathial | 064503 |  |  |  |  | Jatha Hathial & sorrounding area
16 | [5 empty] | Industrial | 064502 |  |  |  |  | Industrial & sorrounding area
17 | [5 empty] | Bhall | 064507 |  |  |  |  | Bhall & sorrounding area
18 |  |  | Tariqabad | Adyala |  | Jarrar Camp | 064510 |  |  |  |  | Jarrar Camp & sorrounding area
9 | IESCO | Jhelum | Jhelum-II | Sanghoi | Sanghoi | New Sanghoi | 126302 | 09.03.26 14.03.26 18.03.26 25.03.26 | 0700 Hrs | 1100 Hrs | Stringing of 11KV Sanghoi feeder | Sanghoi etc
10 | IESCO | Jhelum | Jhelum-II | Sanghoi | Sanghoi | Chotala | 126303 |  | 0700 Hrs | 1100 Hrs |  | Chotala etc
11 | IESCO | Jhelum | Jhelum-II | Sanghoi | Sanghoi | Khai Kulia | 126301 | 14.03.26 18.03.26 25.03.26 | 0700 Hrs | 1100 Hrs |  | Khai Kulia etc
1 | IESCO | Attock | Taxila | Sang Jani | 132 KV GSS B-17 | Saray Kharbooza | 121802 | 11.03.2026 12.03.2026 13.03.2026 28.03.2028 | 09:00 Hours | 11:00 Hours | For shifting of HT/LT line NHA | Sarai Kharbooza
2 |  |  |  |  | 220 KV Sang Jani | Shah Allah Ditta | 081011 |  |  |  |  | Shah allah Ditta
3 |  |  |  |  | 132 KV Cabinet Division | Milat Colony | 133602 |  |  |  |  | Tarnol
1 | IESCO | GSO Circle IESCO Isld | SS&TL Division IESCO Isd | A.E (T) No-II | 20/26MVA Power Transformer T-2 At 132KV GSS Kallar Syedan |  |  | 12-03-2026 To 18-03-2026 (Contineous) | 12-03-2026 08:00 Hrs | 18-03-2026 24:00 Hrs | For augmentation of 20/26MVA Power Transformer T-2 with 40MVA Power Transformer | No area will be affected as load of Power Transformer T-2 will be shifted to Power Transformer T-1 through Bus Coupler.
1 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | APF | 96808 | 12.03.2026 19.03.2026 | 07:00 | 10:00 | For Jumpering of HT Line IRO Qurtaba City Chakri Rawalpindi | APF & surrounding area
2 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | SPD | 96806 |  | 07:00 | 10:00 |  | SPD & surrounding area
3 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Paryal | 96809 |  | 07:00 | 10:00 |  | Paryal & surrounding area
4 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Chakri | 96801 |  | 07:00 | 10:00 |  | Chakri & surrounding area
5 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | HASCOL | 96812 |  | 07:00 | 10:00 |  | Hascol & surrounding area
6 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Chahan | 096802 |  | 07:00 | 10:00 |  | Chahan & surrounding area
7 | IESCO | Cantt | Tariqabad | Chakri | 132KV Chakri | Rajjar | 96803 |  | 07:00 | 10:00 |  | Rajjar & surrounding area
9 | IESCO | Cantt | Tariqabad | Adiala | 132KV Adiala | Kalyal | 109101 | 16.03.2026 18.03.2026 | 07:00 | 10:00 |  | Kalyal & Surrounding areas
1 | IESCO | City | Westridge | Misrial | 132 KV Pirwadhai | Askari XI | 043325 | 16.03.2026 30.03.2026 04.04.2026 | 10:00 Hrs | 01:00 Hrs | D/W Army Graveyard | Askari-XI Lane 01 to 07 St. 01 to 14 & Surrounding areas
2 |  |  |  | Westridge | 132 KV KTM | NRC | 008622 |  |  |  |  | Westridge Bazar, Hali Road, Iqbal Road, Churr Chowk, Race Course Ground & Surrounding areas
1 | IESCO | Cantt | Cantt | Jhanda | 132KV Chaklala | CNC | 002524 | 17.03.2026 18.03.2026 19.03.2026 | 7:00 | 12:00 | For shifting of HT/LT line infront of Jinnah Park Rawalpindi | Army House & sorrounding area | NOC Obtained from Army House & Verbal NOC from Honorable Senior Civcil judge Rawalpindi.
2 |  |  |  | Tariqabad |  | Humayun Road | 002525 |  |  |  |  | Army House, Golf Club, Judges Colony & sorrounding area
3 |  |  | Tariqabad | Adyala |  | 502 Work Shop | 002540 |  |  |  |  | 502 Workshop & sorrounding area
1 | IESCO | Attock | Pindi Gheb | Fateh Jang R | 132 KV Fateh Jnag | Fateh Jang R | 27201 | 17.03.2026 18.03.2026 | 09:00am | 12:00pm | shifting of HT line iro NESCOM Khour Road Fateh Jang | Atomic Energy, Fateh Jang Hastal, Tajabara, kot Fateh Khan, Fateh Jang City & Surrounding Area
2 |  |  |  | Fateh Jang U |  | Laniwala | 27210
3 |  |  |  | Fateh Jang U |  | Nescom | 27218
1 | IESCO | City | City | Gangmandi | 132KV Pirwadhai | Major Masood | 43323 | 18.03.2026 | 07:00 Hrs | 10:00 Hrs | Execution of Safety Hazards near K.K Nimko Gangmadi Road. | Gangmandi & Surrounding areas
1 | IESCO | City | Westridge | Tarnol | 132KV KTM | CWO | 8601 | 18.03.2026 | 07:00 Hrs | 10:00 Hrs | for Installation of 500MCM Cable & re-energization of HT TOU Meter on 11KV CWO feeder | CWO & Surrounding areas
2 | IESCO | City | Westridge | Tarnol | 132KV KTM | Golra | 8605 |  |  |  |  | Golra & Surrounding areas
3 | IESCO | City | Westridge | Tarnol | 132KV KTM | Shamas Colony | 8626 |  |  |  |  | Shamas Colony & Surrounding areas
4 | IESCO | City | Westridge | Tarnol | 132KV KTM | QIH | 8624 |  |  |  |  | QIH
5 | IESCO | City | Westridge | Tarnol | 132KV KTM | P&T Wani | 8610 |  |  |  |  | P&T Wani & Surrounding areas
1 | IESCO | IBD | NO.I | Khanna Dk | Tramari | Khanna DK | 105501 | 26-03-2026 30-03-2026 06-04-2026 | 09:00 | 14:00 | Area Planning of 11KV UC Road Feeder and 11KV Koral Feeder | Khanna DK & Surrounding area.
2 | IESCO | IBD | NO.I | Rawal | Tramari | Burma | 105502 |  |  |  |  | Burma & Surrounding area.
3 | IESCO | IBD | NO.I | Tarlai | Tramari | Ghouri Garden | 105513 |  |  |  |  | Ghouri Garden & Surrounding area.
4 | IESCO | IBD | NO.I | Tarlai | Tramari | Shareefabad | 105521 |  |  |  |  | Shareefabad & Surrounding area.
5 | IESCO | IBD | NO.I | Tarlai | Tramari | Sudhran Road | 105504 |  |  |  |  | Sudhran Road & Surrounding area.
6 | IESCO | IBD | NO.I | Tarlai | Tramari | Scheme-I | 105525 |  |  |  |  | Scheme-I & Surrounding area.
7 | IESCO | IBD | NO.I | Khanna Dk | Tramari | Khanna DK | 105501 | 13-04-2026 20-04-2026 27-04-2026 |  |  |  | Khanna DK & Surrounding area.
8 | IESCO | IBD | NO.I | Rawal | Tramari | Burma | 105502 |  |  |  |  | Burma & Surrounding area.
9 | IESCO | IBD | NO.I | Rawal | Tramari | Waheedabad | 105516 |  |  |  |  | Waheedabad & Surrounding area.
10 | IESCO | IBD | NO.I | Khanna Dk | Tramari | Rehman Enlave | Not allocated |  |  |  |  | Rehman Enlave & Surrounding area.
11 | IESCO | IBD | NO.I | Khanna Dk | Tramari | Khanna East | 105510 |  |  |  |  | Khanna East & Surrounding area.
12 | IESCO | RWP | Satellite Town | Gangal | Tramari | Khanna-II | 105514 |  |  |  |  | Khanna-II & Surrounding area.
13 | IESCO | RWP | Satellite Town | Gangal | Tramari | Al Noor Colony | 105515 |  |  |  |  | Al Noor Colony & Surrounding area.
14 | IESCO | IBD | NO.I | Tarlai | Tramari | Shareefabad | 105521 |  |  |  |  | Shareefabad & Surrounding area.
15 | IESCO | IBD | NO.I | Tarlai | Tramari | Ghouri Garden | 105513 |  |  |  |  | Ghouri Garden & Surrounding area.
16 | IESCO | IBD | NO.I | Tarlai | Tramari | Scheme-I | 105525 |  |  |  |  | Scheme-I & Surrounding area.