## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date |  | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
25 | IESCO | GSO | SS& TL Division IESCO Rwp | AET Margalla | 132 KV New Wah-(Wah-15) Bhatarmore (BMW-2 along with related earth Switch |  |  | 02.10.2026 to 30.11.2026 |  | 14:00 | 14:00 | Extention of already in progress shutdown for erection & stringing activities (during theis period, the portion of line New Wah-Bhatarmore will be Isolated/De-Energized as workingportion) | No area will be effected as 132 KV GSS Bhatarmore will be fed from 132 KV GSS Fateh Jhang side & 132 KV GSS New Wah will be fed from 220KV GSS Burhan side.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Division Rawalakot | 132 KV Bagh (BAG-2) - Hattian (HTN-2) T/Line. |  |  | 15-10-2026 To 30-11-2026 (Continious) |  | 15-10-2026 08:00 Hrs | 30-11-2026 16:00 Hrs | For saftety puprose during reconductring of existing circuit from Lynx to Greely & stringing of 2nd circuit with Greely conductor of 132KV T/Line Bagh to Hattian. | No area will be affected as 132KV GSS Hattian is already been fed from HAZECO siide and 132kV GSS Bagh will be fed from Rawalakot through Trarkhel side. However, up to 40 MW load management will be carried out if required by (ISMO). | The Project Director (GSC), vide letter No. 0001-04 dated 07.10.2026, has intimated that the 132 kV Transmission Lines Kahuta–Plandri (Lot-I & Lot-II) were completed and energized on 12.09.2026.
1 | IESCO | GSO Circle | SS&TL ISD | AE(T) No.II | 132Kv Murree (MRE-2) - Chattar Kalas (CTK-1) Transmission Line | 132KV GSS Minhasa |  | 19.10.2026, 22.10.2026, 25.10.2026, 28.10.2026 31.10.2026, 03.11.2026, 07.11.2026 |  | 07:00 Hrs | 17:00 Hrs | For erection of ZM-60 Tower at Loc No.09 A & Stringing from Loc No. 10 & 12 & dismantling at Loc No. 11
[6 empty] | Dheer Kot | 79401 | [5 empty] | Dheer Kot
[6 empty] | chaman kot | 79402 | [5 empty] | chaman kot
[6 empty] | Dana Express | 79409 | [5 empty] | Dana Express
[6 empty] | DAHLA | 79411 | [5 empty] | DAHLA
[6 empty] | Gujarkohala | 79412 | [5 empty] | Gujarkohala
[6 empty] | Minhasa Sohawa | 79406 | [5 empty] | Minhasa Sohawa
[6 empty] | Numble | 79405 | [5 empty] | Numble
[6 empty] | Birote | 79408 | [5 empty] | Birote
[6 empty] | Rangla | 79407 | [5 empty] | Rangla
[6 empty] | Ghaziabad | 79410 | [5 empty] | Ghaziabad
132KV GSS Chattr Kalas
[6 empty] | Komi Kot | 13603 | [5 empty] | Komi Kot
[6 empty] | chattar kallas-1 | 132601 | [5 empty] | chattar kallas-1
[6 empty] | Chattar Kallas-II | 132602 | [5 empty] | Chattar Kallas-II
1 | IESCO | Attock | Taxila | Mohra Chowk | New Wah | Lalazar | 14607 | 24.10.2026 26.10.2026 | 22.10.2026 29.10.2026 31.10.2026 | 07:00 Hrs | 14:00 Hrs | For safety purpose during stringing of conductor for remodeling work from locatio No.23 to 27 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Lalazar
2 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Hussainabad | 14627 |  | 20.10.2026 |  |  |  | Hussainabad
3 | IESCO | Attock | Taxila | Mohra Chowk | New Wah | Lalazar | 14607 | 24.10.2026 26.10.2026 29.10.2026 01.11.2026 | 22-10-2026 29-10-2026 31-10-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No.2 to 12 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Lalazar
4 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Garhi Afghana | 14626 |  | 22-10-2026 29-10-2026 |  |  |  | Garhi Afghana
5 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Industrial Estate Bahtar | 14625 |  | 24-10-2026 |  |  |  | Industrial Estate Bahtar
6 | IESCO | Attock | Taxila | Mohra Chowk | New Wah | Pour Miana | 14608 |  | 21-10-2026 27-10-2026 |  |  |  | Pour Miana
7 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Lala Rukh | 14622 |  | 24-10-2026 |  |  |  | Lala Rukh
8 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Khanabad | 14619 |  | 24-10-2026 28-10-2026 03-11-2026 09-11-2026 16-11-2026 |  |  |  | Khanabad
9 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Col. Sher Khan | 14621 | 24.10.2026 26.10.2026 29.10.2026 01.11.2026 | 29-10-2026 05-11-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 31 to 40 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Col. Sher Khan
10 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Col. Sher Khan | 14621 | 01.11.2026 04.11.2026 07.11.2026 10.11.2026 | 29-10-2026 05-11-2026 |  |  |  | Col. Sher Khan
11 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Khanabad | 14619 |  | 24-10-2026 28-10-2026 03-11-2026 09-11-2026 16-11-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 40 to 43 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Khanabad
12 | IESCO | Attock | Taxila | Wah Cantt | Bahtar More | Kashif Gul | 112002 | 04.11.2026 07.11.2026 10.11.2026 13.11.2026 | 05-11-2026 14-11-2026 18-11-2026 | 07:00 Hrs | 14:00 Hrs | For safety purpose during stringing of conductor for remodeling work from locatio No. 40 to 43 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Kashif Gul
13 | IESCO | Attock | Taxila | Wah Cantt | Bahtar More | Bahatar More | 112020 |  | 07-11-2026 17-11-2026 |  |  |  | Bahatar More
14 | IESCO | Attock | Taxila | Wah Cantt | Bahtar More | I-Block | 112010 | 21.11.2026 24.11.2026 | 22-10-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 63 to 64 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | I-Block
15 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Ahmed Nagar | 14632 | 24.10.2026 26.10.2026 29.10.2026 | 20-10-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 27 to 31 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Ahmed Nagar
16 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Col. Sher Khan | 14621 |  | 29-10-2026 05-11-2026 |  |  |  | Col. Sher Khan
1 | IESCO | Cantt | Tariqabad | R.A Bazar | 132KV GSS MES | New GHQ | 107605 | 24.10.2026 25.10.2026 31.10.2026 01.11.2026 07.11.2026 08.11.2026 14.11.2026 15.11.2026 21.11.2026 22.11.2026 28.11.2026 29.11.2026 |  | 09:00 | 17:00 | for Standby Duplicate Source trough 02x11 independent feeder IRO GHQ | New GHQ
1 | IESCO | NGC Rawat | Senior Manager Rawat |  | 750MVA. 500/220KV ATB-4 at 500KV GSS NGC Rawat |  |  | 23.10.2026 to 07.11.2026 (Continuous) |  | 23.10.2026 '0800 hrs | 07.11.2026 '1600 hrs | Installation of Tertiary Busbar of 750MVA, 500/220KV ATB-4 | No area will be affected | 150MW Load Management under N-2 Contigency Conditions across designed IESCO Distribution network.
1 | IESCO | City | Westridge | Westridge | 132 KV KTM | Millatabad | 008616 | 04.11.2026 | 26.10.2026 31.10.2026 05.11.2026 14.11.2026 | 09:00 | 14:00 | for Emergency Work Peshawer Road Underpass Project | Misrial Road, Ilyas Colony, Lane 1,2,3 and surrounding area | The AM shut down shall be carried out dated 04.11.2026 Instead of 05.11.2026
2 | IESCO | City | Westridge |  |  | Dk. Chaudrian | 008621 | 26.10.2026 31.10.2026 | 28.10.2026 04.11.2026 11.11.2026 18.11.2026 22.11.2026 |  |  |  | Gulnar Colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding area | The AM shut down shall be carried out dated 05.11.2026 Instead of 04.11.2026
3 | IESCO | City | Westridge |  |  | Peshawer Road | 008612 | 26.10.2026 04.11.2026 | 31.10.2026 07.11.2026 14.11.2026 |  |  |  | Peshawer Road, Mehboob Lane, Lane No. 04 to 07 Mehboob Lane, Fazeelabad and surroundig area
1 | IESCO | Cantt | Tariqabad | Tariq Abad | 132 KV Adyala | Humayun-1 | 109111 | 26.10.2026 31.10.2026 | - | 09:00 | 14:00 | For installation of 200 KVA TF IRO Janjua Town Lane No.05 LV Work | Dk. Parian, Adyala Jail, Shahpur, Gorakhpur, Sammar Zar Cly, Shah pur Syedan.
2 | [5 empty] | Askari-14 | 109112 |  | - |  |  |  | Kalyal Adyala Road, Khaja Corportion, Jarahi, Janjua Town, Natinal Housing Society
3 |  |  |  | Adyala |  | Defence Road | 109113 |  | 21.10.2026 31.10.2026 |  |  |  | Adyala Road Khawaja Corporation, Mubarak Lane, Ali Town, Chungi No.20, Dhoke Noor etc.
4 |  |  |  | Dhamial | 132 KV Ranyal | Hayal | 120407 | 31.10.2026 | 28.10.2026 |  |  | For Removal of Safety Hazard IRO Hala Mohallah | Hayal & sorrounding area
5 | [5 empty] | Gulistan e Fatima | 120406 |  | 27.10.2026 |  |  |  | Gulistan-e-Fatima & sorrounding area
6 | IESCO | Cantt | T/Abad | Dhaimial | 132KV Ranyal | Moorat | 120405 | 24.10.2026 02.11.2026 14.11.2026 17.11.2026 21.11.2026 | 24.10.2026 29.10.2026 02.11.2026 10.11.2026 14.11.2026 17.11.2026 21.11.2026 28.11.2026 |  |  | For stringing of HT Line iro Capital Smart City | Moorat & Surrounding areas
7 |  |  |  |  | 132KV Chakri | Kohala | 120404 |  | 31.10.2026 11.11.2026 21.11.2026 |  |  |  | Khasala & Surrounding areas
8 | [5 empty] | Fatima Jinnah | 120408 |  | - |  |  |  | FJWU & Surrounding areas
9 |  |  |  | Adyala | 132KV Chaklala | Humayun Road | 002525 | 24.10.2026 31.10.2026 03.11.2026 10.11.2026 16.11.2026 19.11.2026 23.11.2026 | - |  |  | For Shifting of HT lines from overhead to underground Tulsa Chowk to Nazar Chowk COD Rawalpindi | Dk Noor & sorrounding area
10 | [5 empty] | New 502 Work Shop | 002540 |  | 08.11.2026 21.11.2026 |  |  |  | New Lalazar, 502 Workshop
11 |  |  |  | Tariqabad | 132 KV Cantt | Askari-7 | 017919 |  | 24.10.2026 31.10.2026 03.11.2026 07.11.2026 28.11.2026 |  |  |  | Askari-7 & sorrounding area
12 |  |  |  | Adyala | 132 KV Adyala | Rose Lane | 109105 |  | 31.10.2026 03.11.2026 07.11.2026 11.11.2026 23.11.2026 |  |  |  | Moorat & Surrounding areas
1 | IESCO | RWP CITY | Satellite Town | Gangal | 132 KV GSS I-8 | KRL | 61113 | 07.11.2026 | 27.10.2026 03.11.2026 08.11.2026 | 07:00 | 14:00 | for safety Purpose during stringing of conductor between location No. 13 to15 & 46 to 57 for new 132KV T/Line feed for shakrial. | KRL Complex | The A.M Shut down on 11KV KRL Feeder is hereby Cancelled & Awail the Shut down as approved dated 07.11.2026
1 | IESCO | Islamabad | Division II | G-11 | F-11 | G-11/1 | 69205 | 27-10-2026 05-11-2026 12-11-2026 | 27.10.2026 05.11.2026 12.11.2026 21.11.2026 | 09:00 | 14:00 | Removal of HT fault F-10/4 feeder Near Service Road West Sec | G-11/1 St 59
2 | IESCO | Islamabad | Division II | G-11 | F-11 | G-11/2 | 69206 |  | 27.10.2026 05.11.2026 12.11.2026 23.11.2026 |  |  |  | G-11/2
3 | IESCO | Islamabad | Division II | G-11 | F-11 | G-11/3 | 69213 |  | 27.10.2026 05.11.2026 12.11.2026 24.11.2026 |  |  |  | G-11/3
4 | IESCO | Islamabad | Division II | G-11 | F-11 | G-11/4 | 69214 |  | 27.10.2026 02.11.2026 05.11.2026 12.11.2026 |  |  |  | G-11/4
5 | IESCO | Islamabad | Division II | G-11 | F-11 | G-11/M | 69222 |  | 27.10.2026 12.11.2026 26.11.2026 |  |  |  | G-11/M
6 | IESCO | Islamabad | Division II | G-11 | F-11 | PHA | 69225 |  | 27.10.2026 31.10.2026 05.11.2026 12.11.2026 25.11.2026 |  |  |  | PHA
7 | IESCO | Islamabad | Division II | G-11 | F-11 | Warda Hamna | 69231 |  | 27.10.2026 05.11.2026 12.11.2026 |  |  |  | Warda Hamna
8 | IESCO | Islamabad | Division II | F-11 | F-11 | F-11/1 | 69202 |  | 27.10.2026 05.11.2026 12.11.2026 |  |  |  | F-11 and some surrounding area
9 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | Faisal Masjid | 22310 | 28-10-2026 03-11-2026 17-11-2026 21-11-2026 25-11-2026 30-11-2026 05-12-2026 14-12-2026 | 27.10.2026 16.11.2026 24.12.2026 |  |  | For Replacement of HT Cable 500 MCM S/C of 11 kV HC-I & 11 kV HC-II Feeder of PIMS Hospital from Zeropoint to Jamia Masjid Rasheed G-8/M | F-8/4 & Surrounding | Load shifted on F-8/1 feeder
10 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | Ayub Market | 22318 |  | 27.10.2026 14.11.2026 23.12.2026 |  |  |  | F-8/4 & Surrounding | Load shifted on F-8 Markaz feeder
11 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | HC-I | 22322 |  | 05.12.2026 |  |  |  | PIMS Hospital G-8/3 | On Fault
12 | IESCO | Islamabad | Division No.II | F-8 | Zero Point | HC-II | 22309 |  | 03.01.2027 |  |  |  | PIMS Hospital G-8/3 | Load shifted on HC-III feeder
13 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | Suparco Chowk | 22330 |  | 03.11.2026 30.11.2026 05.12.2026 08.12.2026 |  |  |  | Suparco Chowk & Surrounding Area | Load shifted on G-8/2 feeder
14 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | T&T C-8 (T&T Colony) | 22319 |  | 22.10.2026 11.11.2026 05.12.2026 10.12.2026 31.12.2026 | 09:00 | 14:00 | For Replacement of HT Cable 500 MCM S/C of 11 kV HC-I & 11 kV HC-II Feeder of PIMS Hospital from Zeropoint to Jamia Masjid Rasheed G-8/M | G-8/1,G-8/4 & Surrounding | Load shifted on G-8/4 feeder
15 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | PTCL | 22331 |  | 25.11.2026 05.12.2026 |  |  |  | PTCL Headqurter | Subject to the Condition of Loading Position
16 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | G-8/1 | 22324 |  | 04.11.2026 12.11.2026 03.12.2026 24.12.2026 |  |  |  | G-8/1 & Surrounding | Load shifted on G-8/2 feeder
17 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | G-8 | 22326 |  | 26.10.2026 17.11.2026 14.12.2026 |  |  |  | G-8 & Surrounding | Load shifted on PHA feeder
18 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | G-8 Markaz | 22338 |  | 31.10.2026 10.11.2026 21.12.2026 |  |  |  | G-8 Markaz & Surrounding | Load shifted on G-8/4 feeder
19 | IESCO | Islamabad | Division No.I | G-7 | Zero Point | Marvi | 22317 |  | 28.10.2026 14.11.2026 15.12.2026 |  |  |  | G-7/2 | Load shifted on PHA feeder
20 | IESCO | Islamabad | Division No.I | G-9 | Zero Point | G-9/4 | 22340 |  | 21.11.2026 05.12.2026 15.12.2026 28.12.2026 |  |  |  | G-9/4 & Surrounding | Load shifted on G-10/1 or T&T Centre feeder
1 | IESCO | IBD | Div-I | G-6 | Rawal | Islamabad Club-1 | 17417 | 05.11.2026 | 04.11.2026 08.11.2026 10.11.2026 15.11.2026 19.11.2026 24.11.2026 | 8:00 | 14:00 | Shifting of 11KV Lines Due to Construction of under pass Kashmir chowk. | Islamabad Club | The Annual Maintenance (A.M.) shutdown scheduled for 04.11.2026 is hereby cancelled. The maintenance work shall instead be carried out on 05.11.2026
2 | IESCO | IBD | Div-I | G-6 | Rawal | Islamabad Club-2 | 17428 |  | 15.11.2026 |  |  |  | Banigala, orchard scheme, club road
3 | IESCO | IBD | Div-I | G-6 | Rawal | Mehfooz Shaheed/Shehzad Town | 17424 |  | 04.11.2026 08.11.2026 12.11.2026 14.11.2026 16.11.2026 21.11.2026 24.11.2026 30.11.2026 |  |  |  | Rawal Town, Schme-4, Sohan Vil, CDA Tubewells (Ameen Faheem) | The Annual Maintenance (A.M.) shutdown scheduled for 04.11.2026 is hereby cancelled. The maintenance work shall instead be carried out on 05.11.2026
4 | IESCO | IBD | Div-I | G-6 | Rawal | Filtration Plant | 17436 |  | 02.11.2026 09.11.2026 15.11.2026 23.11.2026 |  |  |  | Filtration Plant
5 | IESCO | IBD | Div-I | G-6/Rawal | Rawal | Pindorian | 17434 |  | 07.11.2026 17.11.2026 21.11.2026 24.11.2026 |  |  |  | Pindorian and Surrounding area
6 | IESCO | IBD | Div-I | Tarlai | 132 KV Rawal | Scheme-II | 17430 |  | 04.11.2026 08.11.2026 09.11.2026 14.11.2026 19.11.2026 21.11.2026 24.11.2026 26.11.2026 |  |  |  | Scheme - II, Chak shehzad, chatta bakhtawar | The Annual Maintenance (A.M.) shutdown scheduled for 04.11.2026 is hereby cancelled. The maintenance work shall instead be carried out on 05.11.2026
7 | IESCO | IBD | Div-I | G-6 | Rawal | Orchard Scheme | 17439 |  | 02.11.2026 09.11.2026 22.11.2026 26.11.2026 |  |  |  | Margallah Town Phase-1 & Phase-11, Orchad
8 | IESCO | IBD | Div-I | G-6 | Rawal | CDA Pump | 17441 |  | 07.11.2026 15.11.2026 23.11.2026 |  |  |  | CDA Tube Wells NARC
1 | IESCO | Attock | Taxila | Mora Chowk | 132KV New Wah Grid | AWC Houssing | 14624 | 04.11.2026 11.11.2026 | 04.11.2026 11.11.2026 | 09:00 | 14:00 | for safety purpose for erection and stringing work between location No. 07 to 10 for remodeling of 132kv AWC to HMC Taxila portion | Asifabad, Green Town, Basti Chokw
2 | [5 empty] | Munirabad | 14628 |  | 03.11.2026 11.11.2026 |  |  |  | Munirabad
3 | [5 empty] | Rashid Minhas | 14620 |  | 04.11.2026 11.11.2026 |  |  |  | Rashid Minhas
4 | [5 empty] | Shahia | 14629 |  | 04.11.2026 11.11.2026 |  |  |  | Basti, Minar Road