## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Existing Operation Maintenance Date | Proposed Change Date for Operation Maintenance | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Sub Division New Wah | 132KV Faqirabad (FQB-2) - Gondal (GND-2) along with related earth switches. |  |  | 08-09-2025 To 15-10-2025 (Contineous) |  |  | 08-9-2025 08:00 Hrs | 15-10-2025 16:00 Hrs | For safety purpose for dismantling of existing Landative Towers & erection of New ZM Towers for remodeling/ reconductoring with greely of 132KV T/Line Gondal to Faqirabad | No area will be affected as 132KV GSS Faqirabad will be fed from Burhan side & 132KV GSS Gondal will be fed from Jahangira side. Moreover, as per direction of RCC, N-1 (contingency plan) be executed (if required) on connected Grids. also load management will be carried out (if required).
1 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | Shah Pur | 89218 | 23-09-2025 30-09-2025 06.10.2025 |  |  | 08:30 | 13:30 | Installation of HT Structure 58' Beneath the existing HT lines in IRO Bifurcation of 11KV ShahPur Feeder /Stringing of HT line in R/O External Electrification of Park View City Housing Society & Shifting of HT line IRO NHA at satra Meel C/O Safeer Ahmed B/Kahu | Shahpur, Phulgran, Spring Valley
2 | IESCO | IBD | Div-1 | Nilore | 132/220 KV G/S B/Khu | Athal | 89217 |  |  |  | 08:30 | 13:30 |  | Athal Road, Tumair, Athal vill.
3 | IESCO | IBD | B/Khu | B/Khu (R) | 132/220 KV G/S B/Khu | Tret | 89203 |  |  |  | 08:30 | 13:30 |  | Treat and Surrounding Area
4 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | T&T | 89204 |  |  |  | 08:30 | 13:30 |  | Mango Town 17 Meel and Surrounding Area
5 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | B/ Khu-II | 89219 |  |  |  | 08:30 | 13:30 |  | Madina Town, Nain Sukh,and Surrounding Area
6 | IESCO | IBD | B/Khu | B/Khu (U) | 132/220 KV G/S B/Khu | B/ Khu-I | 89201 |  |  |  | 08:30 | 13:30 |  | Bhara Kahu Bazar, Sanjalian and Surrounding Area
7 | IESCO | IBD | B/Khu | B/Khu (R) | 132/220 KV G/S B/Khu | Golf city | 89216 |  |  |  | 08:30 | 13:30 |  | Golf city
8 | IESCO | IBD | Div-1 | Nilore | 132/220 KV G/S B/Khu | Park View | New |  |  |  | 08:30 | 13:30 |  | Park View City
9 | IESCO | IBD | Div-I | Nilore | 132 KV G/S Nilore | Chirah | 14704 | 22-09-2025 29-09-2025 07.10.2025 |  |  | 08:30 | 13:30 | Bifurcation of 11KV Chirrah Feeder | Chirrah and sorrounding areas
10 | IESCO | IBD | Div-I | Nilore | 132 KV G/S Nilore | PINSTECH Coloney | 14721 |  |  |  | 08:30 | 13:30 |  | Pinstech Colony & Surrounding Areas
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Chaklala | State Bank | 002521 | 21.09.2025 28.09.2025 12.10.2025 19.10.2025 26.10.2025 |  |  | 7:00 | 10:00 | For shifting of HT/LT line from Jinnah Park Chowk to Ammar Chowk | New gulzar-e-Quaid & sorrounding area
2 | [5 empty] | Humayun Road | 002525 |  |  |  | 7:00 | 10:00 |  | Askari 13, 14 & 7, Dk Nawaz & sorrounding area
3 |  |  | Cantt | Jhanda | 132KV Cantt | Jhanda | 017921 |  |  |  | 7:00 | 10:00 |  | jhanda chichi police line ,special branch askari 10 police station c/line &iesco complex
4 |  |  |  | Jhanda | 132KV Chaklala | CNC | 002524 |  |  |  | 7:00 | 10:00 |  | Army House & sorrounding area
5 |  |  | Tariqabad | Adyala |  | 502 Work Shop | 002540 |  |  |  | 7:00 | 10:00 |  | fatima jinnah university, IESCO Complex,Distirect Courts ,Dist Nazim, Punjab House
8 |  |  |  | Chaklala | 132KV Chaklala | Kot Jabbi | 002539 | 24.09.2025 01.10.2025 06.10.2025 |  |  | 7:00 | 10:00 | For LV Work Chaklala | Kot Jabbi & sorrounding area
9 | [5 empty] | Bostan Khan | 002538 |  |  |  | 7:00 | 10:00 |  | Bostan Road & sorrounding area
1 | IESCO | Cantt | Tariqabad | Q.A Colony | 132KV Ranyal | Qureshiabad | 120401 | 01.10.2025 07.10.2025 11.10.2025 14.10.2025 |  |  | 8:00 | 13:00 | For External Electrification iro Rehbar Colony Housing Scheme Mouza Hayal Ranyal & Hayal Dhamial Chakri Road | Qureshiabad & sorrounding area
2 | [5 empty] | Girja-I | 120402 | [6 empty] | Girja Road & sorrounding area
3 |  |  |  | Dhamial |  | Ranyal | 120403 | [6 empty] | Ranyal & sorrounding area
1 | IESCO | City | Westridge | T/Bhatta | Kamalabad | Azizabad | 1020 | 25-09-2025 04-10-2025 |  |  | 10:00 Hrs | 13:00 Hrs | Reconductoring Of Capt Amir Feeder | Grooti,kamalabad , Mughalabad ,Pople Colony St No 01 to St No 10, Moh Hajian , Rawal town, Safdarabad
2 | IESCO | City | Westridge | T/Bhatta | Kamalabad | People Colony | 1022 | [6 empty] | St No 11 to St No 57 Allama Iqbal Cly Rwp & Surrounding Area
3 | IESCO | City | Westridge | Kamalabad | Kamalabad | Radio Pak | 1006 | [6 empty] | Chamanabad, Misrial Road,Barafkhana Chowk,Rehmanabad
4 | IESCO | City | Westridge | Kamalabad | Kamalabad | Capt Amir | 104616 | [6 empty] | Dk: Sydian Chowk, ImamBargha, Mohallah Anwarul Islam, Ghaziabad.
5 | IESCO | City | Westridge | Kamalabad | Kamalabad | Kamalabad | 1025 | [6 empty] | Kamalabad & Surrounding Area
6 | IESCO | City | Westridge | T/Bhatta | Kamalabad | Allama Iqbal Cly | 1010 | [6 empty] | Allama Iqbal Colony & Surrounding Area
1 | IESCO | Attock | Attock | Hattian | 132KV Faqirabad | Shamasabad | 12007 | 01.10.2025 04.10.2025 |  |  | 08:00 | 16:00 | for safety Purpose during dismantling of existing tower/erection of location No. 37, 38,43,44 & 23 for remodeling with Greely Conductor of 132Kv S/C Gondal to Faqeerabad | Shamasabad & Surrounding area
6 | IESCO | Islamabad | Division No.I | G-6 | 132KV/220KV Bhara Kahu | Bani Gala | 122507 | 07.10.2025 11.10.2025 14.10.2025' |  |  | 08:30 | 13:30 | Estimate for Rehablitation of 11KV Bani Gala feeder & Ring System of 11KV Bani Gala Mohra Noor and Islamabad Club feeders under bELR Head (W/O 2k25411ELRHT29) | Bani Gala & surrounding area
1 | NTDC (North) | Asset Management (North) 500KV Circle NTDC, New Rawat | Addl. Manager 500KV Grid Station NTDC, Rawat | Addl. Manager 500KV Grid Station NTDC, Rawat | 132KV C.B E1Q2 Controlling Rawat - DHA Phase-IV (DHR-1) Ckt along with related Isolators and E/S |  |  | 01-10-2025 |  |  | 09:00 hrs | 16:00 hrs | For annual maintenance and protectionn testing | No area will be affected as 132KV Grid Station Adyala will be fed from 132KV Grid Station New Chakri & DHA Phase-IV from Adyala side.
2 |  |  |  |  | 132KV C.B E2Q2 Controlling Rawat - Chakri (CKR-1) Ckt along with related Isolators and E/S |  |  | 02-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Chakri will be fed from 132KV Grid Station Chakwal side.
3 |  |  |  |  | 132KV C.B E4Q1 Controlling Rawat - Gujjar Khan (GKN-4) Ckt along with related Isolators and E/S |  |  | 06-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as Gujjar Khan GSS will be fed from Mangla side.
4 |  |  |  |  | 132KV C.B E5Q1 Controlling Rawat - Sanghoi (SNG-1) Ckt along with related Isolators and E/S |  |  | 07-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affected as 132kv Sanghoi, Dina & R.B.Mangla GSS will be fed from Mangla Power House.
5 |  |  |  |  | 132KV C.B E7Q1 Controlling Rawat - Chakwal (CWL-14) Ckt along with related Isolators and E/S |  |  | 08-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Chakwal will be fed from Chakri, Chakri Road or Padshahan side.
6 |  |  |  |  | 132KV C.B E10Q1 Controlling Rawat - Old Rawat (RWT-1) Ckt along with related Isolators and E/S |  |  | 09-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affect as 132KV Old Rawat will be fed from Mangla side.
7 |  |  |  | Addl. Manager 500KV Grid Station NTDC, Rawat | 132KV C.B E12Q1 Controlling Rawat - Rawat-II (RAW-1) Ckt along with related Isolators and E/S |  |  | 13-10-2025 |  |  | 09:00 hrs | 16:00 hrs | For annual maintenance and testing | No Area will be affect as 132KV Kahuta KRL & Rawat-II will be fed from AEC Nilore side through AEC-1 - KHT-1 Circuit
8 | NTDC (North) | Asset Management (North) 500KV Circle NTDC, New Rawat | Addl. Manager 500KV Grid Station NTDC, Rawat |  | 132KV C.B E13Q1 Controlling Rawat - DHA Valley (DHV-1) Ckt along with related Isolators and E/S |  |  | 14-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affect as 132KV DHA Velly will be fed from 132KV GSS Gangal side side through (GNG-1-DHV-2) Circuit
9 |  |  |  |  | 132KV C.B E14Q1 Controlling Rawat - DHA (ISO-102) Ckt along with related Isolators and E/S |  |  | 15-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affect as 132KV DHA will be fed from 132KV GSS NPF side through (NPF-2-ISO-101) Circuit
10 |  |  |  |  | 132KV C.B E16Q1 Controlling Rawat - Sowan (SAN-2) Ckt along with related Isolators and E/S |  |  | 16-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Sowan will be fed from 132KV Grid Station Bakramandi side.
11 |  |  |  |  | 132KV C.B E18Q1 Controlling Rawat - Bahria Town (BTN-1) Ckt along with related Isolators and E/S |  |  | 20-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Bahria Town will be fed from AGL P/H side.
12 |  |  |  |  | 132KV C.B E3Q1 Controlling Rawat - Sohawa (SWA-1) Ckt along with related Isolators and E/S |  |  | 21-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Sohawa will be fed from 132KV Grid Station Jhelum side.
13 |  |  |  |  | 132KV C.B E17Q1 Controlling Rawat - Al-Ghurair Giga (GAG-1) Ckt along with related Isolators and E/S |  |  | 22-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Al- Ghurair Giga will be fed from 132KV Grid Station Chaklala side.
1 | IESCO | City | Westridge | Kamalabad | I-16 | Ameer Hamza | 104616 | 2025-10-02 |  |  | 10:00 Hrs | 13:00 Hrs | S.Hazard Friends Colony Misrial Road | Dk Gujran,Amer Hamza Cly,Chakra Rd, Misrial Rd
2 | IESCO | City | Westridge | Kamalabad | Kamalabad | Radio Pak | 1006 | 01-10-2025 08-10-2025 |  |  |  |  | S.Hazard St No 24 Chammanabad Rawalpindi | Barafkhana,Chammanabad, Madina Cly,Misrial Road
3 | IESCO | City | Westridge | Seham | I-16 | LAkhoo Rd | 104615 | 06-10-2025 11-10-2025 |  |  |  |  | LV Work Shiekhpur Seham | Gulshan e Khudadad,Kohsar Cly Razaq Town,Rehmat Towm,Aftab Town
1 | IESCO | Cantt | Mandra | Sowan | 132KV Sowan | Mehboob Shaheed | 87418 | 02.10.2025 06.10.2025 |  |  | 08:.00 | 11:00 | For DHA Down Town overhead to underground deposit work | Chiriten Colony & Surrounding area
2 |  |  |  | Morgah |  | Park View | 87410 | [6 empty] | Morgah, Park View and Surrounding area.
3 |  |  |  | Morgah |  | Pindi Board | 87415 | [6 empty] | BISE & Surrounding area.
4 |  |  |  | Korang |  | Jail Park-1 | 87407 | [6 empty] | Boastan Road Car Chowk & Surrounding area
5 |  |  |  | Korang |  | Car Chowk | 87414 | [6 empty] | Car Chowk & Surrounding
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Adyala | Humayun-I | 109112 | 02.10.2025 06.10.2025 09.10.2025 |  |  | 9:00 | 12:00 | For dismantling of HT overhead lines & conversion of Overhead to Underground at Khawaja Corporation Chowk Adyala Road Rawalpindi | Askari 13, 14 & 7, Dk Nawaz & sorrounding area
7 |  |  |  | Adyala |  | Defence Road | 109113 | [6 empty] | Defence Road & sorrounding area
8 | [5 empty] | Rose Lane | 109112 | [6 empty] | Rose Lane & sorrounding area
9 | [5 empty] | Adyala | 109106 | [6 empty] | Adyala & sorrounding area
10 | [5 empty] | Kalyal | 109101 | [6 empty] | Kalyal & sorrounding area
1 | IESCO | IBD | B/Kahu | Murree | Murree | Sunny Bank | 13704 | 04.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | 12 Div Motor Agency Sunny Bank Bazar and Chitta Mor.
2 | IESCO | IBD | B/Kahu | Murree | Murree | Cecil | 13714 |  |  |  | 9:00 | 14:00 | Safety purpose | Cecil Resorts
3 | IESCO | IBD | B/Kahu | J/Gali | Murree | Barrian | 13706 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Ratti Gali, Sawar Gali, Kalli Matti, Barrian
4 | IESCO | IBD | B/Kahu | Patriata | Murree | Upper Topa | 13705 |  |  |  | 9:00 | 14:00 | Safety purpose | Mohra Batnara, Sambal Bia, Ghora Bastal, Khajut, Hokra Karri.
5 | IESCO | IBD | B/Kahu | Murree | Murree | Kuldana | 13702 | 06.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | Mall Road, Kashmir Point and Mashyari.
6 | IESCO | IBD | B/Kahu | J/Gali | Murree | Kohallah | 13701 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Khanitak, Osia, Maloot, Rawat
7 | IESCO | IBD | B/Kahu | J/Gali | Murree | PC | 13708 |  |  |  | 9:00 | 14:00 | Safety purpose | PC Bhurban
8 | IESCO | IBD | B/Kahu | Patriata | Murree | Patriata | 13712 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Charhan, Mohra Syedan, Sambal Syedan, Ghel, Sorasi, Dhanda, Waghal, Bandi, Ban, Khalabut
9 | IESCO | IBD | B/Kahu | Patriata | Murree | Upper Topa | 13705 |  |  |  | 9:00 | 14:00 | Safety purpose | Mohra Batnara, Sambal Bia, Ghora Bastal, Khajut, Hokra Karri.
10 | IESCO | IBD | B/Kahu | Murree | Murree | Pindi Point | 13707 | 07.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | Senavo Ahta Noor Khan Motory Way and Lakoot.
11 | IESCO | IBD | B/Kahu | J/Gali | Murree | Gharial | 13711 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Jhika Gali, Gharial, Kashmiri Bazar, Dana, Aliot
12 | IESCO | IBD | B/Kahu | J/Gali | Murree | MCM | 13716 |  |  |  | 9:00 | 14:00 | Safety purpose | Jhika Gali, Gharial, Kashmiri Bazar, Dana, Aliot
13 | IESCO | IBD | B/Kahu | Murree | Murree | Sunny Bank | 13704 | 08.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | 12 Div Motor Agency Sunny Bank Bazar and Chitta Mor.
14 | IESCO | IBD | B/Kahu | Murree | Murree | Cecil | 13714 |  |  |  | 9:00 | 14:00 | Safety purpose | Cecil Resorts
15 | IESCO | IBD | B/Kahu | J/Gali | Murree | Barrian | 13706 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Ratti Gali, Sawar Gali, Kalli Matti, Barrian
16 | IESCO | IBD | B/Kahu | Murree | Murree | Kuldana | 13702 | 09.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | Mall Road, Kashmir Point and Mashyari.
17 | IESCO | IBD | B/Kahu | J/Gali | Murree | Gharial | 13711 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Jhika Gali, Gharial, Kashmiri Bazar, Dana, Aliot
18 | IESCO | IBD | B/Kahu | J/Gali | Murree | MCM | 13716 |  |  |  | 9:00 | 14:00 | Safety purpose | Jhika Gali, Gharial, Kashmiri Bazar, Dana, Aliot
19 | IESCO | IBD | B/Kahu | Patriata | Murree | Patriata | 13712 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Charhan, Mohra Syedan, Sambal Syedan, Ghel, Sorasi, Dhanda, Waghal, Bandi, Ban, Khalabut
20 | IESCO | IBD | B/Kahu | Patriata | Murree | Upper Topa | 13705 |  |  |  | 9:00 | 14:00 | Safety purpose | Mohra Batnara, Sambal Bia, Ghora Bastal, Khajut, Hokra Karri.
21 | IESCO | IBD | B/Kahu | Murree | Murree | Pindi Point | 13707 | 11.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | Senavo Ahta Noor Khan Motory Way and Lakoot.
22 | IESCO | IBD | B/Kahu | J/Gali | Murree | Barrian | 13706 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Ratti Gali, Sawar Gali, Kalli Matti, Barrian
23 | IESCO | IBD | B/Kahu | Patriata | Murree | Patriata | 13712 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Charhan, Mohra Syedan, Sambal Syedan, Ghel, Sorasi, Dhanda, Waghal, Bandi, Ban, Khalabut
24 | IESCO | IBD | B/Kahu | Murree | Murree | Sunny Bank | 13704 | 13.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | 12 Div Motor Agency Sunny Bank Bazar and Chitta Mor.
25 | IESCO | IBD | B/Kahu | Murree | Murree | Cecil | 13714 |  |  |  | 9:00 | 14:00 | Safety purpose | Cecil Resorts
26 | IESCO | IBD | B/Kahu | J/Gali | Murree | Gharial | 13711 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Jhika Gali, Gharial, Kashmiri Bazar, Dana, Aliot
27 | IESCO | IBD | B/Kahu | Murree | Murree | Kuldana | 13702 | 14.10.2025 |  |  | 9:00 | 14:00 | Annual Maintenance | Mall Road, Kashmir Point and Mashyari.
28 | IESCO | IBD | B/Kahu | J/Gali | Murree | Kohallah | 13701 |  |  |  | 9:00 | 14:00 | Annual Maintenance | Khanitak, Osia, Maloot, Rawat
29 | IESCO | IBD | B/Kahu | J/Gali | Murree | PC | 13708 |  |  |  | 9:00 | 14:00 | Safety purpose | PC Bhurban
30 | IESCO | IBD | B/Kahu | Patriata | Murree | Upper Topa | 13705 |  |  |  | 9:00 | 14:00 | Safety purpose | Mohra Batnara, Sambal Bia, Ghora Bastal, Khajut, Hokra Karri.
1 | IESCO | IBD | XEN-II | I-9 | Zero Point | EVC-I | 22345 | 06.10.2025 |  |  | 09.00 AM | 12.00 PM | Provision of Electricity Connection at H-9 Metro Bus Depot For EV Charging Buses | Independent
1 | IESCO | City | S/Town | F-block | H-11 | Raja Sultan | 72716 | 04-10-2025 11-10-2025 |  |  | 08:30 | 13:30 | Fitting of Cross arms at Metro Bus Charging Station at I-9/H-9 Green Belt | Raja Sultan & surroundings
2 | IESCO | City | City | asghar Mall | H-11 | Eidgah | 72714 | [6 empty] | Eidgah Rod & surroundings
3 | IESCO | City | City | K.Sir Syed | H-11 | Dk.Naju | 72715 | [6 empty] | Dk.Naju & surroundings
4 | IESCO | Islamabad | Division II | I-10 | H-11 | Auto Workshop | 72721 |  |  |  | 08:30 | 13:30 |  | Auto Workshop
5 | IESCO | Islamabad | Division II | I-9 | H-11 | PTCL I-9 | 72728 |  |  |  | 08:30 | 13:30 |  | PTCL I-9
6 | IESCO | Islamabad | Division II | I-9 | H-11 | New Exchange | 72719 |  |  |  | 08:30 | 13:30 |  | New Exchange
7 | IESCO | Islamabad | Division II | I-9 | H-11 | Ufone I-9 | 72733 |  |  |  | 08:30 | 13:30 |  | Ufone I-9
8 | IESCO | Islamabad | Division II | I-9 | H-11 | Fazal Ghee I-9 | 72705 |  |  |  | 08:30 | 13:30 |  | Fazal Ghee I-9
9 | IESCO | Islamabad | Division II | I-9 | H-11 | S.E.S I-9 | 72731 |  |  |  | 08:30 | 13:30 |  | S.E.S I-9
10 | IESCO | Islamabad | Division II | I-10 | H-11 | NDC-2 | 72718 |  |  |  | 08:30 | 13:30 |  | NDC-2
1 | IESCO | Attock | Attock | Ghour Ghushti | 132KV Faqirabad | Ghour Ghushti | 12009 | 03.10.2025 to 10.10.2025 |  |  | 08:00 | 14:00 | for stringing 500kv D/CT/Line from Terbela to Islamabad West S/ Station between section T. No 64-69of 132Kv S/C Gondal to Faqeerabad | Ghour Ghushti & Surrounding area
1 | IESCO | Attock | Taxila | Sangjani | 220Kv Sangjani | Sangjani | 81003 | 07.10.2025 09.10.2025 14.10.2025 |  |  | 09:00 | 12:00 | Stringing of HT Line Shifting of Sangjani feeder | Sangjani
2 | IESCO | Attock | Taxila | Sangjani | 132KV Taxila | pind Parian | 121801 |  |  |  | 09:00 | 12:00 |  | pind Parian
3 | IESCO | Attock | Taxila | Sangjani | 132KV Taxila | Cabinet | 121813 |  |  |  | 09:00 | 12:00 |  | Cabinet
4 | IESCO | Attock | Taxila | Sangjani | 220Kv Sangjani | Paswal | 81002 | 03.10.2025 06.10.2025 09.10.2025 |  |  | 09:00 | 12:00 | Safety Hazards works baba Shaheed village Chokar | Paswal