## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date | Existing Operation Maintenance Date | Proposed Change Date for Operation Maintenance | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
1 | IESCO | Cantt | Tariqabad | Tariqabad | 132KV Chaklala | State Bank | 002521 | 21.09.2025 28.09.2025 12.10.2025 19.10.2025 26.10.2025 |  |  | 7:00 | 10:00 | For shifting of HT/LT line from Jinnah Park Chowk to Ammar Chowk | New gulzar-e-Quaid & sorrounding area
2 | IESCO | Cantt |  |  |  | Humayun Road | 002525 |  |  |  | 7:00 | 10:00 |  | Askari 13, 14 & 7, Dk Nawaz & sorrounding area
3 | IESCO | Cantt | Cantt | Jhanda | 132KV Cantt | Jhanda | 017921 |  |  |  | 7:00 | 10:00 |  | jhanda chichi police line ,special branch askari 10 police station c/line &iesco complex
4 | IESCO | Cantt |  | Jhanda | 132KV Chaklala | CNC | 002524 |  |  |  | 7:00 | 10:00 |  | Army House & sorrounding area
5 | IESCO | Cantt | Tariqabad | Adyala |  | 502 Work Shop | 002540 |  |  |  | 7:00 | 10:00 |  | fatima jinnah university, IESCO Complex,Distirect Courts ,Dist Nazim, Punjab House
1 | NTDC (North) | Asset Management (North) 500KV Circle NTDC, New Rawat | Addl. Manager 500KV Grid Station NTDC, Rawat | Addl. Manager 500KV Grid Station NTDC, Rawat | 132KV C.B E1Q2 Controlling Rawat - DHA Phase-IV (DHR-1) Ckt along with related Isolators and E/S |  |  | 01-10-2025 |  |  | 09:00 hrs | 16:00 hrs | For annual maintenance and protectionn testing | No area will be affected as 132KV Grid Station Adyala will be fed from 132KV Grid Station New Chakri & DHA Phase-IV from Adyala side.
2 |  |  |  |  | 132KV C.B E2Q2 Controlling Rawat - Chakri (CKR-1) Ckt along with related Isolators and E/S |  |  | 02-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Chakri will be fed from 132KV Grid Station Chakwal side.
3 |  |  |  |  | 132KV C.B E4Q1 Controlling Rawat - Gujjar Khan (GKN-4) Ckt along with related Isolators and E/S |  |  | 06-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as Gujjar Khan GSS will be fed from Mangla side.
4 |  |  |  |  | 132KV C.B E5Q1 Controlling Rawat - Sanghoi (SNG-1) Ckt along with related Isolators and E/S |  |  | 07-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affected as 132kv Sanghoi, Dina & R.B.Mangla GSS will be fed from Mangla Power House.
5 |  |  |  |  | 132KV C.B E7Q1 Controlling Rawat - Chakwal (CWL-14) Ckt along with related Isolators and E/S |  |  | 08-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Chakwal will be fed from Chakri, Chakri Road or Padshahan side.
6 |  |  |  |  | 132KV C.B E10Q1 Controlling Rawat - Old Rawat (RWT-1) Ckt along with related Isolators and E/S |  |  | 09-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affect as 132KV Old Rawat will be fed from Mangla side.
7 |  |  |  | Addl. Manager 500KV Grid Station NTDC, Rawat | 132KV C.B E12Q1 Controlling Rawat - Rawat-II (RAW-1) Ckt along with related Isolators and E/S |  |  | 13-10-2025 |  |  | 09:00 hrs | 16:00 hrs | For annual maintenance and testing | No Area will be affect as 132KV Kahuta KRL & Rawat-II will be fed from AEC Nilore side through AEC-1 - KHT-1 Circuit
8 | NTDC (North) | Asset Management (North) 500KV Circle NTDC, New Rawat | Addl. Manager 500KV Grid Station NTDC, Rawat |  | 132KV C.B E13Q1 Controlling Rawat - DHA Valley (DHV-1) Ckt along with related Isolators and E/S |  |  | 14-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affect as 132KV DHA Velly will be fed from 132KV GSS Gangal side side through (GNG-1-DHV-2) Circuit
9 |  |  |  |  | 132KV C.B E14Q1 Controlling Rawat - DHA (ISO-102) Ckt along with related Isolators and E/S |  |  | 15-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No Area will be affect as 132KV DHA will be fed from 132KV GSS NPF side through (NPF-2-ISO-101) Circuit
10 |  |  |  |  | 132KV C.B E16Q1 Controlling Rawat - Sowan (SAN-2) Ckt along with related Isolators and E/S |  |  | 16-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Sowan will be fed from 132KV Grid Station Bakramandi side.
11 |  |  |  |  | 132KV C.B E18Q1 Controlling Rawat - Bahria Town (BTN-1) Ckt along with related Isolators and E/S |  |  | 20-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Bahria Town will be fed from AGL P/H side.
12 |  |  |  |  | 132KV C.B E3Q1 Controlling Rawat - Sohawa (SWA-1) Ckt along with related Isolators and E/S |  |  | 21-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Sohawa will be fed from 132KV Grid Station Jhelum side.
13 |  |  |  |  | 132KV C.B E17Q1 Controlling Rawat - Al-Ghurair Giga (GAG-1) Ckt along with related Isolators and E/S |  |  | 22-10-2025 |  |  | 09:00 hrs | 16:00 hrs |  | No area will be affected as 132KV Grid Station Al- Ghurair Giga will be fed from 132KV Grid Station Chaklala side.
19 |  |  |  |  | 132KV Old Rawat | Old Rawat | 017716 | 08.10.2025 11.10.2025 14.10.2025 20.10.2025 23.10.2025 25.10.2025 27.10.2025 30.10.2025 |  |  | 9:00 | 14:00 | For shifting of HT Line from T-Chowk to HASCOL Pump T-Chowk Flyover | Rawat & sorrounding area
20 | [5 empty] | New Rawat | 017701 | [6 empty] | Rawat & sorrounding area
21 |  |  |  |  | 500KV New Rawat | AOWHS | 064506 | [6 empty] | Emaar & sorrounding area
22 |  |  |  |  | 132KV Old Rawat | Suparco | 017717 | [6 empty] | Suparco & sorrounding area
23 |  |  |  |  | 132KV Old Rawat | CWO | 17722 | [6 empty] | CWO & surrounding area
24 |  |  |  |  | 132KV Sowan | IST | 87422 | [6 empty] | Space Technology & sorrounding area
1 | IESCO | Cantt | Cantt | Civil line | 132KV Chaklala | Rawalpindi-III | 002510 | 16.10.2025 21.10.2025 |  |  | 14:00 | 17:00 | For Execution of Meyo Road (RDA Work) | fatima jinnah university, IESCO Complex,Distirect Courts ,Dist Nazim,DCO Office,Punjab House
2 |  |  |  | Jhanda | 132KV Cantt | Jhanda | 17921 | [6 empty] | Jhanda & sorrounding area
3 |  |  |  | Jhanda |  | VIP | 17911 | [6 empty] | VIP & sorrounding area
4 |  |  |  | Civil Line |  | Sir Syed Road | 17913 | [6 empty] | Sir Syed Road & sorrounding area
1 | IESCO | Cantt | Cantt | Civil line | 132KV Chaklala | Rawalpindi-III | 002510 | 19.10.2025 26.10.2025 |  |  | 9:00 | 12:00 | Qazia Street Maqbal Abad Safety Hazard Work | fatima jinnah university, IESCO Complex,Distirect Courts ,Dist Nazim,DCO Office,Punjab House
2 | IESCO | Cantt | Mandra | Mandra | 132KV Gujar Khan | Hamid Jhangi | 004915 | 14.10.2025 18.10.2025 23.10.2025 |  |  | 9:00 | 12:00 | For LV Work Pind Pauan Dk Charbian & Dk Pothi | Hamid Jhangi, Taju Jhangi & sorrounding area
1 | IESCO | Attock | Attock | Hazro | 132KV Faqirabad | Shahdair | 12013 | 15-10-2025 20-10-2025 25-10-2025 27-10-2025 |  |  | 09:00AM | 12:00PM | Erriection of Poles & stringing of line iro Area Planning Shahdair & Hazro Feeder | Shahdair & Surrounding area
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Sub Division New Wah | 132KV Faqirabad (FQB-2) - Gondal (GND-2) along with related earth switches. |  |  | 15-10-2025 To 15-11-2025 (Contineous) |  |  | 15-10-2025 10:00 Hrs | 15-11-2025 16:00 Hrs | For safety purpose for dismantling of existing Landative Towers, erection of New ZM Towers & stringing of conductor for remodeling/ reconductoring with greely of 132KV T/Line Gondal to Faqirabad | No area will be affected as 132KV GSS Faqirabad will be fed from Burhan side & 132KV GSS Gondal will be fed from Attock/Jahangira side.
1 | IESCO | Cantt | Tariqabad | Adyala | 132KV Adyala | Defence Road | 109113 | 18.10.2025 |  |  | 9:00 | 12:00 | For dismantling of HT overhead lines & conversion of Overhead to Underground at Khawaja Corporation Chowk Adyala Road Rawalpindi | Defence Road & sorrounding area
2 | [5 empty] | Rose Lane | 109112 | [6 empty] | Rose Lane & sorrounding area
3 | [5 empty] | Adyala | 109106 | [6 empty] | Adyala & sorrounding area
4 | [5 empty] | Kalyal | 109101 | [6 empty] | Kalyal & sorrounding area
1 | IESCO | Rawalpindi Cantt | Rawat | Rawat | 132kV GSS Old Rawat | CWO | 17722 | 22-10-2025 23-10-2025 |  |  | 08:00 Hrs | 16:00 Hrs | For safety purpose during erection of SPD pole & ED tower along with stringing of conductor & dismantling of existing tower ZM1 tower for shifting of circuits due to construction of T-Chowk fly over near Rewat. | CWO
[6 empty] | SPARCO | 17717 | [6 empty] | SPARCO
[6 empty] | New Rawat | 17701 | [6 empty] | New Rawat
[5 empty] | 500/220/132kV GSS New Rawat | EMAAR (AOWHS) | 64506 | [6 empty] | EMAAR (AOWHS)
[5 empty] | 132kV GSS Sawan | IST | 87422 | [6 empty] | IST
2 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Sub Division New Wah | 132KV Bus BAR PAC Kamara (Consumer) GSS |  |  | 19-10-2025 |  |  | 09:00 Hrs | 16:00 Hrs | For safety purpose during erection of metering CT/PT | During this Shut Down 132KV GSS PAC Kamara will be affected.
3 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | A.E (T) Sub Division Margalla | 132KV Margalla (MRG-3) - NDC-1 (ISO-101) T/Line along with related earth switch |  |  | 18-10-2025 |  |  | 07:00 Hrs | 18:00 Hrs | For Safety Purpose. i. For energization of new line bay (conversion from ISO Bay) along with metering arrangement. ii. For providing droppers up to isolator for Power Transformer T-2. iii. Stringing of one Lynx span | 132KV GSS NDC-I (Consumer Grid) will be affected.
4 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | R.E Sub Division Rawalpindi | 132 KV AGL (E2Q2) - Cantt (RPC-1) T/Line along with related earth switches , AGL (E5Q1) - Bharia Town - (BTN-2) along with related earth switches & 132KV Sowan (SAN-1) - Bakramandi (BKM-2) along with related earth switches |  |  | 20-10-2025 |  |  | 08:00 Hrs | 13:00 Hrs | For safety purpose during providing of flying jumpers from 132kV T/Line Sawan to Bakramandi (between loc # 97 to 98) to provide second source for 132kV T/Line AGL to REPCO Cantt for availing future shut down at 132kV circuits 132kV New Rewat to Al-Ghurair Giga & 132kV New Rawat to Bahria Town | During this Shut Down, only AGL (IPP) will be affected. 132KV GSS Giga, Chaklala, REPCO cantt will be fed through New Rawat (E17Q1), 132kV GSS Bahria Town will be fed from New Rewat (E18Q1) & 132KV Sowan will be fed from New Rewat (E16Q1), & 132kV GSS Bakramandi will be fed through KTM side.
5 |  |  |  |  | 132KV New Rawat (E17Q1) - Al-Ghurair Giga (GRG-1) along with related earth switches & 132KV New Rawat (E18Q1) - Bahria Town Phase-IV (BTN-1) along with related earth switches |  |  | 21-10-2025 To 23-10-2025 (Contineous) |  |  | 21-10-2025 08:00 Hrs | 23-10-2025 16:00 Hrs | For safety purpose during erection of SPD pole & ED tower along with stringing of conductor & dismantling of existing tower ZM1 tower for shifting of circuits due to construction of T-Chowk fly over near Rewat. | No area will be affected, as 132kV T/Line AGL to REPCO Cantt will be energized on 20-10-25 by providing temporary droppers from 132kV T/Line Sowan to Bakramandi
6 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rawalpindi | R.E Sub Division Rawalpindi | 132 KV AGL (E2Q2) - Cantt (RPC-1) T/Line along with related earth switches , AGL (E5Q1) - Bharia Town - (BTN-2) along with related earth switches & 132KV Sowan (SAN-1) - Bakramandi (BKM-2) along with related earth switches |  |  | 24-10-2025 |  |  | 08:00 Hrs | 13:00 Hrs | For safety purpose during removing of flying jumpers of 132kV T/Line Sawan to Bakramandi (between loc # 97 to 98) to provide second source for 132kV T/Line AGL to REPCO Cantt for availing future shut down at 132kV circuits 132kV New Rewat to Al-Ghurair Giga & 132kV New Rewat to Bahria Town | AGL (IPP) will be affected. 132kV GSS Giga, Chaklala, REPCO cantt will be fed through New Rewat (E17Q1), 132kV GSS Bahria Town will be fed from New Rewat (E18Q1) & 132kV Sawan will be fed from New Rewat (E16Q1), & 132kV GSS Bakramandi will be fed through KTM side.