## mail-approval-shutdown
S # | DISCO | Circle | Division | Sub Division | Name of 132 KV Grid Station | Name of Feeder | Feeder Code | Date |  | Time From | Time To | Purpose of Shut Down | Affected Area | Remarks
11 | NGC (North) | Director (FO) A.M (North) NGC Circle Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | 132KV C.B E16Q1 Controlling Rawat - DHA Emaar (DHE-1) Ckt along with related Isolators and E/S |  |  | 20-10-2026 |  | 09:00 hrs | 17:00 hrs | For annual maintenance/ protection testing & to attendt Hot Spot pointed out during Thermovision Survey | No area will be affected as 132KV Grid Station DHA Emaar will be fed from 132KV Grid Station Sowan side.
12 | NGC (North) | Director (FO) A.M (North) NGC Circle Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | 132KV C.B E17Q1 Controlling Rawat - Al-Ghurair Giga (GAG-1) Ckt along with related Isolators and E/S |  |  | 21-10-2026 |  | 09:00 hrs | 17:00 hrs |  | No area will be affected as 132KV Grid Station Al- Ghurair Giga will be fed from 132KV Grid Station Chaklala side.
13 | NGC (North) | Director (FO) A.M (North) NGC Circle Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | 132KV C.B E18Q1 Controlling Rawat - Bahria Town (BTN-1) Ckt along with related Isolators and E/S |  |  | 22-10-2026 |  | 09:00 hrs | 17:00 hrs | For annual maintenance and testing | No area will be affected as 132KV Grid Station Bahria Town will be fed from AGL P/H side.
14 |  |  |  |  | 132KV C.B E8Q1, Bus Coupler along with related isolators |  |  | 23-10-2026 |  | 09:00 hrs | 17:00 hrs |  | No area will be affected.
15 |  |  |  |  | 132KV Bus Bar.1 along with 132KV C.B E2Q2 Controlling Rawat - Chakri (CKR-1) Ckt along with related Isolators and E/S |  |  | 26-10-2026 |  | 09:00 hrs | 11:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E2Q21 | No area will be affected as 132KV Grid Station Chakri will be fed from 132KV Grid Station Chakwal side.
16 | NGC (North) | Director (FO) A.M (North) NGC Circle Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | 132KV Bus Bar.1 along with 132KV C.B E3Q1 Controlling Rawat - Sohawa (SWA-1) Ckt along with related Isolators and E/S |  |  | 26-10-2026 |  | 11:00 hrs | 13:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E3Q11 | No area will be affected as 132KV Grid Station Sohawa will be fed from 132KV Grid Station Jhelum side.
17 | NGC (North) | Director (FO) A.M (North) NGC Circle Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | 132KV Bus Bar.1 along with 220/132KV, 250MVA Auto Transformer T-5 |  |  | 26-10-2026 |  | 13:00 hrs | 15:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E6Q11 | No area will be affected.
18 |  |  |  |  | 132KV Bus Bar No-1 a.w 132KV C.B E7Q1 Controlling Rawat - Chakwal (CWL-14) Ckt along with related Isolators and E/S |  |  | 26-10-2026 |  | 15:00 hrs | 17:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E7Q11 | No area will be affected as 132KV Chakwal will be fed from Chakri, Chakri Road or Padshahan side.
19 |  |  |  |  | 132KV Bus Bar.1 along with 220/132KV, 250MVA Auto Transformer T-7 |  |  | 27-10-2026 |  | 09:00 hrs | 11:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E10Q21 | No area will be affected.
20 | NGC (North) | Director (FO) A.M (North) NGC Circle Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | Senior Manager (FO) 500KV Grid Station NGC, Rawat | 132KV Bus Bar No-I a.w 132KV C.B E10Q1 Controlling Rawat - Old Rawat (RWT-1) Ckt along with related Isolators |  |  | 27-10-2026 |  | 11:00 hrs | 13:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E10Q11 | No Area will be affect as 132KV Old Rawat will be fed from Mangla side.
21 |  |  |  |  | 132KV Bus Bar No-1 a.w 132KV C.B E17Q1 Controlling Rawat - Al-Ghurair Giga (GAG-1) Ckt along with related Isolators and E/S |  |  | 27-10-2026 |  | 13:00 hrs | 15:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E17Q11 | No area will be affected as 132KV Grid Station Al- Ghurair Giga will be fed from 132KV Grid Station Chaklala side.
22 |  |  |  |  | 132KV Bus Bar No-II a.w 132KV C.B E2Q2 Controlling Rawat - Chakri (CKR-1) Ckt along with related Isolators and E/S |  |  | 28-10-2026 |  | 09:00 hrs | 11:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E2Q22 | No area will be affected as 132KV Grid Station Chakri will be fed from 132KV Grid Station Chakwal side.
23 |  |  |  |  | 132KV Bus Bar No-II a.w 132KV C.B E5Q1 Controlling Rawat - Sanghoi (SGI-1) Ckt along with related Isolators and E/S |  |  | 28-10-2026 |  | 11:00 hrs | 13:00 hrs | To attend the Hot Spots of 132KV Bus Bar Isolator E5Q12 | No Area will be affected as 132kv Sanghoi, Dina & R.B.Mangla GSS will be fed from Mangla Power House.
25 | IESCO | GSO | SS& TL Division IESCO Rwp | AET Margalla | 132 KV New Wah-(Wah-15) Bhatarmore (BMW-2 along with related earth Switch |  |  | 02.10.2026 to 30.11.2026 |  | 14:00 | 14:00 | Extention of already in progress shutdown for erection & stringing activities (during theis period, the portion of line New Wah-Bhatarmore will be Isolated/De-Energized as workingportion) | No area will be effected as 132 KV GSS Bhatarmore will be fed from 132 KV GSS Fateh Jhang side & 132 KV GSS New Wah will be fed from 220KV GSS Burhan side.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Islamabad | A.E (T) Sub Division Rawalakot | 132 KV Bagh (BAG-2) - Hattian (HTN-2) T/Line. |  |  | 15-10-2026 To 30-11-2026 (Continious) |  | 15-10-2026 08:00 Hrs | 30-11-2026 16:00 Hrs | For saftety puprose during reconductring of existing circuit from Lynx to Greely & stringing of 2nd circuit with Greely conductor of 132KV T/Line Bagh to Hattian. | No area will be affected as 132KV GSS Hattian is already been fed from HAZECO siide and 132kV GSS Bagh will be fed from Rawalakot through Trarkhel side. However, up to 40 MW load management will be carried out if required by (ISMO). | The Project Director (GSC), vide letter No. 0001-04 dated 07.10.2026, has intimated that the 132 kV Transmission Lines Kahuta–Plandri (Lot-I & Lot-II) were completed and energized on 12.09.2026.
1 | IESCO | GSO | SS&TL ISD & Rwp | AE(T) No.I | 500KV GSS NGC Rawat |  |  | 12.10.2026 to 01.11.2026 (Continuous) |  | 0800 hrs | 1600 hrs | Installation of Tertiary Busbar of 450MVA, 500/220KV ATB-3 | No area will be affected | 150MW Load Management under N-2 Contigency Conditions across designed IESCO Distribution network Maximum load recorded during last one week was 45-55% during peak hours
1 | IESCO | Cantt | Cantt | Civil Line | 132KV GSS Chaklala | Rawalpindi-III | 002510 | 18.10.2026 25.10.2026 |  | 09:00 | 14:00 | for Shifting of HT/LT line at Katchary Chowk. | Fatiam Jinnah University, IESCO Complex, District Courts, District Nazim, DCO Office & Residency, Income Tax Office, SSP Office. Dk. Chiragh Din Punjab House.
2 | IESCO | Cantt | Cantt | Jhanda |  | VIP | 017911 | [5 empty] | Army House, District Courts, Generals Colony, VIP Colony, ANF H/Q, GOR-I, COAS House, Golf Club, Ayub Park & Forest department.
3 | IESCO | Cantt | Taeiqabad | Taeiqabad |  | Hamayun Road | 002525 | [5 empty] | Askari 13, 14,& 7, Dk Nawaz & surrounding area
1 | IESCO | GSO Circle | SS&TL ISD | AE(T) No.II | 132Kv Murree (MRE-2) - Chattar Kalas (CTK-1) Transmission Line | 132KV GSS Minhasa |  | 19.10.2026, 22.10.2026, 25.10.2026, 28.10.2026 31.10.2026, 03.11.2026, 07.11.2026 |  | 07:00 Hrs | 17:00 Hrs | For erection of ZM-60 Tower at Loc No.09 A & Stringing from Loc No. 10 & 12 & dismantling at Loc No. 11
[6 empty] | Dheer Kot | 79401 | [5 empty] | Dheer Kot
[6 empty] | chaman kot | 79402 | [5 empty] | chaman kot
[6 empty] | Dana Express | 79409 | [5 empty] | Dana Express
[6 empty] | DAHLA | 79411 | [5 empty] | DAHLA
[6 empty] | Gujarkohala | 79412 | [5 empty] | Gujarkohala
[6 empty] | Minhasa Sohawa | 79406 | [5 empty] | Minhasa Sohawa
[6 empty] | Numble | 79405 | [5 empty] | Numble
[6 empty] | Birote | 79408 | [5 empty] | Birote
[6 empty] | Rangla | 79407 | [5 empty] | Rangla
[6 empty] | Ghaziabad | 79410 | [5 empty] | Ghaziabad
132KV GSS Chattr Kalas
[6 empty] | Komi Kot | 13603 | [5 empty] | Komi Kot
[6 empty] | chattar kallas-1 | 132601 | [5 empty] | chattar kallas-1
[6 empty] | Chattar Kallas-II | 132602 | [5 empty] | Chattar Kallas-II
1 | IESCO | Islamabad | Division I | F-6 | F-6 | Secretariat III | 86423 | 25.10.2026 |  | 09:00 | 14:00 | For safety purpose at Plot No 56-N Mall of Islamabad Park lane Tower Blue Area Islamabad | Secretariat III
2 | IESCO | Islamabad | Division I | F-6 | F-6 | Secretariat IV | 86424 | [5 empty] | Secretariat IV
3 | IESCO | Islamabad | Division I | F-6 | F-6 | Jinnah Super | 86411 | [5 empty] | Jinnah Super
4 | IESCO | Islamabad | Division I | F-6 | F-6 | NIC | 86415 | [5 empty] | NIC
5 | IESCO | Islamabad | Division I | F-6 | F-6 | State Life | 86426 | [5 empty] | State Life
6 | IESCO | Islamabad | Division I | F-6 | F-6 | Saudi Pak Tower | 86407 | [5 empty] | Saudi Pak Tower
7 | IESCO | Islamabad | Division I | F-6 | F-6 | Stock Exchange | 86413 | [5 empty] | Stock Exchange
8 | IESCO | Islamabad | Division I | F-6 | F-6 | F-7/2 | 86403 | [5 empty] | F-7/2
9 | IESCO | Islamabad | Division I | F-6 | F-6 | Shamas | 86421 | [5 empty] | Shamas
10 | IESCO | Islamabad | Division I | F-6 | F-6 | F-6/1(Loop) | 86402 | [5 empty] | F-6/1(Loop)
11 | IESCO | Islamabad | Division I | F-6 | F-6 | Babul Islam | 86420 | [5 empty] | Babul Islam
12 | IESCO | Islamabad | Division I | F-6 | F-6 | PTET | 86416 | [5 empty] | PTET
13 | IESCO | Islamabad | Division I | F-6 | F-6 | Parbat Road | 86404 | [5 empty] | Parbat Road
1 | IESCO | Cantt | Rawat | Nara Mator | 132KV GSS Kahuta | Nara Mator | 009002 | 21.10.2026 22.10.2026 26.10.2026 28.10.2026 31.10.2026 |  | 08:00 | 15:00 | for Stringing work newly constructed 500KV D/C T/line (TLC-22) | Vill. Batala, Thoa Khalsa, Maira, Matore, Bagla
1 | IESCO | Attock | Taxila | Mohra Chowk | New Wah | Lalazar | 14607 | 24.10.2026 26.10.2026 | 22.10.2026 29.10.2026 31.10.2026 | 07:00 Hrs | 14:00 Hrs | For safety purpose during stringing of conductor for remodeling work from locatio No.23 to 27 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Lalazar
2 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Hussainabad | 14627 |  | 20.10.2026 |  |  |  | Hussainabad
3 | IESCO | Attock | Taxila | Mohra Chowk | New Wah | Lalazar | 14607 | 24.10.2026 26.10.2026 29.10.2026 01.11.2026 | 22-10-2026 29-10-2026 31-10-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No.2 to 12 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Lalazar
4 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Garhi Afghana | 14626 |  | 22-10-2026 29-10-2026 |  |  |  | Garhi Afghana
5 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Industrial Estate Bahtar | 14625 |  | 24-10-2026 |  |  |  | Industrial Estate Bahtar
6 | IESCO | Attock | Taxila | Mohra Chowk | New Wah | Pour Miana | 14608 |  | 21-10-2026 27-10-2026 |  |  |  | Pour Miana
7 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Lala Rukh | 14622 |  | 24-10-2026 |  |  |  | Lala Rukh
8 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Khanabad | 14619 |  | 24-10-2026 28-10-2026 03-11-2026 09-11-2026 16-11-2026 |  |  |  | Khanabad
9 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Col. Sher Khan | 14621 | 24.10.2026 26.10.2026 29.10.2026 01.11.2026 | 29-10-2026 05-11-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 31 to 40 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Col. Sher Khan
10 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Col. Sher Khan | 14621 | 01.11.2026 04.11.2026 07.11.2026 10.11.2026 | 29-10-2026 05-11-2026 |  |  |  | Col. Sher Khan
11 | IESCO | Attock | Taxila | Wah Cantt | New Wah | Khanabad | 14619 |  | 24-10-2026 28-10-2026 03-11-2026 09-11-2026 16-11-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 40 to 43 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Khanabad
12 | IESCO | Attock | Taxila | Wah Cantt | Bahtar More | Kashif Gul | 112002 | 04.11.2026 07.11.2026 10.11.2026 13.11.2026 | 05-11-2026 14-11-2026 18-11-2026 | 07:00 Hrs | 14:00 Hrs | For safety purpose during stringing of conductor for remodeling work from locatio No. 40 to 43 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Kashif Gul
13 | IESCO | Attock | Taxila | Wah Cantt | Bahtar More | Bahatar More | 112020 |  | 07-11-2026 17-11-2026 |  |  |  | Bahatar More
14 | IESCO | Attock | Taxila | Wah Cantt | Bahtar More | I-Block | 112010 | 21.11.2026 24.11.2026 | 22-10-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 63 to 64 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | I-Block
15 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Ahmed Nagar | 14632 | 24.10.2026 26.10.2026 29.10.2026 | 20-10-2026 |  |  | For safety purpose during stringing of conductor for remodeling work from locatio No. 27 to 31 of 132kV T/Line New Wah to Bahtar More to Fateh Jang. | Ahmed Nagar
16 | IESCO | Attock | Taxila | Hassanabdal | New Wah | Col. Sher Khan | 14621 |  | 29-10-2026 05-11-2026 |  |  |  | Col. Sher Khan
1 | IESCO | Cantt | Tariqabad | R.A Bazar | 132KV GSS MES | New GHQ | 107605 | 24.10.2026 25.10.2026 31.10.2026 01.11.2026 07.11.2026 08.11.2026 14.11.2026 15.11.2026 21.11.2026 22.11.2026 28.11.2026 29.11.2026 |  | 09:00 | 17:00 | for Standby Duplicate Source trough 02x11 independent feeder IRO GHQ | New GHQ
1 | IESCO | NGC Rawat | Senior Manager Rawat |  | 750MVA. 500/220KV ATB-4 at 500KV GSS NGC Rawat |  |  | 23.10.2026 to 07.11.2026 (Continuous) |  | 23.10.2026 '0800 hrs | 07.11.2026 '1600 hrs | Installation of Tertiary Busbar of 750MVA, 500/220KV ATB-4 | No area will be affected | 150MW Load Management under N-2 Contigency Conditions across designed IESCO Distribution network.
1 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rwp | A.E (T) New Wah | 132 KV T/L New Wah – Mustehkam Cement Ckt (WAH-9 – ISO-101) |  |  | 25-10-2026 |  | 07:00 Hrs | 18:00 Hrs | Only for safety purpose for erection and stringing work between Loc. # 07 to 10 for remodeling of 132 KV AWC to Taxila portion | 132KV Mustehkam Cement will be affected.
2 |  |  |  |  | 132 KV T/L New Wah – Haripur Hattar (WAH-3 – HTR-1) | [7 empty] | No area will be affected as 132KV Harripur Hattar will be fed from Burhan side.
3 |  |  |  |  | 132 KV T/L New Wah – Taxila Ckt (WAH-4 – TXL-1) | [7 empty] | No area will be affected. However, 132 KV Taxila Grid will be fed from 220 KV/ 132 KV Sangjani GSS.
4 | IESCO | GSO Circle IESCO Islamabad | SS&TL Division IESCO Rwp | A.E (T) New Wah | 66 KV T/L New Wah – Haripur Ckt (WAH-11 – HRP-101) |  |  | 25-10-2026 |  | 07:00 Hrs | 09:00 Hrs | For safety purpose for stringing work of earth wire between Loc. # 06 to 07 for remodeling of 132 KV AWC to HMC Taxila portion. | No area will be affected. However, 66 KV GSS Haripur will be fed from Havelian side.
1 | IESCO | City | Westridge | Westridge | 132 KV KTM | Millatabad | 008616 | 04.11.2026 | 26.10.2026 31.10.2026 05.11.2026 14.11.2026 | 09:00 | 14:00 | for Emergency Work Peshawer Road Underpass Project | Misrial Road, Ilyas Colony, Lane 1,2,3 and surrounding area | The AM shut down shall be carried out dated 04.11.2026 Instead of 05.11.2026
2 | IESCO | City | Westridge |  |  | Dk. Chaudrian | 008621 | 26.10.2026 31.10.2026 | 28.10.2026 04.11.2026 11.11.2026 18.11.2026 22.11.2026 |  |  |  | Gulnar Colony, Qasim Market, Raja Akram Road, Roomi Lane, Seham Road and surrounding area | The AM shut down shall be carried out dated 05.11.2026 Instead of 04.11.2026
3 | IESCO | City | Westridge |  |  | Peshawer Road | 008612 | 26.10.2026 04.11.2026 | 31.10.2026 07.11.2026 14.11.2026 |  |  |  | Peshawer Road, Mehboob Lane, Lane No. 04 to 07 Mehboob Lane, Fazeelabad and surroundig area
1 | IESCO | IBD | Div-I | TARLAI | Tramri | TARMARI | 105503 | 23.10.2026 | 20.10.2026 25.10.2026 | 08:00 | 12:00 | Conversion of overhead 11 KV Feeders to Underground in front of DHA Margalla Orchards, Islamabad. | JAIGOT ROAD, GULBERAG, TAMMA, JABBI, PIRSHOWA
2 | IESCO | IBD | Div-I | TARLAI | Tramri | ISI | 105505 |  | 25.10.2026 |  |  |  | JAIGOT ROAD, GULBERAG, TAMMA, JABBI, PIRSHOWA
3 | IESCO | IBD | Div-I | TARLAI | Tramri | CHATTA BAKHTAWAR | 105507 |  | 25.10.2026 31.10.2026 |  |  |  | ROYAL AVENUE, ALSYED AVENUE, GULSHAN UL HAD | The A.M Shut down dated 26.10.2026 & 27.10.2026 is herby Cancelled
4 | IESCO | IBD | Div-I | TARLAI | TRAMMARI | KUND RAJGAN | 105522 | [5 empty] | NEW CHATTA, KUND RAJGAN,
5 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | CM Pak | 105509 | [5 empty] | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital.
6 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | Rehara | 105511 | [5 empty] | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital.
7 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | Kuri | 105506 |  | 25.10.2026 |  |  |  | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital. | The A.M Shut down dated 26.10.2026 is herby Cancelled
8 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | I.T Park | 105528 |  | 25.10.2026 31.10.2026 |  |  |  | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital. | The A.M Shut down dated 27.10.2026 is herby Cancelled
9 | IESCO | IBD | Div-I | Tarlai | 132 KV Tramri GS | King Hamad University | 105526 | [5 empty] | King Hamad University | The A.M Shut down dated 26.10.2026 & 27.10.2026 is herby Cancelled
10 | Div-I | IBD | Div-I | Tarlai | Trammari | Comsats | 105508 |  | 25.10.2026 |  |  |  | comsats etc
11 | IESCO | IBD | Div-I | TARLAI | Tramri | TARMARI | 105503 | 25.10.2026 | 20.10.2026 25.10.2026 | 09:00 | 14:00 |  | JAIGOT ROAD, GULBERAG, TAMMA, JABBI, PIRSHOWA
12 | IESCO | IBD | Div-I | TARLAI | Tramri | ISI | 105505 |  | 25.10.2026 |  |  |  | JAIGOT ROAD, GULBERAG, TAMMA, JABBI, PIRSHOWA
13 | IESCO | IBD | Div-I | TARLAI | Tramri | CHATTA BAKHTAWAR | 105507 |  | 25.10.2026 31.10.2026 |  |  |  | ROYAL AVENUE, ALSYED AVENUE, GULSHAN UL HAD | The A.M Shut down dated 26.10.2026 & 27.10.2026 is herby Cancelled
14 | IESCO | IBD | Div-I | TARLAI | TRAMMARI | KUND RAJGAN | 105522 | [5 empty] | NEW CHATTA, KUND RAJGAN,
15 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | CM Pak | 105509 | [5 empty] | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital.
16 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | Rehara | 105511 | [5 empty] | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital.
17 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | Kuri | 105506 |  | 25.10.2026 |  |  |  | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital. | The A.M Shut down dated 26.10.2026 is herby Cancelled
18 | IESCO | IBD | B/Kahu | B/K (U) | TARMARI | I.T Park | 105528 |  | 25.10.2026 31.10.2026 |  |  |  | Mohra Noor, Rehara, Kuri Sher, Zong H/Q, Behria Enclave, Isolation Hospital.
19 | IESCO | IBD | Div-I | Tarlai | 132 KV Tramri GS | King Hamad University | 105526 | [5 empty] | King Hamad University | The A.M Shut down dated 26.10.2026 & 27.10.2026 is herby Cancelled
20 | Div-I | IBD | Div-I | Tarlai | Trammari | Comsats | 105508 |  | 25.10.2026 |  |  |  | comsats etc
1 | IESCO | GSO Circle | SS&TL ISD | AE(T) No.2 | 11 KV Sub-Incoming of Power Transformer T-1 (31.5 /40MVA) At 132KV GSS I-8 | Following 11kv feedeers of T-1 will be affected |  | 23-10-2026 |  | 08:00 Hrs | 11:00 Hrs | For Coupling of 11 KV outgoing panel for newly constructed Holy Family Feeder
[6 empty] | FLOUR MILL-2 | 061130 | [5 empty] | Imran F/Mill, Al-Hiolal F/Mill, Arshad F/Mill, Kashmir F/Mill, Fine F/Mill,
[6 empty] | MUZAMMAL TOWN | 061133 | [5 empty] | MUZAMMAL TOWN
[6 empty] | A. F. O. H. S | 061131 | [5 empty] | Flacon Complex
[6 empty] | Sohan | 061134 | [5 empty] | Sohan & surrounding
[6 empty] | CCC-II | 061135 | [5 empty] | indepandent
1 | IESCO | GSO Circle | SS&TL ISD | AE(T) No.2 | 132KV University (E3Q1) - Taramri (TRC-1) & 132KV Taramri (TRC-2) - Bahria Enclave (BEN-2) along with related earth switch | Following 11kv feedeers of T-3 will be affected |  | 25-10-2026 |  | 08:00 Hrs | 11:00 Hrs | For safety purpose during erection of pole at T-off location and allied stringing work for new 132KV T/Line feed for Technopolis Grid Station
[6 empty] | Park Encl:1 | 105518 | [5 empty] | Park Enclave-1
[6 empty] | PHA-1 | 105519 | [5 empty] | PHA-1
[6 empty] | Isolation Hospital | 105520 | [5 empty] | Isolation Hospital
[6 empty] | PHA-II | [6 empty] | PHA-II
[6 empty] | Khadraper | 105523 | [5 empty] | Khadraper
[6 empty] | Waris Haveli | 105524 | [5 empty] | Waris Haveli
[6 empty] | Scheme-1 | 105525 | [5 empty] | Scheme-1
[6 empty] | King Hammad Uni. | 105526 | [5 empty] | King Hammad Uni.
[6 empty] | PARK Enclave-II | 105527 | [5 empty] | PARK Enclave-II
[6 empty] | IT Park | 105528 | [5 empty] | IT Park
[6 empty] | UC 2 | N.A | [5 empty] | UC 2
| IESCO | GSO Circle | SS&TL ISD | AE(T) No.2 | 132KV University (E3Q1) - Taramri (TRC-1) along with related earth switch |  |  | 25-10-2026 To 26-10-2026 (Contineous) |  | 25-10-2026 11:00 Hrs | 26-10-2026 16:00 Hrs | For Stringing Work | No area will be affected as 132KV GSS Taramari will be fed from 132KV Bahria Enclave side.
| IESCO | Isd | Barakahu | Barakahu Urban | Taramari | CM Pak Zong | 105509 | 26-10-2026 |  | 07:00 Hrs | 13:00 Hrs | For Stringing Work | CM Pak Zong
[6 empty] | Rehara | 105511 | [5 empty] | Rehara
[6 empty] | PHA-1 | 105519 | [5 empty] | PHA-1
[6 empty] | Isolation Hospital | 105520 | [5 empty] | Isolation Hospital
[6 empty] | IT Park | 105528 | [5 empty] | IT Park